## Discovery & Arivis Decommission
DISCOVERY DATA, ARIVIS, E3 LICENSES & SCHRÖDINGER ¦ AWS/AZURE DECOMMISSION ¦ FINANCIAL BUSINESS CASE
Prepared for Internal Review ¦ March 2026 ¦ Base case: Decommission all cost items. E3 Licenses (800 × $30/mo) & Schrödinger Azure ($1,800/mo): savings from Apr 2027 (employee transition). Arivis: customer pays from Apr 2027, fully decommissioned Q1 2028. Discovery AWS S3: purging/migration Q3 2027 – Q1 2028, savings from Q2 2028. SharePoint: 20TB freed — storage benefit only, no cost saving.
AWS ARIVIS (customer pays Apr 2027; fully decommissioned Q1 2028) |  | DISCOVERY AWS S3 (purging Q3 2027 – Q1 2028) |  | E3 LICENSES (800 × $30/mo from Apr 2027) |  | 5-YEAR NET SAVING (base case — 2026-2030)
$8,800 |  | $2,870 |  | $24,000 |  | $1,631,710
$8,800/mo native AWS (EC2+S3) customer takes over Apr 2027 |  | $2,870/mo 753.6 TiB post-migration purged Q1 2028 after sign-off |  | $24,000/mo 800 E3 licences × $30/mo saving from Apr 2027 |  | Gross $1,651,710 ¦ One-time −$20,000 ¦ Net $1,631,710
SCHRÖDINGER AZURE (2 RGs — from Apr 2027) |  | SHAREPOINT & OTHERS ¦ Note only — no cost saving
$1,800 |  | SharePoint 20TB storage freed — no direct cost impact, but free storage capacity available for other use.
$1,800/mo Schrödinger 2 RGs Azure saving from Apr 2027 |  | Storage benefit only. No recurring cost saving. Excluded from all financial calculations in this analysis.
Assumptions : "If direct migration decision made Oct 2026 (Azure/HubStor → customer storage), that migration expense is part of a separate initiative — NOT in this analysis. Only incremental AWS S3 bucket cost savings counted here."
SECTION 2 — 5-YEAR FINANCIAL PLAN (2026 – Dec 2030)
5-year plan: 2026–2030. 2026: No activity — baseline year ($0 saving). Arivis: customer assumes cost from Apr 2027, fully decommissioned Q1 2028 ($8,800/mo saving). E3 Licenses: 800 × $30 = $24,000/mo saving from Apr 2027 (employee transition). Schrödinger Azure: $1,800/mo saving from Apr 2027. Discovery AWS S3: $2,870/mo saving from Q2 2028 (purging/migration completes Q1 2028). SharePoint: 20TB freed — storage benefit only, no cost saving.
Period | Quarter | Arivis (AWS Cost) | E3 Licenses (Service Cost) | Schrödinger (Azure Cost) | Discovery (AWS S3 Cost) | Monthly Saving | Quarterly / Cumulative Saving
Q1 2027 | Jan-Mar 2027 (all still running — no savings) | $8,800 | -- | -- | $2,870 | -- | --
Q2 2027 | Apr-Jun 2027 ARIVIS → CUSTOMER E3 & SCHRÖDINGER START | Eliminated ($8,800 saved) | Eliminated ($24,000 saved) | Eliminated ($1,800 saved) | $2,870 | $34,600/mo | $103,800 / $103,800
Q3 2027 | Jul-Sep 2027 DISCOVERY PURGING STARTS (Arivis/E3/Schrödinger saving) | Eliminated ($8,800 saved) | Eliminated ($24,000 saved) | Eliminated ($1,800 saved) | $2,870 | $34,600/mo | $103,800 / $207,600
Q4 2027 | Oct-Dec 2027 DISCOVERY STILL PURGING (SharePoint — storage freed, no cost saving) | Eliminated ($8,800 saved) | Eliminated ($24,000 saved) | Eliminated ($1,800 saved) | $2,870 | $34,600/mo | $103,800 / $311,400
Q1 2028 | Jan-Mar 2028 ARIVIS FULLY DECOMMISSIONED DISCOVERY FINAL PURGE ⚠ Arivis migration one-time: $20,000 | Eliminated ($8,800 saved) | Eliminated ($24,000 saved) | Eliminated ($1,800 saved) | $2,870 | $34,600/mo (−$20,000 one-time) | Gross: $103,800 ¦ One-time: −$20,000 Net Q saving: $83,800 ¦ Cumul. Net: $395,200
2027 TOTAL | Jan-Dec 2027 | $79,200 (9 months) | $216,000 (9 months) | $16,200 (9 months) | $0 (still purging) | $311,400 | Cumulative: $311,400
Year | Period | Arivis Saving | E3 Licenses Saving | Schrödinger Saving | Discovery Saving | Gross Annual Saving | One-time Cost / Net / Cumul. Net
2026 | Jan-Dec 2026 | $0 | $0 | $0 | $0 | $0 | — / $0 / $0
2027 | Jan-Dec 2027 | $79,200 | $216,000 | $16,200 | $0 | $311,400 | — / $311,400 / $311,400
2028 | Jan-Dec 2028 | $105,600 | $288,000 | $21,600 | $25,830 | $441,030 | −$20,000 / Net $421,030 / Cumul. $732,430
2029 | Jan-Dec 2029 | $105,600 | $288,000 | $21,600 | $34,440 | $449,640 | — / $449,640 / Cumul. $1,182,070
2030 | Jan-Dec 2030 | $105,600 | $288,000 | $21,600 | $34,440 | $449,640 | — / $449,640 / Cumul. $1,631,710
5-YR TOTAL | 2026–2030 | $396,000 | $1,080,000 | $81,000 | $94,710 | $1,651,710 | −$20,000 / 5-YR NET: $1,631,710
PAYBACK < 1 month ($34,600 saving Apr 2027. One-time Arivis migration $20,000 recovered within 1 month of full savings.) |  |  |  | 5-YR GROSS: $1,651,710 ¦ ONE-TIME: −$20,000 ¦ 5-YR NET: $1,631,710 ¦ Annual (from Q2 2028): $449,640/yr
FINANCIAL SUMMARY & RECOMMENDED ACTIONS |  |  |  |  | Value at risk: $34,600/mo until E3 & Schrödinger confirmed (Apr 2027 target)
Current combined cost | $37,470/month ($8,800 Arivis + $24,000 E3 + $1,800 Schrödinger + $2,870 Discovery) Note: SharePoint $250 excluded — storage benefit only, no cost saving. |  |  |  | Every month of inaction = $11,920 of avoidable spend.
Arivis decommission | Apr 2027: Customer assumes cost ¦ Q1 2028: Fully transferred/decommissioned from AWS |  |  |  | $8,800/mo saving from Apr 2027 (customer takes over).
E3 Licenses (800 × $30/mo) | Apr 2027 — employee transition to customer/new platform |  |  |  | $24,000/mo saving from Apr 2027.
Schrödinger Azure (2 RGs) | Apr 2027 — Azure RGs decommissioned |  |  |  | $1,800/mo saving from Apr 2027.
Discovery purging/migration target | Q3 2027 – Q1 2028 — written sign-off from all 12 site owners |  |  |  | $2,870/mo saving from Q2 2028.
SharePoint & Others | 20TB storage freed — storage benefit only. No recurring cost saving. |  |  |  | No financial saving. Excluded from all calculations.
Full monthly saving (from Q2 2028) | $37,470/month = $449,640/year |  |  |  | All 4 cost items decommissioned (SP excluded — no cost saving).
5-year gross saving (2026-2030) | $1,651,710 |  |  |  | 2026=$0 baseline. One-time Arivis migration $20,000 charged Q1 2028.
5-year NET saving (after one-time cost) | $1,631,710 (gross $1,651,710 − $20,000 Arivis migration) |  |  |  | One-time $20,000 recovered within 1 month of full savings from Q2 2028.
RECOMMENDED ACTIONS | 1. Confirm E3 employee transition date with customer — target Apr 2027 2. Confirm Schrödinger Azure RG decommission with customer — target Apr 2027 3. Arivis: obtain written customer confirmation; initiate AWS cost handover Apr 2027; plan full decommission Q1 2028 4. Initiate sign-off process for all 12 Discovery site owners immediately (LEI, HER, GRO, KUO, SZG, FRE, LYO, EVR, FRI, CRP, HAR, PTH) 5. Legal: prepare data destruction certificate template for Discovery S3 purge
SECTION 3 — KEY ASSUMPTIONS
SCOPE NOTE ▶ "If a direct migration decision was made in Oct 2026 (Azure/HubStor → customer storage), that migration expense is part of a SEPARATE initiative — NOT included in this analysis. Only incremental AWS S3 bucket cost savings are counted here."
# | Assumption | Basis / Detail | Financial Impact if Wrong | Status
A1 | E3 licence cost = $30/user/mo × 800 users = $24,000/mo from Apr 2027 | Assumes all 800 E3 licences are formally cancelled / transitioned as part of the employee handover programme in Apr 2027. Unit cost and headcount verified with IT/Procurement. | Each 100-user variance = $3,600/mo = $180,000 over 5 years. Confirm exact count before sign-off. | Estimate — verify from IT/Procurement
A2 | Arivis AWS cost = $8,800/mo; customer assumes from Apr 2027; one-time migration = $20,000 in Q1 2028 | Active AWS bill (EC2 + S3) confirmed. Customer formally takes over payment from Apr 2027. Full technical decommission and data migration completed Q1 2028 at a one-time cost of $20,000. | Cost overrun on migration: every additional $10,000 reduces 5-yr net by $10,000. Delay in handover: each quarter = $26,400 avoidable spend. | Confirmed — monitor migration scope
A3 | Schrödinger Azure = $1,800/mo; both RGs decommissioned Apr 2027 | Assumes both Azure Resource Groups are fully shut down when new company platform is live and validated. Cost verified from Azure Cost Management. No residual RG charges after Apr 2027. | Each $500/mo variance = $30,000 over 5 years. Validate Azure billing before presenting externally. | Estimate — verify from Azure billing
A4 | Discovery AWS S3 purging Q3 2027 – Q1 2028; saving $2,870/mo from Q2 2028 | All 12 site data owners (LEI, HER, GRO, KUO, SZG, FRE, LYO, EVR, FRI, CRP, HAR, PTH) provide written sign-off. 753.6 TiB permanently deleted. Deletion certificate issued. S3 cost eliminated from Q2 2028. | Without sign-off purge cannot proceed. Each quarter of delay = $8,610 avoidable S3 cost. If new company needs data, up to $45,000 migration cost may apply (separate initiative). | CRITICAL — initiate sign-off now
A5 | AWS and Azure pricing held flat 2026–2030; SharePoint has no recurring cost saving | AWS S3 and EC2 pricing assumed constant (AWS has historically reduced prices — conservative assumption). Azure pricing flat. SharePoint 20TB freed is a storage benefit only; no licence cost saving has been confirmed and it is excluded from all financial calculations. | If AWS/Azure prices fall (likely): actual savings higher than modelled. If SharePoint cost saving is confirmed in future, up to $250/mo ($12,500 over 5 years) additional upside available. | Conservative — upside only
SECTION 4 — TOP 5 RISKS
# | Risk | Likelihood | Impact | Score | Mitigation | Residual | Owner
R1 | E3 employee transition delayed beyond Apr 2027 800 licences × $30/mo = $24,000/mo avoidable spend per month of delay. | MEDIUM | HIGH | HIGH | Confirm employee transition go-live date with customer immediately. Escalate to Programme Director if not confirmed by Jan 2027. Track weekly — each month of delay = $24,000 avoidable cost. | MEDIUM | IT / Programme Director
R2 | Arivis migration overruns $20,000 budget or slips beyond Q1 2028 Scope creep or data complexity could inflate the one-time migration cost or delay full decommission. | MEDIUM | MEDIUM | MODERATE | Define migration scope and fix-price contract before Q4 2027. Assign dedicated technical lead. Establish weekly milestone check-ins from Oct 2027. Any overrun > $5,000 requires Programme Director approval. | LOW | Cloud Arch / Programme Director
R3 | Discovery data purge delayed — sign-off not obtained from all 12 site owners Each quarter of delay = $8,610 avoidable S3 cost. Irreversible deletion requires 100% sign-off. | MEDIUM | HIGH | HIGH | Initiate sign-off process immediately — do not wait for technical readiness. Legal to issue standard destruction approval template. Track per-site completion weekly. QA and Legal must co-sign destruction certificate. | LOW | Legal / QA / Programme Manager
R4 | Schrödinger Azure RG decommission delayed — new platform not ready by Apr 2027 $1,800/mo avoidable Azure cost per month of delay. | LOW | MEDIUM | MODERATE | Validate new company platform readiness for Schrödinger workloads at least 4 weeks before planned decommission. Hard rule: platform must be live and user-validated minimum 2 weeks before RG deletion. | LOW | Cloud Arch / New Company
R5 | New company requires Discovery data — additional migration cost triggered If new company needs the 753.6 TiB of Discovery S3 data, an out-of-scope migration cost applies. Note: if direct migration decision was made in Oct 2026 (Azure/HubStor to customer storage), this cost belongs to the other initiative. | LOW | HIGH | HIGH | Obtain written confirmation from new company on data requirements before any purge planning begins. If data is needed and falls within this initiative, budget additional cost and adjust timeline. If covered by the Oct 2026 initiative, document scope boundary explicitly. | LOW | Programme Director / Legal
SECTION 5 — MONEY STEPS & HOW WE MEASURE SUCCESS
Each step below unlocks a specific saving. The measure column defines exactly how finance/ops confirms the saving has been realised.
Step | Action / Trigger | Saving Unlocked | Target Date | How We Measure It | Evidence Required | Owner | Status
MS-1 | E3 employee transition completed — 800 licences cancelled / reassigned to new platform | $24,000/mo ($288,000/yr) | Apr 2027 | 1. Monthly IT licence report shows 800 fewer E3 licences active 2. Microsoft/O365 billing reduced by ≥$24,000/mo 3. AWS Cost Explorer shows no E3-related infrastructure charges | IT licence reconciliation report; updated Microsoft invoice; Finance confirmation of reduced billing | IT / Programme Director | PENDING
MS-2 | Arivis AWS cost handed to customer — AWS bill transferred to customer account | $8,800/mo ($105,600/yr) | Apr 2027 | 1. AWS Cost Explorer: Arivis EC2+S3 line items show $0 on our account 2. Customer confirms receipt of AWS account/billing ownership 3. Finance monthly reconciliation excludes Arivis AWS charges | AWS billing dashboard screenshot; customer written confirmation of cost ownership; Finance sign-off | Cloud Arch / Finance | PENDING
MS-3 | Schrödinger Azure RGs decommissioned — both resource groups deleted after new company platform validated | $1,800/mo ($21,600/yr) | Apr 2027 | 1. Azure Cost Management: both RGs show $0 charges post-deletion 2. New company platform confirmed live and Schrödinger workloads migrated 3. Azure subscription billing reduced by ≥$1,800/mo | Azure portal deletion confirmation; Azure invoice showing $0 for both RGs; new platform sign-off by Schrödinger user team | Cloud Arch / New Company | PENDING
MS-4 | Arivis full decommission + one-time migration cost incurred — AWS instance terminated, data migrated, $20,000 invoice settled | Completes Arivis saving (+ $20K cost) | Q1 2028 | 1. AWS EC2 instance terminated — confirmed in AWS console 2. All S3 data deleted or migrated — deletion certificate issued 3. Migration vendor invoice of $20,000 paid and recorded in Finance 4. Net saving from Q2 2028 onwards = $8,800/mo fully realised | AWS console termination screenshot; S3 deletion certificate; paid migration invoice; Finance cost ledger entry | Cloud Arch / Finance / Legal | PENDING
MS-5 | Discovery AWS S3 purge complete — all 12 site data owners signed off, 753.6 TiB deleted | $2,870/mo ($34,440/yr) | Q1 2028 (saving from Q2 2028) | 1. Written sign-off received from all 12 site owners (LEI, HER, GRO, KUO, SZG, FRE, LYO, EVR, FRI, CRP, HAR, PTH) 2. AWS S3 bucket confirmed empty — Cost Explorer shows $0 Discovery S3 charges 3. Data destruction certificate issued by Legal/QA 4. Finance confirms $2,870/mo saving on AWS bill from Apr 2028 | All 12 sign-off documents; AWS S3 Cost Explorer screenshot ($0); Legal destruction certificate; Finance billing reconciliation | Legal / QA / Programme Manager | PENDING
SECTION 6 — INTERDEPENDENCIES
These items must be resolved in the right sequence. A delay in any upstream dependency directly delays its downstream savings.
ID | This Item | Depends On | Nature of Dependency | If Dependency Fails / Delays | Mitigation | Sequence | Priority
ID-1 | E3 Licence Saving ($24,000/mo from Apr 2027) | Employee transition programme go-live date confirmed by new company | Hard dependency — E3 saving cannot start until employees formally transition. No transition = no licence cancellation. | Saving delayed month-for-month. Each month slip = $24,000 lost saving. Risk to $216,000 of 2027 savings. | Secure written go-live commitment from new company by Jan 2027. Escalate to CIO / Programme Board if not confirmed. | 1st — gates all 2027 savings | CRITICAL
ID-2 | Arivis AWS cost handover ($8,800/mo from Apr 2027) | E3 transition confirmed AND new company platform operational for Arivis image analysis capability | Arivis handover is part of the same Apr 2027 transition event. New company must have a working replacement before we hand over / terminate the AWS instance. | If platform not ready, Arivis AWS cost continues at $8,800/mo. Each quarter of delay = $26,400 avoidable spend. Also risks $20,000 migration budget if scope changes. | Validate new company platform readiness 4 weeks before Apr 2027. Hard rule: platform live + user-validated 2 weeks before handover. Escalate to Programme Board if not on track by Mar 2027.
ID-3 | Schrödinger Azure decommission ($1,800/mo from Apr 2027) |  |  |  | Run platform validation for Schrödinger workloads in parallel with Arivis validation. Independent sign-off from Schrödinger team.
ID-4 | Arivis full decommission + $20K migration (Q1 2028) |  |  |  | Obtain customer data requirements decision by Sep 2027. Engage migration supplier by Oct 2027. Fix-price contract with defined scope.
ID-5 | Discovery S3 purge ($2,870/mo from Q2 2028) |  |  |  | Initiate sign-off process immediately — parallel to technical preparation. Legal to issue template to all 12 owners by Q2 2027. Track completion per site weekly. Do not let this become the critical path.
ID-6 | Oct 2026 direct migration initiative (Azure/HubStor → customer storage) |  |  |  | Document scope boundary explicitly with Finance and Programme Board. Confirm in writing which initiative owns the migration cost. Ensure this business case is updated if scope boundary changes.