## Discovery & Arivis Decommission
DISCOVERY DATA & ARIVIS ¦ POST-MIGRATION AWS DECOMMISSION ¦ Purge vs Transfer Decision
Context: Migration complete. Discovery (753.6 TiB) and Arivis already on AWS. Decision: PURGE from AWS or TRANSFER to vendor. Costs confirmed: Discovery $2,870/mo · Arivis $8,800/mo.
DISCOVERY AWS S3 (post-migration storage) |  | AWS ARIVIS (compute + storage + licence) |  | COMBINED MONTHLY SAVING (both eliminated) |  | 5-YEAR GROSS SAVING (no migration cost needed)
$2,870 |  | $8,800 |  | $11,670 |  | $577,380
$2,870/mo · 753.6 TiB · eliminated Q3 2027 |  | $8,800/mo active AWS bill · eliminated Q1 2028 |  | $140,040/yr · pure AWS cost elimination |  | Net after transfer cost: $482,380–$527,380
CURRENT STATE — What is on AWS today (migration complete)
Item | Discovery Data — AWS S3 |  |  |  | Arivis — AWS Platform
Volume / scope | 753.6 TiB · LEI, HER, GRO, KUO, SZG, FRE, LYO, EVR (WestEurope) FRI (GermanyWC) · CRP, HAR, PTH (UKSouth Discovery) |  |  |  | Full Arivis image analysis platform EC2 compute + S3 image data + licensing
Monthly AWS cost | $2,870/month (S3 Standard / IA / Glacier tiers) |  |  |  | $8,800/month (EC2 + S3 + licence)
Why on AWS | Migrated as part of main programme. Vendor platform not yet contracted. |  |  |  | Migrated to AWS. Needs permanent home — AWS or vendor.
Still needed? | Yes — scientific research data. Cannot delete without data owner sign-off. |  |  |  | Yes — active research tool. Cannot terminate without vendor alternative ready.
Decision required | PURGE (delete from AWS) — requires governance sign-off from all 12 site owners OR TRANSFER to vendor platform |  |  |  | PURGE Arivis AWS — vendor must be ready before termination OR TRANSFER workload to vendor platform
THE DECISION — Option A: Purge from AWS vs Option B: Transfer to Vendor
ASSUMPTION: Data owners confirm Discovery data disposition. ASSUMPTION: Arivis vendor equivalent available before AWS termination. Both options eliminate AWS cost — difference is data preservation.
| Criterion | Option A — PURGE from AWS | Option B — TRANSFER to Vendor
Discovery | Action | Delete all 753.6 TiB from AWS S3 (s3 rm --recursive) |  |  | Transfer 753.6 TiB to new vendor platform
| AWS cost after | $0/mo — eliminated immediately on deletion |  |  | $0/mo on AWS — vendor platform cost applies
| One-time cost | < $50 API fees + ~$2,000 IT labour |  |  | Est. $40,000–$80,000 egress + vendor ingestion
| Data preserved? | No — permanently deleted. Full governance sign-off required from all 12 site owners. |  |  | Yes — data moves intact to vendor platform
| Risk | Irreversible. Wrong sign-off = permanent data loss. Regulatory / GxP exposure. |  |  | Vendor delay · transfer cost · timeline risk
Arivis | Action | Terminate EC2 + delete S3 after confirmed backup |  |  | Export workload + data to vendor Arivis equivalent
| AWS cost after | $0/mo — Arivis AWS eliminated |  |  | $0/mo on AWS — vendor Arivis cost applies
| One-time cost | ~$2,000 IT labour for controlled shutdown |  |  | Est. $5,000–$15,000 vendor setup + data export
| Service continuity | Unavailable after termination — vendor must be live first |  |  | 2-week parallel run — seamless cutover
RECOMMENDED APPROACH (subject to data owner sign-off)
DISCOVERY: Recommend Option B (Transfer to vendor) unless data owners confirm data is duplicated and can be permanently destroyed. Purging 753.6 TiB of scientific research data is irreversible — governance risk is too high without certainty. Target Q3 2027 vendor transfer. ARIVIS: Recommend controlled transfer (Option B) — run vendor Arivis in parallel 2 weeks before terminating AWS. If vendor not ready by Q4 2027, defer AWS termination rather than risk service loss.
PHASED COST ELIMINATION TIMELINE (vendor selection dependent)
Discovery transfer Q3 2027 → $2,870/mo saving. Arivis transfer Q1 2028 → $8,800/mo saving. Full $11,670/mo from Jan 2028.
Period
Month
Discovery $2,870/mo
Arivis $8,800/mo
Total AWS Cost
Monthly Saving
Cumulative Saving
Notes
Now | Mar 2026 | $2,870 | $8,800 | $11,670 | — | — | Both active. Decision required.
Q2 2027 | Apr–Jun 2027 | $2,870 | $8,800 | $11,670 | — | — | Vendor onboarding. Still paying AWS.
Q3 2027 | Jul–Sep 2027 | $0 | $8,800 | $8,800 | $2,870 | $8,610 | Discovery transferred/purged. Phase 1 saving.
Q4 2027 | Oct–Dec 2027 | $0 | $8,800 | $8,800 | $2,870 | $17,220 | Arivis parallel run with vendor starts.
Q1 2028 | Jan–Mar 2028 | $0 | $0 | $0 | $11,670 | $52,230 | Arivis AWS terminated. Both gone. Full saving.
Q2 2028+ | Apr 2028+ | $0 | $0 | $0 | $11,670 | Growing | Full $11,670/mo continues.
5-YEAR SAVINGS PROJECTION (Jul 2027 – Dec 2031)
Phase 1 (6 months Discovery, Q3–Q4 2027): $17,220. Full saving from Jan 2028: $11,670/mo. 5-year gross: $577,380. Net (after max transfer $95K): $482,380.
Period
Calendar
Discovery Saving
Arivis Saving
Annual Saving
Cumulative Saving
Notes
Phase 1 (partial) | Jul–Dec 2027 (6 months) | $17,220 | — | $17,220 | $17,220 | Discovery eliminated Q3 2027. Arivis still running.
Year 1 | Jan–Dec 2028 | $34,440 | $105,600 | $140,040 | $157,260 | First full year — both items eliminated from AWS.
Year 2 | Jan–Dec 2029 | $34,440 | $105,600 | $140,040 | $297,300 | Full saving continues.
Year 3 | Jan–Dec 2030 | $34,440 | $105,600 | $140,040 | $437,340 | Saving continues.
Year 4 | Jan–Dec 2031 | $34,440 | $105,600 | $140,040 | $577,380 | 4 full years post-decommission.
5-YR TOTAL | Jul 2027–Dec 2031 | $154,980 | $422,400 | $577,380 | $577,380 | Net after transfer cost (~$50–95K): $482,380–$527,380
KEY ASSUMPTIONS (must be validated before any data deletion)
#
Assumption
Detail & Implication
If Wrong — Impact
Status
A1 | Migration complete — all Discovery + Arivis data is on AWS | Discovery (753.6 TiB) and Arivis fully migrated to AWS. No data still on Azure/HubStor. Azure costs ceased. | If migration incomplete, both AWS and Azure costs running. | ✅ Confirmed — migration complete
A2 | Discovery AWS S3 cost = $2,870/mo (confirmed) | Actual AWS S3 storage cost for 753.6 TiB across Standard/IA/Glacier. Confirmed from provided data. | If actual differs, all savings calculations change. | ✅ Confirmed from provided data
A3 | Arivis AWS cost = $8,800/mo (confirmed) | Arivis running on AWS EC2+S3 billing $8,800/mo. Active recurring AWS bill to be eliminated. | If billing changed, confirm from AWS console. | ✅ Confirmed from provided data
A4 | Data owners must sign off before any deletion | Written approval from all 12 site data owners required before deleting Discovery data. LEI, HER, GRO, KUO, SZG, FRE, LYO, EVR, FRI, CRP, HAR, PTH. Irreversible action. | Without sign-off: Option A unavailable. Purge without approval = regulatory violation. | ⚠ CRITICAL — initiate NOW
A5 | Vendor platform available for Discovery by Q3 2027 | For Option B, vendor must be contracted and onboarding completed by Q2 2027. | Each month slip = $2,870 additional AWS Discovery cost. | ⚠ Dependent on vendor selection
A6 | Arivis vendor equivalent ready by Q1 2028 | Vendor Arivis platform live and user-validated for 2 weeks before AWS termination. | Each month slip = $8,800 additional Arivis AWS cost. | ⚠ Must be contracted
A7 | Purge (Option A) cost is negligible | S3 delete API calls < $50. IT labour ~$2,000 documented deletion. No egress fees. | No material impact — Option A always cheapest upfront. | ✅ Confirmed
A8 | Transfer (Option B) cost est. $50K–$95K one-time | Discovery: $40–80K egress+ingestion. Arivis: $5–15K setup. Payback < 1 month of full saving. | If vendor charges more, payback period extends. Still < 12 months in worst case. | ⚠ Vendor quote required
TOP 5 KEY RISKS
#
Risk
Likelihood
Impact
Score
Mitigation
Residual
Owner
R1 | Data deletion without full governance sign-off Purging 753.6 TiB of scientific data without written sign-off from all 12 site owners is irreversible. GxP, GDPR and data governance breach possible. | MEDIUM | CRITICAL | 🔴 CRITICAL | Mandatory written sign-off from ALL site data owners before deletion. QA+Legal review. Option B (transfer) removes this risk entirely. | LOW | Legal / QA / Data Owners
R2 | Vendor not selected in time — Q3 2027 Discovery transfer at risk Each month of vendor slip costs $2,870 in ongoing AWS Discovery S3 storage. | HIGH | HIGH | 🔴 HIGH | Treat vendor selection as programme critical path. Target signed contract Q2 2026 for Q3 2027 transfer readiness. | MEDIUM | Programme Director
R3 | Arivis AWS terminated before vendor platform ready Research teams lose image analysis capability — active scientific workflow disruption. | LOW | HIGH | 🔴 HIGH | Hard rule: vendor Arivis must be live and user-validated for 2 weeks before AWS termination. Sequence locked in project plan. | LOW | Cloud Arch / Arivis Team
R4 | Discovery storage cost higher than $2,870/mo Retrieval patterns or lifecycle misconfiguration could push actual S3 cost above estimate. | LOW | MEDIUM | 🟡 MODERATE | Set AWS Cost Anomaly alert at $4,000/mo. Review S3 Storage Lens monthly. Validate lifecycle rules weekly for first month. | LOW | Cloud Arch
R5 | Vendor transfer cost exceeds $95K estimate Premium ingestion rates for 753 TiB or data transformation requirements could increase cost. | LOW | MEDIUM | 🟡 MODERATE | Obtain vendor quotation before commitment. Negotiate volume discount. Even at 2× estimated cost, payback < 2 months. | LOW | Finance / Cloud Arch
KEY ACTIONS — Immediate steps to realise savings
Priority
Action
Owner
Deadline
Impact if delayed
Status
🔴 CRITICAL | Initiate written sign-off from all 12 Discovery site data owners (required before either Option A or B) | Data Owners / Legal | Immediate | Blocks all options. Cannot proceed without this. | Not started
🔴 CRITICAL | Confirm Arivis AWS cost ($8,800/mo) from live AWS billing console | Finance | Immediate | All financial projections use this figure. | Not started
🔴 CRITICAL | Select and contract vendor platform — must cover Discovery 753.6 TiB + Arivis equivalent | Programme Director | Q2 2026 | Q3 2027 Discovery saving at risk — $2,870 per month slipped | Not started
🔴 HIGH | Legal / QA review of data destruction process if Option A (purge) is chosen | Legal / QA | Q3 2026 | Irreversible deletion without review = regulatory risk | Not started
⚠ HIGH | Obtain vendor quotation for Discovery transfer + Arivis onboarding cost | Cloud Arch + Vendor | Q3 2026 | Cannot finalise Option A vs B without knowing transfer cost | Not started
⚠ HIGH | Lock Arivis vendor delivery date in contract — target AWS termination Jan 2028 | Legal / Programme Dir | Q4 2026 | Each month slip = $8,800 additional Arivis AWS cost | Not started
✅ PROCEED | Set AWS Cost Anomaly alerts: Discovery $4K/mo threshold · Arivis $10K/mo threshold | Cloud Arch | Now | Monitoring only — no financial impact | Ready