## Discovery & Arivis Decommission
DISCOVERY DATA & ARIVIS ¦ AWS DECOMMISSION ¦ FINANCIAL BUSINESS CASE
Prepared for Internal Review ¦ March 2026 ¦ Base case: PURGE all items. Arivis: purged end of Q2 2027 on new company confirmation. Discovery: purging/migration Q3 2027 – Q1 2028 after data owner sign-off. SharePoint & Others: decommission starts Q3 2027. Conditional: if new company requires data, add $45K migration cost + 1Q Discovery slip.
AWS ARIVIS (purged end Q2 2027) |  | DISCOVERY AWS S3 (purging Q3 2027 – Q1 2028) |  | SHAREPOINT & OTHERS (decommission from Q3 2027) |  | 4-YEAR NET SAVING (base case — purge only)
$8,800 |  | $2,870 |  | $250 |  | $474,060
$8,800/mo native AWS (EC2+S3) purged Apr 2027 on new company confirmation |  | $2,870/mo 753.6 TiB post-migration purged Jul 2027 after sign-off |  | $250/mo SharePoint sites & others decommission from Q3 2027 |  | Gross $474,060 No purge cost Payback < 1 month
SECTION 1 — WHAT IS BEING PURGED AND WHEN
| AWS Arivis |  |  |  | Discovery Data — AWS S3
What it is | Arivis image analysis platform. Originally implemented natively on AWS (EC2 + S3). Active running service. |  |  |  | 753.6 TiB of Discovery site scientific data on AWS S3 (post-migration). LEI, HER, GRO, KUO, SZG, FRE, LYO, EVR · FRI · CRP, HAR, PTH
Monthly AWS cost | $8,800/month (EC2 + S3 — active AWS bill) |  |  |  | $2,870/month (S3 Standard / IA / Glacier — post-migration estimate)
Why purged | New company platform replaces Arivis capability. AWS instance and data no longer required once new company confirms. |  |  |  | Post-migration data no longer required on AWS. New company has confirmed they do not need this data.
Key prerequisite | Written confirmation from new company that they do not need Arivis data or functionality from AWS. This is the single gate for purge. |  |  |  | Written sign-off from ALL 12 site data owners: LEI, HER, GRO, KUO, SZG, FRE, LYO, EVR, FRI, CRP, HAR, PTH Confirming data is not required and can be permanently deleted.
What happens to data | AWS Arivis EC2 instance terminated. All S3 data deleted after confirmed backup by Arivis team. Irreversible. |  |  |  | All 753.6 TiB permanently deleted from AWS S3. Deletion certificate issued. Irreversible.
Target date | End of Q2 2027 (June 2027) |  |  |  | Q3 2027 – Q1 2028 (July 2027 – March 2028) Fully decommissioned by end Q1 2028
One-time cost | $0 (No data transfer. EC2 termination and S3 delete are standard AWS operations.) |  |  |  | $0 base case (Conditional: ~$45,000 if migration required for all Discovery sites)
SharePoint Site & Others — Decommission starting Q3 2027 ¦ Monthly saving: $250/mo ¦ Starts same time as Discovery purging
SECTION 2 — 4-YEAR FINANCIAL PLAN (Q2 2027 – Dec 2030)
Updated base case: purge all items. Arivis saving from Q3 2027 ($8,800/mo — purged end Q2 2027). SharePoint & Others decommissioned Q4 2027 ($250/mo saving from Q4 2027). Discovery saving from Q2 2028 ($2,870/mo — purging/migration completes Q1 2028). Full $11,920/mo from Q2 2028.
Period | Quarter | Arivis $8,800/mo | Discovery $2,870/mo | SharePoint & Others $250/mo | Monthly Saving | Quarterly Saving | Cumul. Saving
Q1 2027 | Jan-Mar 2027 (all still running) | $8,800 | $2,870 | $250 | -- | -- | --
Q2 2027 | Apr-Jun 2027 ARIVIS PURGED (end of Q2) | $8,800 | $2,870 | $250 | -- | -- | --
Q3 2027 | Jul-Sep 2027 ARIVIS SAVING STARTS DISCOVERY PURGING SHAREPOINT STARTS | $0 | $2,870 | $250 | $8,800/mo | $26,400 | $26,400
Q4 2027 | Oct-Dec 2027 DISCOVERY STILL PURGING SHAREPOINT DECOMMISSIONED | $0 | $2,870 | $0 | $9,050/mo | $27,150 | $53,550
Q1 2028 | Jan-Mar 2028 DISCOVERY LAST PURGE QUARTER | $0 | $2,870 | $0 | $9,050/mo | $27,150 | $80,700
2027 TOTAL | Jan-Dec 2027 | $0 | $0 | $750 | Avg $4,463/mo | $53,550 | $53,550
Year | Period | Arivis Saving | Discovery Saving | SharePoint & Others Saving | Gross Annual Saving | One-time Cost | Net Annual Saving / Cumulative
2027 | Jan-Dec 2027 | $52,800 | $0 | $750 | $53,550 | $0 | $53,550 / $53,550
2028 | Jan-Dec 2028 | $105,600 | $25,830 | $3,000 | $134,430 | One-time Cost | $134,430 / $187,980
2029 | Jan-Dec 2029 | $105,600 | $34,440 | $3,000 | $143,040 | -- | $143,040 / $331,020
2030 | Jan-Dec 2030 | $105,600 | $34,440 | $3,000 | $143,040 | -- | $143,040 / $474,060
4-YR TOTAL | 2027-2030 | $369,600 | $94,710 | $9,750 | $474,060 | $0 | $474,060
PAYBACK < 1 month ($9,050 first full month saving from Q3 2027 — no purge cost) |  |  |  | ANNUAL SAVING (from Q2 2028): $143,040/yr 4-YR GROSS: $474,060 4-YR NET: $474,060
CONDITIONAL SCENARIO — If New Company Requires the Data
If the new company confirms they REQUIRE Discovery or Arivis data: add one-time migration cost of $45,000 (data export/transfer for all Discovery sites) AND Discovery purge slips by 1 quarter to Q2 2028. Arivis purge date unchanged (end Q2 2027 — AWS infrastructure only). SharePoint & Others decommission unaffected.
Item | Base Case (purge only) | Conditional (new company needs data) | Difference | Note
Arivis purge date | End Q2 2027 (Jun) | End Q2 2027 (Jun) | No change | Arivis is AWS infrastructure. Purge unaffected by data requirement.
Discovery purge date | Q3 2027 – Q1 2028 | Q3 2027 – Q2 2028 (slips 1 quarter) | Slips 1 quarter | 1 extra quarter of Discovery S3 cost = $2,870 × 3 = $8,610.
Additional migration cost | $0 | $45,000 | −$45,000 | Data export / transfer to new company platform for all Discovery sites. One-time.
Total one-time cost | $0 | ~$45,000 | −$45,000 | Migration cost only. No purge labour cost.
2027 gross saving | $53,550 | $53,550 | No change | Discovery had no savings in 2027 in either scenario — no impact on 2027 gross.
2027 net saving | $53,550 | $53,550 | No change | One-time cost charged in 2028 when migration occurs.
4-year gross saving | $474,060 | $465,450 | −$8,610 | Only Q2 2028 Discovery saving is lost (1Q slip).
4-year NET saving | $474,060 | $420,450 | −$53,610 | Net impact = $8,610 lost saving + $45,000 migration = $53,610 total reduction.
Payback | < 1 month | ~5 months | Longer payback | $45K one-time vs $11,920/mo full saving from Q2 2028.
CONCLUSION: Even if the new company requires data, the 4-year net saving remains $420,450 — still a very strong business case. The migration cost of $45,000 is recovered in approximately 5 months. This analysis should not materially change the decision to proceed.
SECTION 3 — KEY ASSUMPTIONS & RISKS
Assumptions
# | Assumption | Basis / Detail | Financial Impact if Wrong | Status
A1 | Arivis was natively implemented on AWS (EC2+S3) | Arivis has run on AWS since original implementation — not a migrated workload. Decommission is straightforward: terminate EC2, delete S3 data. No data transfer from another platform required. | No impact — confirmed fact. | Confirmed
A2 | Arivis AWS cost = $8,800/mo (EC2 + S3, no licence) | Active AWS bill covering EC2 compute and S3 storage only. Verify current figure from live AWS Cost Explorer before presenting externally. | Each $1,000/mo variance = $60,000 over 5 years. | Confirmed — verify from billing
A3 | New company has confirmed they do NOT need the data (key assumption) | This is the fundamental assumption underpinning the purge decision. Both Arivis and Discovery purge require explicit written confirmation from the new company that they do not require access to or copies of this data. If they need the data, see Conditional Scenario in Section 2. | If new company DOES need data: add $45,000 migration cost + Discovery slips 1Q → net 4-yr saving reduces by $53,610 but remains $420,450. | CRITICAL — written confirmation required
A4 | Arivis purged end of Q2 2027 — triggered by new company confirmation | No fixed calendar date. Triggered when new company provides written confirmation. EC2 termination and S3 deletion takes days once confirmed. End of Q2 2027 is the plan assumption. | Each quarter of delay = $27,150 avoidable cost (Arivis $8,800 + SharePoint $250 × 3 months). | Warning — track new company weekly
A5 | Discovery AWS S3 cost = $2,870/mo | Estimated AWS S3 storage cost for 753.6 TiB post-migration across Standard/IA/Glacier tiers. Monitor actual from AWS Cost Explorer once migration is live. | Each $1,000/mo variance = $60,000 over 5 years. Set anomaly alert at $4,000/mo. | Confirmed estimate — monitor
A6 | Discovery purging/migration Q3 2027 – Q1 2028 — requires sign-off from all 12 site owners | LEI, HER, GRO, KUO, SZG, FRE, LYO, EVR, FRI, CRP, HAR, PTH must each provide written approval. Purging/migration spans Q3 2027 to Q1 2028. AWS cost of $2,870/mo continues until completion. | Without sign-off: purge cannot proceed. Discovery savings only begin Q2 2028. Each quarter of delay = $8,610 avoidable cost. | CRITICAL — initiate sign-off now
A7 | Purge only — no data transfer unless new company requests it | Both Arivis and Discovery data will be permanently deleted from AWS. No vendor migration, no egress fees, no ingestion costs. SharePoint & Others decommissioned separately. If the new company requires data, the Conditional Scenario applies ($45K additional cost). | If conditional scenario triggered: net 5-yr saving reduces by $53,220 to $564,630. Still strongly positive. | Confirmed — purge is the plan
A8
A9
Top 5 Risks
# | Risk | Likelihood | Impact | Score | Mitigation | Residual | Owner
R1 | New company confirmation delayed beyond end Q2 2027 Arivis purge triggered by new company written confirmation. Each quarter of delay = $27,150 avoidable AWS cost ($8,800 Arivis + $250 SharePoint × 3 months). | HIGH | HIGH | CRITICAL | Escalate to Programme Director. Engage new company with specific deadline. Include live AWS Arivis cost in every client onboarding status update. Each week without confirmation is a quantified financial loss. | MEDIUM | Programme Director / New Company
R2 | New company states they need the data (conditional scenario triggered) If new company requires Discovery or Arivis data, $45K migration cost applies and Discovery purge slips 1 quarter. Net 5-yr saving reduces by $53,220. | MEDIUM | MEDIUM | MODERATE | Obtain written confirmation from new company on data requirements as first action — before any purge planning. If data is needed, activate conditional scenario budget ($45K). Still a very strong business case either way. | LOW | Programme Director / New Company
R3 | Discovery data purged without full governance sign-off 753.6 TiB permanently deleted without written approval from all 12 site data owners. Irreversible. GxP / GDPR breach possible. | LOW | CRITICAL | HIGH | Mandatory written sign-off from all 12 site owners before deletion. QA and Legal to review and sign off on destruction certificate. Initiate sign-off process immediately — do not wait for technical readiness. | LOW | Legal / QA / Data Owners
R4
R5
R6 | SharePoint & Others actual saving lower than estimated $250/mo is an estimate. Actual decommission saving could be lower if only partial services are removed. |  |  |  | Verify exact SharePoint & associated service costs from IT/licensing records before finalising business case. Immaterial to overall case even if zero.
FINANCIAL SUMMARY & RECOMMENDED ACTIONS |  |  |  |  | Value at risk: $27,150 per quarter of new company confirmation delay
Current combined cost | $11,920/month ($8,800 Arivis + $2,870 Discovery S3 + $250 SharePoint & Others) |  |  |  | Every month of inaction = $11,920 of avoidable spend.
Arivis purge target | End Q2 2027 (June) — triggered by new company written confirmation |  |  |  | $8,800/mo saving from Q3 2027 (Jul). 74% of total combined saving.
Discovery purging/migration target | Q3 2027 – Q1 2028 — written sign-off from all 12 site owners |  |  |  | $2,870/mo saving from Q2 2028 (Apr 2028).
SharePoint & Others target | Q3 2027 (July) — same start as Discovery purging |  |  |  | $250/mo saving from Q3 2027.
Full monthly saving (from Q2 2028) | $11,920/month = $143,040/year |  |  |  | All three items decommissioned. Pure cost elimination.
One-time cost (base case) | $0 (no migration, no egress, no vendor fees) |  |  |  | No egress fees. No vendor fees. No IT labour charge.
Conditional: if new company needs data | +$45,000 migration cost + Discovery slips to Q2 2028 |  |  |  | Net 4-yr saving reduces by $53,610 → still $420,450. Strong ROI.
2027 gross saving (base case) | $53,550 (Arivis Q3-Q4 + SharePoint Q4 only) |  |  |  | Discovery savings start Q2 2028.
4-year gross saving (2027-2030) | $474,060 |  |  |  | No migration cost. Pure service eliminations including SharePoint.
4-year NET saving (base case) | $474,060 (gross saving — zero purge cost) |  |  |  | Conditional scenario: $420,450. Both scenarios strongly positive.
RECOMMENDED ACTIONS | 1. Obtain written confirmation from new company — do they need any data? (gates everything) 2. Initiate sign-off process for all 12 Discovery site owners immediately 3. Legal: prepare data destruction certificate template 4. Confirm actual SharePoint & Others monthly spend with IT/licensing team 5. If new company needs data: budget $45K migration cost, activate conditional plan |  |  |  | Value at risk: $27,150 per quarter of new company confirmation delay