## Executive Summary
NON-DISCOVERY MIGRATION ¦ HubStor → AWS S3 ¦ PoC: DEL-Microbial (May–Jul 2026) ¦ Full migration by Dec 2026
Non-Discovery only (Safety Assessment + Microbial + RMS) ¦ Azure Backup: proportional share (30%) only ¦ 2-month grace per site before decommission
CURRENT MONTHLY COST (HubStor + Backup 30%) | AWS MONTHLY COST (S3 + 4 Gateways + Ops) | MONTHLY SAVING vs Current | ONE-TIME MIGRATION COST (+10% contingency)
$11,616/mo | $1,128/mo | $10,489/mo | $45,503
HubStor $10,716 + Backup share $900 | S3 storage + 4 Gateway sites + ops | $125,863/yr ¦ 90.3% reduction | Payback: 4.3 months from decommission
CURRENT STORAGE & COSTS BY SITE (Non-Discovery only — HubStor_Non_Discovery.xlsx)
Site / Stor | Region | Total GiB | Total TiB | Monthly Cost ($) | % of Total
DEL-Microbial ★ PoC | Azure East US 2 | 25022.62 | 24.4362 | 1716.22 | 16.01%
CHA-Microbial (inactive) | Azure East US 2 | 0 | 0 | 0 | 0%
RMS East US | Azure East US 2 | 914.1 | 0.89268 | 34.4 | 0.321%
Safety Assessment East US | Azure East US 2 | 195536.23 | 190.9533 | 5930.68 | 55.34%
Safety Assessment UK | Azure UK South | 525.59 | 0.51327 | 15.72 | 0.1467%
Safety Assessment FR+NL | Azure West Europe | 25098.77 | 24.5105 | 810.99 | 7.568%
Safety Assessment West US | Azure West US 2 | 72998.02 | 71.2871 | 2208.33 | 20.61%
TOTAL |  | 320095.33 | 312.5931 | 10716.34 | 100%
AZURE BACKUP — PROPORTIONAL SHARE ONLY (out of scope for migration)
Azure Backup ($3,000/mo total) is apportioned at 30.0% = $900/mo for Non-Discovery (based on Non-Disc GiB 320,095 ÷ Total GiB 1,066,705 = 30.0%). Azure Backup is NOT being migrated in this phase — it requires separate investigation. Only the proportional cost is included here so the business case reflects the true Non-Discovery cost baseline.
AWS MONTHLY COST BREAKDOWN (post-migration)
S3 Storage — tiered by class and region (IA + Deep Archive) | 479.7735
File Gateway EC2 — 4 sites × $130/mo | 520
CloudWatch + KMS (5 keys) + SNS + Config | 48
S3 API operations (ongoing PUTs/GETs) | 40
Glacier retrieval + S3 egress (est.) | 40
★ TOTAL AWS MONTHLY | 1127.7735

## Assumptions
CENTRAL ASSUMPTIONS — NON-DISCOVERY MIGRATION ¦ Yellow = input
STORAGE VOLUMES (HubStor_Non_Discovery.xlsx)
Parameter | Cell Ref | Value | Unit | Source / Notes
Standard tier GiB | A6 | 0 | GiB | Non-Discovery actuals
Hot tier GiB | A7 | 4887.87 | GiB | Non-Discovery actuals
Cool tier GiB | A8 | 14645.59 | GiB | Non-Discovery actuals
Cold tier GiB | A9 | 0 | GiB | Non-Discovery actuals
Archive tier GiB | A10 | 300561.87 | GiB | Non-Discovery actuals
GiB → GB factor | A11 | 1.074 | × | 1 GiB = 1.074 GB
Total GiB | A13 | 320095.33 | GiB | Sum all tiers — Non-Discovery only
Total TiB | A14 | 312.5931 | TiB | ÷ 1024
US GiB (EastUS2 + WestUS2) | A16 | 294470.97 | GiB | EastUS2 + WestUS2
EU GiB (UKSouth + WestEurope) | A17 | 25624.36 | GiB | UKSouth + WestEurope
PoC site — DEL-Microbial GiB | — | 25022.62 | GiB | DEL connector only; CHA=0 usage
AZURE BACKUP — PROPORTIONAL SHARE
Parameter | Cell Ref | Value | Unit | Source / Notes
Azure Backup total monthly (full) | A66 | 3000 | $/mo | Total charge — all sites disc+non-disc
Non-Discovery GiB | — | 320095.33 | GiB | From Non-Discovery file
Total GiB (disc + non-disc) | — | 1066704.64 | GiB | From Master Report v5
Non-Discovery ratio | — | 0.3001 | % | 320,095 ÷ 1,066,705
Azure Backup — Non-Disc share | A67 | 900 | $/mo | $3,000 × 30.0% = $900 (proportional only)
TOTAL current monthly (HubStor + Backup share) | A68 | 11616.34 | $/mo | Used as baseline for savings calculation
AZURE PRICING
Parameter | Cell Ref | Value | Unit | Source / Notes
Azure Archive $/GB/mo | A26 | 0.002 | $/GB/mo | Azure Archive tier
Azure Archive rehydration $/GB | A30 | 0.022 | $/GB | Standard rehydration ~15hr
Azure Cool retrieval $/GB | A28 | 0.01 | $/GB | Azure Blob Cool read
Azure egress tier1 $/GB (0-10TB) | A31 | 0.087 | $/GB | Internet egress
Azure egress tier4 $/GB (>150TB) | A34 | 0.05 | $/GB | Highest-volume discount
HubStor monthly — Non-Disc actuals | A65 | 10716.34 | $/mo | From HubStor_Non_Discovery.xlsx
AWS PRICING
Parameter | Cell Ref | Value | Unit | Source / Notes
S3 Standard-IA $/GB/mo (US) | A40 | 0.0125 | $/GB/mo | Hot+Cool tier → Standard-IA
S3 Standard-IA $/GB/mo (EU) | A41 | 0.013 | $/GB/mo | EU Standard-IA
S3 Glacier Deep Archive $/GB (US) | A44 | 0.00099 | $/GB/mo | Archive tier → Deep Archive
S3 Glacier Deep Archive $/GB (EU) | A45 | 0.001 | $/GB/mo | EU Deep Archive
File Gateway EC2 $/mo/site | A52 | 130 | $/mo/site | t3.xlarge per non-disc site
Number of Gateway sites | A54 | 4 | sites | EastUS2, UKSouth, WestEurope, WestUS2
AWS DataSync $/GB scanned | A63 | 0.0125 | $/GB | One-time migration tool
Annual data growth rate | A64 | 0.05 |  | 5% YoY
PoC hardware — Snowball Edge (1 device) | — | 300 | $ | One Snowball for 25 TiB PoC

## Migration Plan & Costs
ONE-TIME MIGRATION COSTS — NON-DISCOVERY SITES ¦ All components itemised
COMPONENT 1 — AZURE RETRIEVAL CHARGES (reading data out before egress)
Tier | GiB | GB (×1.074) | Retrieval $/GB | Cost ($) | Notes
Standard | 0 | 0 | 0 | 0 | No fee
Hot | 4887.87 | 5249.5724 | 0 | 0 | No fee
Cool | 14645.59 | 15729.3637 | 0.01 | 157.2936 | Per-GB read
Cold | 0 | 0 | 0.03 | 0 | Per-GB read
Archive | 300561.87 | 322803.4484 | 0.022 | 7101.6759 | Standard rehydration ~15hr
SUBTOTAL — RETRIEVAL |  |  |  | 7258.9695
COMPONENT 2 — AZURE EGRESS (tiered internet egress to S3 public endpoint)
Region Group | Volume (GB) | Tier1 $/GB | Tier4 $/GB | Egress Cost ($) | Notes
US Regions (EastUS2 + WestUS2) | 316261.8218 | 0.087 | 0.05 | 19494.3911 | Tiered: first 100GB free then $0.087→$0.05/GB
EU Regions (UKSouth + WestEurope) | 27520.5626 | 0.087 | 0.05 | 2315.5067 | Tiered: first 100GB free then $0.087→$0.05/GB
SUBTOTAL — EGRESS |  |  |  | 21809.8978
COMPONENT 3 — AWS DataSync ($0.0125/GB scanned)
Item | Total GB | Rate $/GB |  | DataSync Cost ($) | Notes
DataSync scan + transfer — all Non-Discovery data | 343782.3844 | 0.0125 |  | 4297.2798 | One-time tool — $0.0125/GB for all data scanned via DataSync
SUBTOTAL — DataSync |  |  |  | 4297.2798
COMPONENT 4 — AWS ONE-TIME SETUP + PoC COSTS
Item | Qty | Unit Cost ($) |  | Total ($) | Notes
File Gateway EC2 setup + config | 4 | 500 |  | 2000 | $500/site IT labour; recurring EC2 from launch
PoC — Snowball Edge (1 device for 25 TiB) | 1 | 300 |  | 300 | Hardware ingestion to S3 — free import; device $300/job
S3 buckets, lifecycle rules, Object Lock | 1 | 500 |  | 500 | 4 regions, lifecycle, GxP Object Lock
IAM roles, KMS keys, bucket policies | 1 | 500 |  | 500 | Per-region security — least privilege
Testing, validation, UAT (all sites) | 1 | 3000 |  | 3000 | Integrity checks, retrieval tests, smoke tests
HubStor decommission admin | 1 | 2000 |  | 2000 | Contract termination, legal sign-off, final data cert
SUBTOTAL — Setup |  |  |  | 8300
GRAND TOTAL — ONE-TIME MIGRATION COST
1. Azure Retrieval | 7258.9695
2. Azure Egress | 21809.8978
3. AWS DataSync | 4297.2798
4. Lifecycle Transitions (Option A — PUT direct to class) | 0
5. AWS Setup + PoC costs | 8300
Contingency (10%) | 4136.6147
★ GRAND TOTAL — ONE-TIME MIGRATION | 45502.7618
ROI & PAYBACK ANALYSIS
Monthly saving (Current − AWS) | 10488.5665
Payback period from full decommission (months) | 4.3383
Year 1 annual gross saving (12 × monthly) | 125862.7976
Net saving after Year 1 (gross − migration cost) | 80360.0358
3-year net cumulative saving | 332085.6311

## Migration Timeline
NON-DISCOVERY MIGRATION TIMELINE ¦ PoC May–Jul 2026 (DEL-Microbial) ¦ 15 days/site Aug–Oct ¦ Full decommission Dec 2026
Azure Backup proportional cost ($900/mo) included as baseline. 2-month grace per site. HubStor parallel run. Well within Apr 2027 target.
PoC SITE: DEL-Microbial (EastUS2) ¦ 25 TiB ¦ Managed by the knowledgeable DEL person ¦ Month 1: AWS setup + engagement ¦ Month 2: 100GB internet sample test ¦ Month 3: Snowball bulk + Storage Gateway cutover ¦ CHA-Microbial (0 usage) excluded
Phase | Site / Description | Start | End | Duration | Data (GiB) | Data (TiB) | Cost/mo ($) | Key Activities | Owner | Decommission Date | Status
PoC Month 1 | Foundation: Landing Zone + Engagement | 01 May 2026 | 31 May 2026 | 31 days | — | — | — | AWS accounts, IAM, S3 buckets, CloudWatch, KMS. Cohesity AE engaged (decommission planning). Azure AE engaged (egress waiver). Resolve all unknowns: HubStor export format, stub recall, dedup expansion, metadata. No data moved this month. | Cloud Arch + Cohesity AE | — | Not Started
PoC Month 2 | Sample Data Test — DEL-Microbial (~100 GB internet) | 01 Jun 2026 | 30 Jun 2026 | 30 days | 102.4 | 0.1 | — | HubStor native export of ~100 GB sample from DEL-Microbial to local NAS. Upload to S3 via internet (no hardware). Deploy Storage Gateway VM on-prem. Mount NFS share. Verify files readable via Gateway. Validate checksum, metadata, file open. Go/no-go gate before ordering hardware. | Migration Team + DEL Admin | — | Not Started
PoC Month 3 | Bulk Transfer + Gateway Cutover — DEL-Microbial (25 TiB) | 01 Jul 2026 | 31 Jul 2026 | 31 days | 25022.62 | 24.4362 | 1716.22 | Full HubStor native export of DEL-Microbial (25 TiB) to NAS. Order AWS Snowball Edge. Copy NAS → Snowball → ship to AWS. AWS ingests to S3 us-east-2. Gateway VM serves NFS/SMB share. Switch DEL connector to Storage Gateway. Monitor for 2 weeks. PoC sign-off. | Migration Team + DEL Admin | 30 Sep 2026 | Not Started
Phase 1 | RMS East US — EastUS2 (914 GiB) | 01 Aug 2026 | 15 Aug 2026 | 15 days | 914.1 | 0.89268 | 34.4 | Smallest remaining store. HubStor native export → NAS → DataSync to S3. 3 connectors (WLM-RMS). Storage Gateway already live from PoC. Switch connector. Quick validation (914 GiB ≈ few hours DataSync). | Migration Team | 15 Oct 2026 | Not Started
Phase 2 | Safety Assessment UK — UKSouth (525 GiB) | 16 Aug 2026 | 31 Aug 2026 | 16 days | 525.59 | 0.51327 | 15.72 | 525 GiB archive — fast transfer. Deploy Gateway VM at Edinburgh (EDI). Data residency: eu-west-2 (London). GDPR confirmed. 1 connector (EDI-SafetyAssessment). | Migration Team | 31 Oct 2026 | Not Started
Phase 3 | Safety Assessment FR+NL — WestEurope (24.5 TiB) | 01 Sep 2026 | 15 Sep 2026 | 15 days | 25098.77 | 24.5105 | 810.99 | FR (FRE/LYO/EVR = 7.1 TiB) + NL (HER = 18 TiB). Deploy Gateway at Amsterdam (eu-west-1). Archive rehydration then DataSync. GDPR data residency eu-west-1. | Migration Team | 15 Nov 2026 | Not Started
Phase 4 | Safety Assessment East US — EastUS2 (191 TiB) | 16 Sep 2026 | 30 Sep 2026 | 15 days | 195536.23 | 190.9533 | 5930.68 | Largest store. 189 TiB archive — rehydration required (~15hr batches). DataSync over 3-4 nights. 8 remaining connectors (MWN, ASH, SHR, SPE, LAV + CHA-Microbial inactive). Second Snowball if needed. | Migration Team | 30 Nov 2026 | Not Started
Phase 5 | Safety Assessment West US — WestUS2 (71 TiB) | 01 Oct 2026 | 15 Oct 2026 | 15 days | 72998.02 | 71.2871 | 2208.33 | 71 TiB archive. Reno site (RNO). Deploy Gateway VM. Archive rehydration then DataSync. Data residency us-west-2. | Migration Team | 15 Dec 2026 | Not Started
Phase 6 | Full Cutover Validation | 16 Oct 2026 | 31 Oct 2026 | 16 days | — | — | — | All sites on S3 via Storage Gateway. Final S3 Inventory vs HubStor Master Report — 100% match required. Zero Azure Blob writes confirmed. Object Lock validation. All connectors confirmed healthy. | Cloud Arch | — | Not Started
Phase 7 | Parallel Run — 2-Month Grace Period | 01 Nov 2026 | 15 Dec 2026 | 45 days | — | — | — | HubStor runs in parallel but receives no new writes. Both systems monitored. Compliance checks, legal hold verification, eDiscovery readiness. Site-by-site HubStor decommission as grace periods expire (Oct–Dec). Full HubStor decommission Dec 2026. | Cloud Arch + Legal | — | Not Started
Phase 8 | Full HubStor Decommission | 16 Dec 2026 | 31 Dec 2026 | 16 days | — | — | — | Cancel ALL HubStor/Cohesity licences. Terminate Azure Blob Storage accounts (4 regions). Remove all HubStor agents. Retain metadata catalog export. Azure Backup decision separate (out of scope). Project closed. | Finance + Legal | — | Not Started
SITE DECOMMISSION SCHEDULE — 2-month grace period per site after cutover
Site | Region | Cutover Date | Grace Period | Decommission Date | HubStor Agent Remove | Azure Blob Delete | Note
DEL-Microbial ★ PoC | EastUS2 | 31 Jul 2026 | 2 months | 30 Sep 2026 | 30 Sep 2026 | 30 Sep 2026 | PoC site — first decommission
RMS East US | EastUS2 | 15 Aug 2026 | 2 months | 15 Oct 2026 | 15 Oct 2026 | 15 Oct 2026 | Smallest store
Safety Assess. UK | UKSouth | 31 Aug 2026 | 2 months | 31 Oct 2026 | 31 Oct 2026 | 31 Oct 2026 | EDI connector
Safety Assess. FR+NL | WestEurope | 15 Sep 2026 | 2 months | 15 Nov 2026 | 15 Nov 2026 | 15 Nov 2026 | GDPR data residency confirmed
Safety Assess. East US | EastUS2 | 30 Sep 2026 | 2 months | 30 Nov 2026 | 30 Nov 2026 | 30 Nov 2026 | Largest store — 191 TiB
Safety Assess. West US | WestUS2 | 15 Oct 2026 | 2 months | 15 Dec 2026 | 15 Dec 2026 | 15 Dec 2026 | Reno — last site
ALL SITES — Full HubStor Decommission | All | 15 Oct 2026 | 2 months | 31 Dec 2026 | 31 Dec 2026 | 31 Dec 2026 | Cancel all licences. Azure Backup: separate decision.

## Financial Model
FINANCIAL MODEL — May 2026 to Apr 2027 ¦ Azure Backup: proportional $900/mo ¦ HubStor ramps down as sites decommission
PoC months (May-Jul): migration cost front-loaded + AWS ramp. Aug-Oct: 15-day site windows. Nov-Dec: parallel run + decommission per site.
MODEL INPUTS
HubStor + Azure Backup baseline (current total) | 11616.34
AWS total monthly (post-migration) | 1127.7735
One-time migration cost (total) | 45502.7618
Metric | May 2026 | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | Total / Note
HubStor + Azure Backup ($) | 11616.34 | 11616.34 | 11616.34 | 11616.34 | 11616.34 | 9900.12 | 9850 | 3108.33 | 900 | 900 | 900 | 900 | 84540.15
AWS Total Monthly ($) | 0 | 0 | 295.505 | 426.8751 | 725.2821 | 1387.7735 | 1387.7735 | 1387.7735 | 1387.7735 | 1387.7735 | 1387.7735 | 1387.7735 | 11162.077
One-time Migration Cost ($) | 18201.1047 | 18201.1047 | 9100.5524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45502.7618
Total Monthly Outgoing ($) | 29817.4447 | 29817.4447 | 21012.3974 | 12043.2151 | 12341.6221 | 11287.8935 | 11237.7735 | 4496.1035 | 2287.7735 | 2287.7735 | 2287.7735 | 2287.7735 | 141204.9888
Monthly Saving vs Baseline ($) | -18201.1047 | -18201.1047 | -9396.0574 | -426.8751 | -725.2821 | 328.4465 | 378.5665 | 7120.2365 | 9328.5665 | 9328.5665 | 9328.5665 | 9328.5665 | -1808.9088
Cumulative Net Saving ($) | -18201.1047 | -36402.2094 | -45798.2669 | -46225.142 | -46950.4241 | -46621.9776 | -46243.4112 | -39123.1747 | -29794.6082 | -20466.0418 | -11137.4753 | -1808.9088 | -1808.9088
ANNUAL SUMMARY
Year | Period | HubStor Cost | AWS Cost | Net Saving
2026 | May–Dec 2026 (migration + PoC) | 80940.15 | 51113.7447 | 29826.4053
2027 | Jan–Apr 2027 (full AWS running) | 3600 | 5551.0941 | -1951.0941

## Detailed Migration Plan
DETAILED MIGRATION PLAN — NON-DISCOVERY ¦ PoC: DEL-Microbial 3-Month Process ¦ 15 days per site
Week | Category | Task | Owner | Detail / Notes | Success Criteria
POC MONTH 1 — FOUNDATION & ENGAGEMENT (May 1–31, 2026) ¦ No data moved. Resolve all unknowns.
Wk1 | Commercial | Serve HubStor/Cohesity contract termination notice — verify notice period | Legal + Finance | Notice period clock starts. Decommission target Dec 2026. If >6 months notice, adjust. | NOTICE SERVED
Wk1 | AWS Setup | Create AWS account for us-east-2 (EastUS2 PoC). Enable region, set SCPs, org billing. | Cloud Arch | Single region first. Expand to uk/eu after PoC sign-off. | Account active
Wk1 | AWS Setup | Configure IAM: DataSync role, Gateway role, S3 bucket policy, KMS CMK for us-east-2. | Cloud Arch | Least-privilege. Test all roles with AWS CLI before proceeding. | IAM complete
Wk2 | AWS Setup | Create S3 bucket us-east-2: versioning, SSE-S3, block public access, lifecycle (Archive→Glacier Deep Archive), Object Lock. | Cloud Arch | Object Lock for Safety Assessment GxP data. Lifecycle prevents wrong tier. | Bucket + lifecycle active
Wk2 | Monitoring | Deploy CloudWatch dashboard: cost alarm (120% threshold), DataSync health, Gateway health. | Cloud Arch | SNS alert to team email. Finance visibility on cost from day 1. | Dashboard live
Wk2 | Engagement | Cohesity AE — formal kick-off: confirm decommission process, export runbook, notice period, written decommission confirmation letter. | Programme Mgr | State clearly: full non-discovery decommission by Dec 2026. Get runbook. | Cohesity engaged
Wk2 | Engagement | Azure AE — confirm egress fee waiver for Data Box export. Confirm Azure Blob account closure process. FastTrack eligibility check. | Cloud Arch | Egress waiver in writing before ordering Data Box. Saves significant cost. | Azure AE engaged
Wk3 | Unknowns | HubStor admin: confirm native export format for DEL-Microbial. Run capacity estimate — what is the post-dedup, post-decompress size of 25 TiB? | HubStor Admin | CRITICAL: 25 TiB in Azure may expand to 30–75 TiB post-export. Must know before ordering Snowball. HubStor native export produces standard files + sidecar JSON. | Capacity estimate done
Wk3 | Unknowns | Inventory all file stubs at DEL-Microbial site. Count and size of stubbed files. Plan stub recall before cutover. | HubStor Admin + DEL Admin | Stubs point to HubStor — break after cutover. Must recall to local server first. | Stub inventory done
Wk3 | Unknowns | Identify any applications using HubStor REST API directly at DEL site. Plan API migration to S3 API or NFS/SMB. | App Teams | Apps calling HubStor API directly will break at cutover. Must be updated. | App inventory done
Wk4 | Unknowns | Map critical metadata fields: retention dates, legal hold flags, custodian from HubStor catalog → S3 object tags. Scripting plan. | HubStor Admin + Dev | Compliance-critical metadata must not be lost. Script to apply S3 tags from catalog CSV. | Metadata map complete
Wk4 | Network | Deploy Storage Gateway File Gateway VM at DEL on-prem server (VMware/Hyper-V/KVM). Min spec: 4 vCPU, 16GB RAM, 150GB SSD cache. Connect to us-east-2 via HTTPS. | Network + Cloud Arch | Use existing on-prem server. No new hardware. Test write → S3 → read back. | Gateway VM online
Wk4 | Testing | E2E connectivity test: write 1GB test file via Gateway NFS share → verify in S3 → download and checksum match. | Migration Team | Confirms full path: on-prem → Gateway → S3 → retrieve. Must pass before Month 2. | E2E test PASSED
POC MONTH 2 — SAMPLE DATA TEST VIA INTERNET (Jun 1–30, 2026) ¦ ~100 GB sample, no hardware.
Wk5 | Export | Run HubStor native export of ~100 GB representative sample from DEL-Microbial to local NAS. Include: stubbed files, deduplicated files, compressed files, archived files — all edge cases. | HubStor Admin + DEL Admin | This is the critical format test. Export = standard files + sidecar JSON metadata. NOT raw Azure Blobs. | 100 GB export complete
Wk5 | Export | Generate SHA256 checksums for all exported files on NAS before upload. | Migration Team | Baseline for integrity validation after S3 ingestion. | Checksums recorded
Wk6 | Transfer | Upload 100 GB sample to S3 us-east-2 via AWS CLI (internet — no hardware for sample test). Use --storage-class=STANDARD_IA for cool data, DEEP_ARCHIVE for archive. | Migration Team | Test the upload path. Should complete in a few hours on business internet. Monitor DataSync/CLI progress. | Sample uploaded to S3
Wk6 | Validation | Download sample from S3 to a separate on-prem machine. Verify SHA256 checksums match NAS baseline. | Migration Team | 100% checksum match required. Any mismatch = investigate before proceeding. | Checksum VERIFIED
Wk6 | Validation | Open representative files of each type (PDF, DOCX, images, archives) via Storage Gateway NFS share. Confirm readable and uncorrupted. | DEL Admin + App Teams | Tests that Storage Gateway serves files correctly from S3. Open 10 files minimum across types. | Files readable via Gateway
Wk7 | Validation | Test stub recall: identify 5 stubbed files in DEL-Microbial, recall them via HubStor, confirm they appear as full files in the export. | HubStor Admin | Confirms stub recall works before full export. Critical for data completeness. | Stub recall TESTED
Wk7 | Validation | Apply S3 object tags from HubStor catalog export (retention, custodian) to sample objects. Verify tags visible in S3 console. | Migration Team + Dev | Tests the metadata scripting approach. Must work before full migration. | Metadata tags applied
Wk8 | Go/No-Go | Sample test retrospective. Review: checksums, file readability, stub recall, metadata, Gateway performance. Signed go/no-go gate. | Programme Mgr + Stakeholders | All checks must pass. Order Snowball Edge only after this gate. Budget sign-off for hardware. | GO/NO-GO SIGNED
POC MONTH 3 — BULK TRANSFER + STORAGE GATEWAY CUTOVER (Jul 1–31, 2026) ¦ 25 TiB via Snowball.
Wk9 | Export | Run full HubStor native export of DEL-Microbial (all connectors — DEL only, CHA inactive) to local NAS. Estimated 25–50 TiB post-dedup. Run stub recall first. | HubStor Admin + DEL Admin | Run stub recall before export. NAS must have capacity for post-dedup size (from Month 1 estimate). Export may take 2-3 days. | Full export on NAS
Wk9 | Hardware | Order AWS Snowball Edge Storage Optimized (80 TiB usable). Confirm delivery address. Expected 2-3 business day delivery (enterprise account). | Cloud Arch | Place order immediately after Month 2 go/no-go. Snowball must arrive before export completes. | Snowball ordered
Wk10 | Transfer | Connect Snowball Edge via 10GbE. Copy NAS export to Snowball using OpsHub or Snowball CLI. Verify manifest on device. | Migration Team | Copy speed ~400 GB/hr at 10GbE → 25 TiB ≈ 60 hrs. Run continuously. Monitor progress. | Snowball copy complete
Wk10 | Transfer | Ship Snowball Edge to AWS (pre-paid UPS label from OpsHub). AWS receives at us-east-2 ingestion facility in 2-3 days. | Migration Team | Track shipment in AWS Console > Snow Family. SNS notification on ingestion completion. | Snowball shipped
Wk11 | Ingestion | AWS ingests Snowball data to S3 us-east-2 bucket. Monitor SNS notification. Run S3 Inventory report. | Cloud Arch | Automated — no action required. Typically 2-3 days after delivery. SNS confirms completion. | S3 ingestion COMPLETE
Wk11 | Validation | Compare S3 Inventory (object count + total size) vs NAS export manifest. 100% match required. Spot-check 20 files via SHA256. | Migration Team | Any discrepancy: rerun DataSync for missing objects before cutover. | S3 inventory VERIFIED
Wk12 | Cutover | Run stub recall for all remaining DEL-Microbial stubs on local server. | DEL Admin | All stubs must be full files before switching connector. | Stubs recalled
Wk12 | Cutover | Switch DEL-Microbial connector from HubStor share to Storage Gateway NFS/SMB mount. Run archive write test (file → S3) and restore test (file ← S3). | DEL Admin + App Teams | Both tests must pass. If fail: revert to HubStor and investigate. | Connector switched
Wk12 | Cutover | Monitor DEL-Microbial on Storage Gateway for 2 weeks: write speed, read latency, error rate. | Cloud Arch | Target: <5s cached reads, <30min uncached archive. Zero errors. | 2-week soak PASS
Wk12 | PoC Closeout | PoC retrospective: document lessons learned, update runbook for remaining sites, confirm Phase 1 go/no-go. | Programme Mgr | Signed lessons document. Runbook updated. Remaining sites proceed on 15-day schedule. | PoC SIGNED OFF
PHASE 1 — RMS EAST US (Aug 1–15, 2026) ¦ 914 GiB ¦ 3 connectors (WLM-RMS)
Wk13 | Migration | HubStor native export of RMS East US to NAS (914 GiB). Stub recall first. Expected <2 hours. | HubStor Admin | Small store. Upload direct to S3 via DataSync (no Snowball needed). | Export complete
Wk13 | Migration | DataSync: NAS → S3 us-east-2. storage-class=STANDARD_IA (cool+archive mix). Expected <1 hour. | Migration Team | Monitor DataSync CloudWatch. Zero errors required. | DataSync complete
Wk13 | Validation | S3 Inventory vs NAS manifest. Open 5 files via Gateway. Checksum spot-check. | Migration Team | 100% match. All files readable. | Integrity VERIFIED
Wk14 | Cutover | Switch WLM-RMS connector to Gateway. Write + restore test. Monitor 1 week. | App Teams | Both tests pass. Gateway logs clean. | RMS LIVE on S3
PHASE 2 — SAFETY ASSESSMENT UK (Aug 16–31, 2026) ¦ 525 GiB ¦ 1 connector (EDI)
Wk14 | Migration | Deploy Gateway VM at Edinburgh (EDI). Connect to eu-west-2 (London) S3 bucket. GDPR data residency enforced. | Cloud Arch | Data MUST stay in eu-west-2. SCP enforced. Test connectivity. | UK Gateway online
Wk15 | Migration | HubStor native export + DataSync: Safety Assessment UK (525 GiB) → S3 eu-west-2. Quick transfer. | Migration Team | Archive only. Rehydration may be needed (~15hr). Small store. | UK migrated
Wk15 | Cutover | Switch EDI connector to Gateway. GDPR residency confirmed. Legal sign-off. | App Teams + Legal | Legal must sign off on GDPR compliance in eu-west-2. | UK LIVE on S3
PHASE 3 — SAFETY ASSESSMENT FR+NL — WestEurope (Sep 1–15, 2026) ¦ 24.5 TiB
Wk16 | Migration | Deploy Gateway VM at Amsterdam (eu-west-1). FR (FRE/LYO/EVR) + NL (HER) connectors. GDPR confirmed. | Cloud Arch | All WestEurope data stays in eu-west-1. 2 connectors. | EU Gateway online
Wk16 | Migration | Archive rehydration: SA FR (7.1 TiB) + SA NL (18 TiB). Submit Azure rehydration jobs. | Migration Team | Standard rehydration ~15hr each. Plan 2-day window. | Rehydration started
Wk17 | Migration | DataSync: SA FR + SA NL after rehydration completes. Run overnight each. | Migration Team | FR: 7.1 TiB (~15hr). NL: 18 TiB (~36hr). Monitor. | FR+NL migrated
Wk17 | Cutover | Switch FRE/LYO/EVR/HER connectors to Gateway. GDPR residency confirmed. Legal sign-off. | App Teams + Legal | Data residency audit report produced. | WestEurope LIVE on S3
PHASE 4 — SAFETY ASSESSMENT EAST US (Sep 16–30, 2026) ¦ 191 TiB ¦ Largest store
Wk18 | Migration | Submit archive rehydration: Safety Assessment East US (189 TiB archive). Batch across 8 connectors (MWN/ASH/SHR/SPE/LAV). ~15hr per batch. | Migration Team | Plan 3-day rehydration window. Stagger batches. CHA-Microbial: 0 usage — no action. | Rehydration started
Wk18 | Migration | Second Snowball Edge ordered if post-dedup export exceeds 80 TiB. Monitor NAS export size. | Cloud Arch | Based on Month 1 capacity estimate. Order early. | Snowball ready if needed
Wk19 | Migration | DataSync: SA East US after rehydration. Run 4-5 nights. Monitor CloudWatch daily. | Migration Team | 195 TiB → ~400 hrs at 200GB/hr. Run continuously overnight. | SA East migrated
Wk19 | Validation | S3 Inventory cross-check. Spot-check 50 files. Object Lock confirmed on GxP data. | Migration Team + QA | GxP/Safety Assessment: Object Lock mandatory. QA sign-off required. | EastUS2 verified
Wk20 | Cutover | Switch all EastUS2 Safety Assessment connectors to Gateway. Disable Azure EastUS2 write access. | App Teams | 8 connectors. All tested. Zero errors before go-live. | EastUS2 LIVE on S3
PHASE 5 — SAFETY ASSESSMENT WEST US (Oct 1–15, 2026) ¦ 71 TiB ¦ Reno
Wk21 | Migration | Deploy Gateway VM at Reno (RNO). Connect to us-west-2 S3 bucket. Archive rehydration (71 TiB). | Cloud Arch | RNO-SafetyAssessment connector. Data residency us-west-2. | RNO Gateway online
Wk21 | Migration | DataSync: Safety Assessment West US (71 TiB). Run 2-3 nights. | Migration Team | ~145 hrs at 200GB/hr. Monitor. | WestUS2 migrated
Wk22 | Cutover | Switch RNO connector to Gateway. Write + restore test. Disable Azure WestUS2 writes. | App Teams | Final site cutover. Zero errors. | WestUS2 LIVE on S3
PHASE 6 — FULL CUTOVER VALIDATION (Oct 16–31, 2026)
Wk23 | Validation | Full S3 Inventory across all regions vs HubStor Master Report Non-Discovery. 100% match. | Migration Team | Final integrity pass. Zero discrepancy. | FINAL INTEGRITY PASS
Wk23 | Validation | Confirm zero Azure Blob writes from any connector. CloudWatch metric: 0 bytes written to Azure. | Cloud Arch | All connectors confirmed on Storage Gateway. | Zero-Azure confirmed
Wk23 | Commercial | Submit HubStor subscription cancellation notice. Confirm no auto-renewal. | Finance + Legal | Cancel all non-discovery licences. Written confirmation. | HubStor CANCELLED
PHASE 7 — PARALLEL RUN & GRACE PERIOD (Nov 1 – Dec 15, 2026)
Wk24-29 | Monitoring | HubStor runs in parallel — no new writes from any site. Both systems monitored for 2 months. | Cloud Arch | CloudWatch confirms S3 is sole write path. HubStor is read-only reference. | Parallel confirmed
Wk24-29 | Compliance | Legal hold verification, eDiscovery readiness, retention policy checks per site. | Legal + Compliance | Legal team sign-off required before each site decommission. | Compliance SIGNED
Wk24-29 | Decommission | Site-by-site decommission as grace periods expire: DEL(Sep30) → RMS(Oct15) → UK(Oct31) → FR+NL(Nov15) → SA East(Nov30) → West US(Dec15) | Cloud Arch | Per-site: remove HubStor agent, delete Azure Blob containers, retain metadata catalog. | Sites decommissioned
PHASE 8 — FULL DECOMMISSION (Dec 16–31, 2026) ¦ Well within Apr 2027 target
Wk30 | Commercial | Cancel ALL remaining HubStor/Cohesity licences. Terminate all Azure Blob accounts (4 regions). Download final invoices. | Finance + Legal | Written decommission confirmation from Cohesity. Azure closure confirmed. | ALL DECOMMISSIONED
Wk30 | Commercial | Azure Backup: note this is out of scope and requires separate decision. Do not terminate until investigated. | Finance + Cloud Arch | Azure Backup is a separate service — flag for investigation as separate workstream. | Azure Backup: TBD
Wk30 | Optimisation | Enable S3 Storage Lens. Review lifecycle effectiveness. Cost Anomaly Detection configured. | Cloud Arch | Monthly cost report to Finance: actual vs $10,466/mo saving target. | Optimisation ACTIVE
Wk31 | Closeout | Migration project closed. Retrospective documented. Metadata catalog archived permanently. | Programme Mgr | Lessons learned. Team recognised. Project docs archived. | PROJECT CLOSED 🎉

## Cost Comparison
AZURE HUBSTOR vs AWS S3 — NON-DISCOVERY COST COMPARISON ¦ Azure Backup at proportional 30% share
MONTHLY COST — CURRENT vs AWS POST-MIGRATION
Cost Item | Current (HubStor/Azure) | AWS Post-Migration | Monthly Saving | Annual Saving | Notes
HubStor Storage (Non-Discovery) | 10716.34 | 479.7735 | 10236.5665 | 122838.7976 | Tier-proportional S3 pricing
Azure Backup (30% share — proportional) | 900 | 0 | 900 | 10800 | Stops at decommission; separate investigation
File Gateway EC2 (4 sites × $130) | 0 | 520 | -520 | -6240 | New cost — EC2 t3.xlarge per site
CloudWatch + KMS + SNS + Config | 0 | 48 | -48 | -576 | Monitoring + security
S3 API + retrieval + egress (est.) | 0 | 80 | -80 | -960 | Ongoing ops
TOTAL | 11616.34 | 1127.7735 | 10488.5665 | 125862.7976 | 90.3% saving
AZURE BACKUP NOTE — PROPORTIONAL SHARE RATIONALE
The Azure Backup charge ($3,000/mo total) covers ALL HubStor data (Discovery + Non-Discovery). For this Non-Discovery analysis we attribute only the proportional share: Non-Discovery GiB 320,095 ÷ Total GiB 1,066,705 = 30.0% → $900/mo. Discovery sites bear the remaining 70.0% = $2,100/mo. Azure Backup itself is NOT migrated in this phase and requires separate investigation.
ROI & PAYBACK ANALYSIS
One-time migration cost (incl. 10% contingency) | 45502.7618
Monthly saving (current baseline − AWS) | 10488.5665
Annual saving (12 months) | 125862.7976
Payback period from decommission (months) | 4.3383
Year 1 net saving (annual saving − migration cost) | 80360.0358
3-year cumulative net saving | 332085.6311