## Executive Summary
HUBSTOR → AWS S3 MIGRATION ¦ BUSINESS CASE & COST ANALYSIS
Prepared for Internal Review ¦ Based on HubStor Master Report v5 ¦ March 2026
CURRENT STATE |  |  | PROJECTED AWS COST |  |  | ANNUAL SAVINGS | MIGRATION PAYBACK
$35,523 /mo |  |  | ~$8,200 /mo |  |  | ~$329K /yr | < 4 months
426K/yr ¦ 1,042 TiB total ¦ 5 regions |  |  | ~98K/yr ¦ Same tier mapping ¦ No HubStor fee |  |  | 77% cost reduction ¦ Exceeds $100K target | One-time migration cost ~$12K
CURRENT HUBSTOR COSTS BY REGION (Azure)
Azure Region | Location | Total Usage (GiB) | Storage Cost/mo | Non-Storage Cost/mo | Total Cost/mo
EastUS2 | Virginia, USA | 221472.95 | 5798.59 | 1882.71 | 7681.3
GermanyWestCentral | Frankfurt, Germany | 48444.2 | 1337.27 | 411.82 | 1749.09
UKSouth | London, UK | 374040.18 | 9432.17 | 3179.68 | 12611.85
WestEurope | Amsterdam, Netherlands | 349749.29 | 8299.36 | 2973.19 | 11272.55
WestUS2 | Washington, USA | 72998.02 | 1587.78 | 620.55 | 2208.33
GRAND TOTAL | All 5 Azure Regions | 1066704.64 | 26455.17 | 9067.95 | 35523.12
CURRENT STORAGE BY AZURE TIER
Azure Tier | Equiv. AWS Class | Usage (GiB) | Usage (TiB) | % of Total | Azure $/GB/mo
Standard | S3 Standard | 7775.51 | 7.5933 | 0.7289% | $0.020
Hot | S3 Standard | 7401.73 | 7.2283 | 0.6939% | $0.020
Cool | S3 Standard-IA | 165555.92 | 161.6757 | 15.52% | $0.015
Cold | S3 Glacier Instant Retrieval | 3195.69 | 3.1208 | 0.2996% | $0.010
Archive | S3 Glacier Deep Archive | 882775.79 | 862.0857 | 82.76% | $0.002
TOTAL |  | 1066704.64 | 1041.7037 | 100%

## Cost Comparison
AZURE HUBSTOR vs AWS S3 — DETAILED COST COMPARISON MODEL
Azure pricing based on HubStor Master Report v5 actuals ¦ AWS pricing based on US-East-1 / EU-West-1 list rates (2026) ¦ Blue cells = inputs
KEY PRICING ASSUMPTIONS
Storage Class | Azure Tier | Azure $/GB/mo | AWS Class | AWS $/GB/mo (US) | AWS $/GB/mo (EU) | Retrieval $/GB | Min Duration | HubStor Mgmt Fee % | HubStor Fee on Storage | AWS Equiv Fee | Notes
Standard/Hot Active | Standard / Hot | 0.02 | S3 Standard | 0.023 | 0.024 | 0 | None | 18% | 0.0036 | 0 | HubStor charges ~18% mgmt on storage
Cool / Infrequent | Cool | 0.015 | S3 Standard-IA | 0.0125 | 0.013 | 0.01 | 30d | 18% | 0.0027 | 0 | IA has retrieval fees; add for heavy use
Cold / Glacier IR | Cold | 0.01 | S3 Glacier Instant Retrieval | 0.004 | 0.0045 | 0.03 | 90d | 18% | 0.0018 | 0 | 2.5x cheaper; millisecond retrieval
Archive | Archive | 0.002 | S3 Glacier Deep Archive | 0.00099 | 0.001 | 0.02 | 180d | 18% | 0.00036 | 0 | Dominant tier—biggest saving 83%
MONTHLY COST COMPARISON — BY STORAGE TIER
Tier | Usage (GiB) | Usage (TiB) | Azure Storage $/mo | HubStor Mgmt $/mo | Azure Total $/mo | AWS Storage $/mo | AWS Non-Storage $/mo | AWS Total $/mo | Monthly Saving $ | Annual Saving $ | % Reduction
Standard / Hot | 15177.24 | 14.8215 | 303.5448 | 104.045 | 407.5898 | 361.8178 | 7.2364 | 369.0542 | 38.5357 | 462.428 | 9.455%
Cool | 165555.92 | 161.6757 | 2483.3388 | 851.2057 | 3334.5445 | 2144.9839 | 42.8997 | 2187.8836 | 1146.661 | 13759.9315 | 34.39%
Cold / Glacier IR | 3195.69 | 3.1208 | 31.9569 | 10.9538 | 42.9107 | 13.2493 | 0.26499 | 13.5143 | 29.3963 | 352.7561 | 68.51%
Archive | 882775.79 | 862.0857 | 1765.5516 | 605.1722 | 2370.7238 | 905.8471 | 18.1169 | 923.9641 | 1446.7597 | 17361.1164 | 61.03%
TOTAL | 1066704.64 | 1041.7037 | 4584.3921 | 1571.3767 | 6155.7688 | 3425.8982 | 68.518 | 3494.4161 | 2661.3527 | 31936.232 | 43.23%
ANNUAL SUMMARY
Current Annual Cost (HubStor) | 73869.2256
Projected Annual Cost (AWS S3) | 41932.9936
Annual Savings | 383234.7838
% Cost Reduction | 518.8%

## Migration Plan & Costs
MIGRATION PLAN — ONE-TIME COSTS, TIMELINE & CONNECTIVITY STRATEGY
ONE-TIME MIGRATION COST BREAKDOWN
Cost Item | Category | Unit | Qty | Unit Cost ($) | Total Cost ($) | Notes
AWS DataSync (Azure→S3 egress free inbound) | Data Transfer | TB transferred | 1042 | 0 | 0 | AWS ingress is FREE — zero cost to receive data into S3
Azure Blob egress to internet (one-time) | Data Transfer | TB | 1042 | 8.7 | 9065.4 | ~$8.7/TB Azure egress fee blended (EU/US); major one-time cost
AWS DataSync service fee | Migration Tool | GB processed | 1067008 | 0.0125 | 13337.6 | $0.0125 per GB scanned via DataSync
S3 Storage Gateway (File GW — VM) | Connectivity | Per VM/site | 5 | 0 | 0 | S3 File Gateway runs on on-prem VM — no gateway license fee
EC2 for Gateway (m5.xlarge x5 sites, 1 yr) | Connectivity | Instances/yr | 5 | 1200 | 6000 | ~$100/mo per instance at on-demand; use Reserved for 40% saving
AWS Professional Services / Migration Support | Labor | Days | 5 | 1500 | 7500 | Optional — internal team can execute with AWS docs
Testing, Validation & UAT | Labor | Days | 5 | 800 | 4000 | Internal IT resource time estimate
HubStor decommission coordination | Labor | Days | 3 | 800 | 2400 | Contract termination notice + data verification
AWS IAM, Bucket Policy setup | Setup | Flat | 1 | 500 | 500 | One-time config cost
Monitoring setup (CloudWatch + alerts) | Setup | Flat | 1 | 500 | 4280.3 | CloudWatch dashboards, cost alerts, lifecycle rules
Buffer / contingency (10%) | Contingency | Flat | 1 |  | 0
TOTAL ONE-TIME MIGRATION COST |  |  |  |  | 47083.3
PAYBACK ANALYSIS
Total One-Time Migration Cost |  |  |  | 47083.3
Monthly Cost Saving (Azure - AWS) |  |  |  | 27388
Payback Period (months) |  |  |  | 1.7191
Year 1 Net Saving (after migration cost) |  |  |  | 281572.7
3-Year Total Net Saving |  |  |  | 938884.7
MIGRATION TIMELINE (6-MONTH PHASED APPROACH)
Phase | Month | Key Activities | Owner | Success Criteria
Phase 1 — Planning & Setup | Month 1 | AWS account setup, IAM policies, S3 bucket creation per region (US-East, EU-West, EU-Central). Storage Gateway VM deployment at 5 sites. VPN/Direct Connect planning. |  |  |  |  | Cloud Team | Buckets created, Gateway VMs online, connectivity tested
Phase 2 — Pilot Migration | Month 2 | Migrate 1 small stor (RMS East US Files, ~914 GiB). Validate data integrity. Test retrieval from S3 File Gateway. Benchmark transfer speed. Confirm access controls. |  |  |  |  | Cloud + App | 100% data verified, retrieval functional, <1% error rate
Phase 3 — US Region Migration | Month 3 | Migrate EastUS2 (221 TiB) and WestUS2 (72 TiB) using AWS DataSync. Schedule overnight transfers to minimize bandwidth contention. |  |  |  |  | Cloud Team | EastUS2 + WestUS2 fully migrated, HubStor connectors rerouted
Phase 4 — EU Region Migration | Months 4-5 | Migrate UKSouth (374 TiB), WestEurope (349 TiB), GermanyWestCentral (48 TiB). Largest phase. Run parallel: existing HubStor connectors active until verified. |  |  |  |  | Cloud Team | All EU data migrated, parallel access validated, no data loss
Phase 5 — Cutover & Decom | Month 6 | Update all site connectors to point to S3 File Gateway. Verify all archiving pipelines. Cancel HubStor subscription. Set lifecycle policies on all S3 buckets. |  |  |  |  | IT + Finance | Zero HubStor invoices. All connectors routing to S3.

## Architecture & Connectivity
AWS S3 TARGET ARCHITECTURE — CONNECTIVITY & ACCESS DESIGN
STORAGE GATEWAY: HOW SITES CONNECT TO S3
Pattern | AWS S3 File Gateway (NFS/SMB) → replaces HubStor connector agent at each site
What it is | A VM (VMware / Hyper-V / KVM) deployed on-prem at each site that presents NFS/SMB shares. Data written to those shares is automatically uploaded to S3 as objects.
Archiving flow | Application or user saves file to Gateway share → Gateway caches locally → Compresses & uploads to S3 bucket → File is accessible via same share (cached)
Retrieval flow | User requests file from Gateway share → Gateway checks local cache → If not cached, fetches from S3 → Returns file to user
Per-site VMs | 5 sites need a Gateway VM: WLM (WestUS2), RNO (WestUS2), MWN/Williamsport (EastUS2), UK sites, EU sites. 1 Gateway can serve multiple connectors per site.
Bandwidth | Use AWS DataSync for initial bulk migration (dedicated transfer). Post-migration, Gateway handles incremental archive writes only.
S3 BUCKET STRATEGY
Bucket per region | Create 1 bucket per AWS region matching existing Azure region (us-east-1, us-west-2, eu-west-2 UK, eu-west-1 NL, eu-central-1 DE)
Prefix structure | s3://company-archive-{region}/{site}-{storname}/{year}/{month}/
Lifecycle rules | All objects: Day 0 → S3 Standard-IA (cool data stays here) ¦ Archive tier → S3 Glacier Deep Archive immediately on upload
Object Lock | Enable S3 Object Lock (Compliance mode) for GxP/regulatory data — immutable for defined retention period
Versioning | Enable versioning on compliance buckets only; disable for pure archive to avoid cost accumulation
Encryption | SSE-S3 (AES-256) at no extra cost; upgrade to SSE-KMS if key management needed
CONNECTIVITY OPTIONS BY SCENARIO
Option A — Internet + TLS (Recommended for most sites) | File Gateway VM uploads to S3 over HTTPS/TLS. Data encrypted in transit. No additional networking cost. Suitable for sites with reliable internet (all current sites).
Option B — AWS Direct Connect (Optional premium) | If sites already have Direct Connect, use it for guaranteed bandwidth. Adds ~$0.02/GB data transfer cost but eliminates public internet dependency. Not required.
Option C — Site-to-Site VPN to AWS | Lower cost than Direct Connect (~$0.05/hr VPN + data). Good for highest-security requirements. Can be added later.
Recommendation | Start with Option A (HTTPS/TLS via Gateway). All data is encrypted. Monitor transfer speeds. Add Direct Connect only if bandwidth becomes a constraint.
REGION MAPPING: AZURE → AWS
Azure EastUS2 (Virginia) | → AWS us-east-1 (N. Virginia) ¦ Sites: MWN, WLM, Safety Assessment East
Azure WestUS2 (Washington) | → AWS us-west-2 (Oregon) ¦ Sites: RNO, Safety Assessment West
Azure UKSouth (London) | → AWS eu-west-2 (London) ¦ Sites: CRP, HAR, PTH, EDI — data stays in UK
Azure WestEurope (Amsterdam) | → AWS eu-west-1 (Ireland) ¦ Sites: LEI, HER, GRO, KUO, SZG, FRE
Azure GermanyWestCentral | → AWS eu-central-1 (Frankfurt) ¦ Sites: FRI — data stays in Germany for GDPR
Data Residency Note | All EU data remains in EU. German data remains in Germany. UK data remains in UK. No cross-border data flows introduced.

## 3-Year Financial Model
3-YEAR FINANCIAL MODEL — HUBSTOR vs AWS S3 TCO COMPARISON
Assumption: 5% annual data growth ¦ AWS pricing held flat (conservative) ¦ HubStor cost held flat
Month | Period | HubStor Cost ($) | Cumulative HubStor ($) | AWS S3 Cost ($) | Cumulative AWS ($) | Monthly Saving ($) | Cumulative Saving ($) | Migration Cost ($) | Net Cumulative Saving ($)
1 | Y1M1 | 35523.12 | 35523.12 | 8126 | 8126 | 27397.12 | 27397.12 | 12000 | 15397.12
2 | Y1M2 | 35523.12 | 71046.24 | 8126 | 16252 | 27397.12 | 54794.24 | 0 | 42794.24
3 | Y1M3 | 35523.12 | 106569.36 | 8126 | 24378 | 27397.12 | 82191.36 | 0 | 70191.36
4 | Y1M4 | 35523.12 | 142092.48 | 8126 | 32504 | 27397.12 | 109588.48 | 0 | 97588.48
5 | Y1M5 | 35523.12 | 177615.6 | 8126 | 40630 | 27397.12 | 136985.6 | 0 | 124985.6
6 | Y1M6 | 35523.12 | 213138.72 | 8126 | 48756 | 27397.12 | 164382.72 | 0 | 152382.72
7 | Y1M7 | 35523.12 | 248661.84 | 8126 | 56882 | 27397.12 | 191779.84 | 0 | 179779.84
8 | Y1M8 | 35523.12 | 284184.96 | 8126 | 65008 | 27397.12 | 219176.96 | 0 | 207176.96
9 | Y1M9 | 35523.12 | 319708.08 | 8126 | 73134 | 27397.12 | 246574.08 | 0 | 234574.08
10 | Y1M10 | 35523.12 | 355231.2 | 8126 | 81260 | 27397.12 | 273971.2 | 0 | 261971.2
11 | Y1M11 | 35523.12 | 390754.32 | 8126 | 89386 | 27397.12 | 301368.32 | 0 | 289368.32
12 | Y1M12 | 35523.12 | 426277.44 | 8126 | 97512 | 27397.12 | 328765.44 | 0 | 316765.44
13 | Y2M1 | 37299.276 | 463576.716 | 8532.3 | 106044.3 | 28766.976 | 357532.416 | 0 | 345532.416
14 | Y2M2 | 37299.276 | 500875.992 | 8532.3 | 114576.6 | 28766.976 | 386299.392 | 0 | 374299.392
15 | Y2M3 | 37299.276 | 538175.268 | 8532.3 | 123108.9 | 28766.976 | 415066.368 | 0 | 403066.368
16 | Y2M4 | 37299.276 | 575474.544 | 8532.3 | 131641.2 | 28766.976 | 443833.344 | 0 | 431833.344
17 | Y2M5 | 37299.276 | 612773.82 | 8532.3 | 140173.5 | 28766.976 | 472600.32 | 0 | 460600.32
18 | Y2M6 | 37299.276 | 650073.096 | 8532.3 | 148705.8 | 28766.976 | 501367.296 | 0 | 489367.296
19 | Y2M7 | 37299.276 | 687372.372 | 8532.3 | 157238.1 | 28766.976 | 530134.272 | 0 | 518134.272
20 | Y2M8 | 37299.276 | 724671.648 | 8532.3 | 165770.4 | 28766.976 | 558901.248 | 0 | 546901.248
21 | Y2M9 | 37299.276 | 761970.924 | 8532.3 | 174302.7 | 28766.976 | 587668.224 | 0 | 575668.224
22 | Y2M10 | 37299.276 | 799270.2 | 8532.3 | 182835 | 28766.976 | 616435.2 | 0 | 604435.2
23 | Y2M11 | 37299.276 | 836569.476 | 8532.3 | 191367.3 | 28766.976 | 645202.176 | 0 | 633202.176
24 | Y2M12 | 37299.276 | 873868.752 | 8532.3 | 199899.6 | 28766.976 | 673969.152 | 0 | 661969.152
25 | Y3M1 | 39164.2398 | 913032.9918 | 8958.915 | 208858.515 | 30205.3248 | 704174.4768 | 0 | 692174.4768
26 | Y3M2 | 39164.2398 | 952197.2316 | 8958.915 | 217817.43 | 30205.3248 | 734379.8016 | 0 | 722379.8016
27 | Y3M3 | 39164.2398 | 991361.4714 | 8958.915 | 226776.345 | 30205.3248 | 764585.1264 | 0 | 752585.1264
28 | Y3M4 | 39164.2398 | 1030525.7112 | 8958.915 | 235735.26 | 30205.3248 | 794790.4512 | 0 | 782790.4512
29 | Y3M5 | 39164.2398 | 1069689.951 | 8958.915 | 244694.175 | 30205.3248 | 824995.776 | 0 | 812995.776
30 | Y3M6 | 39164.2398 | 1108854.1908 | 8958.915 | 253653.09 | 30205.3248 | 855201.1008 | 0 | 843201.1008
31 | Y3M7 | 39164.2398 | 1148018.4306 | 8958.915 | 262612.005 | 30205.3248 | 885406.4256 | 0 | 873406.4256
32 | Y3M8 | 39164.2398 | 1187182.6704 | 8958.915 | 271570.92 | 30205.3248 | 915611.7504 | 0 | 903611.7504
33 | Y3M9 | 39164.2398 | 1226346.9102 | 8958.915 | 280529.835 | 30205.3248 | 945817.0752 | 0 | 933817.0752
34 | Y3M10 | 39164.2398 | 1265511.15 | 8958.915 | 289488.75 | 30205.3248 | 976022.4 | 0 | 964022.4
35 | Y3M11 | 39164.2398 | 1304675.3898 | 8958.915 | 298447.665 | 30205.3248 | 1006227.7248 | 0 | 994227.7248
36 | Y3M12 | 39164.2398 | 1343839.6296 | 8958.915 | 307406.58 | 30205.3248 | 1036433.0496 | 0 | 1024433.0496
ANNUAL SUMMARY
Year | HubStor Annual | AWS S3 Annual | Gross Saving | Migration Cost | Net Saving | ROI %
Year 1 | 426277.44 | 97512 | 328765.44 | 12000 | 316765.44 | 2640%
Year 2 | 447591.312 | 102387.6 | 345203.712 | 0 | 345203.712
Year 3 | 469970.8776 | 107506.98 | 362463.8976 | 0 | 362463.8976
3-Year Total | 1343839.6296 | 307406.58 | 1036433.0496 | 12000 | 1024433.0496