## Assumptions
CENTRAL ASSUMPTIONS — ALL INPUTS IN ONE PLACE
Yellow = hardcoded inputs (change here) ¦ All other sheets reference these cells ¦ Black text = formula ¦ Blue text = linked input
STORAGE VOLUMES (from HubStor Master Report v5)
Parameter | Cell Ref | Value | Unit | Source / Notes
Standard tier GiB | A6 | 7775.51 | GiB | HubStor Master Report v5 actuals
Hot tier GiB | A7 | 7401.73 | GiB | HubStor Master Report v5 actuals
Cool tier GiB | A8 | 165555.92 | GiB | HubStor Master Report v5 actuals
Cold tier GiB | A9 | 3195.69 | GiB | HubStor Master Report v5 actuals
Archive tier GiB | A10 | 882775.79 | GiB | HubStor Master Report v5 actuals
GiB → GB conversion factor | A11 | 1.074 | × | 1 GiB = 1.074 GB (decimal)
GiB per TiB (divisor) | A12 | 1024 | ÷ | 1 TiB = 1024 GiB
Total GiB (all tiers) | A13 | 1066704.64 | GiB | Sum of all five tiers
Total TiB | A14 | 1041.7038 | TiB | Total GiB ÷ 1,024
Total GB (decimal) | A15 | 1145640.7834 | GB | Total GiB × 1.074 (for Azure/AWS pricing which uses decimal GB)
US region GiB | A16 | 294470.97 | GiB | EastUS2 + WestUS2 (from Master Report)
EU region GiB | A17 | 772233.67 | GiB | UKSouth + WestEurope + GermanyWestCentral
US region GB | A18 | 316261.8218 | GB | US GiB × 1.074
EU region GB | A19 | 829378.9616 | GB | EU GiB × 1.074
AZURE / HUBSTOR PRICING
Parameter | Cell Ref | Value | Unit | Source / Notes
Azure Standard/Hot $/GB/mo | A23 | 0.02 | $/GB/mo | Azure Blob Standard pricing (public)
Azure Cool $/GB/mo | A24 | 0.015 | $/GB/mo | Azure Blob Cool tier
Azure Cold $/GB/mo | A25 | 0.01 | $/GB/mo | Azure Blob Cold tier
Azure Archive $/GB/mo | A26 | 0.002 | $/GB/mo | Azure Blob Archive tier
HubStor mgmt fee % of storage | A27 | 34.28% | % | Actual ratio: $9,068 non-storage ÷ $26,455 storage from Master Report
Azure Cool retrieval $/GB | A28 | 0.01 | $/GB | Azure Blob Cool read charge
Azure Cold retrieval $/GB | A29 | 0.03 | $/GB | Azure Blob Cold read charge
Azure Archive rehydration $/GB | A30 | 0.022 | $/GB | Standard rehydration priority (~15hr wait)
Azure egress tier1 $/GB | A31 | 0.087 | $/GB | 0–10 TB internet egress
Azure egress tier2 $/GB | A32 | 0.083 | $/GB | 10–50 TB internet egress
Azure egress tier3 $/GB | A33 | 0.07 | $/GB | 50–150 TB internet egress
Azure egress tier4 $/GB | A34 | 0.05 | $/GB | >150 TB internet egress
AWS PRICING
Parameter | Cell Ref | Value | Unit | Source / Notes
S3 Standard $/GB/mo (US) | A38 | 0.023 | $/GB/mo | AWS us-east-1 list price 2026
S3 Standard $/GB/mo (EU) | A39 | 0.024 | $/GB/mo | AWS EU regions list price
S3 Standard-IA $/GB/mo (US) | A40 | 0.0125 | $/GB/mo | AWS Standard-IA storage rate
S3 Standard-IA $/GB/mo (EU) | A41 | 0.013 | $/GB/mo | AWS EU Standard-IA
S3 Glacier IR $/GB/mo (US) | A42 | 0.004 | $/GB/mo | Glacier Instant Retrieval
S3 Glacier IR $/GB/mo (EU) | A43 | 0.0045 | $/GB/mo | Glacier IR EU
S3 Glacier Deep Archive $/GB/mo (US) | A44 | 0.00099 | $/GB/mo | Glacier Deep Archive (cheapest tier)
S3 Glacier Deep Archive $/GB/mo (EU) | A45 | 0.001 | $/GB/mo | Glacier Deep Archive EU
S3 Standard PUT $/1K requests | A46 | 0.005 | $/1K | PUT/COPY/POST/LIST Standard
S3 Standard-IA PUT $/1K requests | A47 | 0.01 | $/1K | IA has higher PUT rate
S3 Glacier Deep Archive PUT $/1K | A48 | 0.05 | $/1K | 10× Standard — file size matters
S3 API non-storage overhead % | A49 | 2% | % | Estimated ongoing API/request costs as % of storage (conservative)
Glacier Deep Archive retrieval $/GB | A50 | 0.02 | $/GB | Data retrieval fee from Deep Archive
S3 egress to internet $/GB (first 10TB) | A51 | 0.09 | $/GB | S3 outbound data transfer
Storage Gateway Hardware Appliance (amortised 36mo) $/mo/site | A52 | 470 | $/mo | AWS Storage Gateway Hardware Appliance ~$16,920 list price ÷ 36 months; no EC2, no EBS
S3 Transfer Acceleration $/mo (set 0 if not used) | A53 | 0 | $/mo | Transfer Acceleration adds speed for global uploads; set $0 for archive-only workload
Number of gateway sites | A54 | 5 | sites | 5 distinct sites: US-East, US-West, UK, NL/EU, DE
CloudWatch $/mo | A55 | 31 | $/mo | Dashboards + custom metrics + alarms + log groups
KMS key $/mo per key | A56 | 1 | $/mo | AWS KMS CMK; 1 per region = 5 keys
Number of KMS keys | A57 | 5 | keys | One per AWS region
SNS alerts $/mo | A58 | 2 | $/mo | Notification topics for cost/health alerts
AWS Config $/mo | A59 | 10 | $/mo | Compliance rule evaluation
S3 ongoing API operations $/mo | A60 | 65 | $/mo | PUT new archive data + GET requests monthly
Glacier retrieval $/mo (est.) | A61 | 86 | $/mo | 0.5% of 862 TiB archive retrieved monthly × $0.02/GB
S3 egress internet $/mo (est.) | A62 | 39 | $/mo | ~10% of retrieved data goes to internet
AWS DataSync $/GB scanned | A63 | 0.0125 | $/GB | One-time migration only
Annual data growth rate | A64 | 5% | % | 5% YoY assumption for financial model
HubStor monthly cost (actual) | A65 | 35523.12 | $/mo | Actuals from Master Report — storage + non-storage

## Executive Summary
HUBSTOR → AWS S3 COMPLETE MIGRATION ¦ BUSINESS CASE & COST ANALYSIS
Prepared for Internal Review ¦ Based on HubStor Master Report v5 ¦ Full HubStor + Azure Blob replacement
CURRENT HUBSTOR + AZURE COST |  |  | AWS TOTAL MONTHLY (after migration) |  |  | MONTHLY SAVING (HubStor − AWS) |  | ONE-TIME MIGRATION COST
35523.12 |  |  | 6196.0458 |  |  | 29327.0742 |  | 121370.2342
$426,277/yr ¦ 1,042 TiB ¦ 5 Azure regions |  |  | $74,353/yr ¦ S3 storage + Gateway appliance |  |  | $351,925/yr saved ¦ 83% cost reduction |  | Payback: ~5.0 months after migration (Jan 2027 + migration cost + Phase 1 AWS overlap)
CURRENT HUBSTOR COSTS BY AZURE REGION (Source: HubStor Master Report v5)
Azure Region | Azure Location | Total Usage (GiB) | Formula: GiB | Storage Cost/mo ($) | Non-Storage/HubStor Fee ($) | Total Cost/mo ($) | Formula: Total
EastUS2 | Virginia, USA | 221472.95 | Hardcoded from Master Report | 5798.59 | 1882.71 | 7681.3 | Storage + HubStor platform/non-storage fee
GermanyWestCentral | Frankfurt, Germany | 48444.2 | Hardcoded from Master Report | 1337.27 | 411.82 | 1749.09 | Storage + HubStor platform/non-storage fee
UKSouth | London, UK | 374040.18 | Hardcoded from Master Report | 9432.17 | 3179.68 | 12611.85 | Storage + HubStor platform/non-storage fee
WestEurope | Amsterdam, Netherlands | 349749.29 | Hardcoded from Master Report | 8299.36 | 2973.19 | 11272.55 | Storage + HubStor platform/non-storage fee
WestUS2 | Washington, USA | 72998.02 | Hardcoded from Master Report | 1587.78 | 620.55 | 2208.33 | Storage + HubStor platform/non-storage fee
GRAND TOTAL | All 5 Azure Regions | 1066704.64 | SUM(C10:C14) — sum all regions | 26455.17 | 9067.95 | 35523.12 | Storage Cost + Non-Storage/HubStor platform fee
STORAGE BY AZURE TIER (all values from Assumptions sheet — change inputs there)
Azure Tier | Equiv. AWS Class | Usage (GiB) | Usage (TiB) | % of Total | Azure $/GB/mo
Standard | S3 Standard | 7775.51 | 7.5933 | 0.7289% | 0.02
Hot | S3 Standard | 7401.73 | 7.2283 | 0.6939% | 0.02
Cool | S3 Standard-IA | 165555.92 | 161.6757 | 15.52% | 0.015
Cold | S3 Glacier IR | 3195.69 | 3.1208 | 0.2996% | 0.01
Archive | S3 Deep Archive | 882775.79 | 862.0857 | 82.76% | 0.002
TOTAL |  | 1066704.64 | 1041.7038 | 100%

## Cost Comparison
AZURE HUBSTOR vs AWS S3 — COMPLETE COST COMPARISON (Storage + All Infrastructure)
All values linked to Assumptions sheet ¦ Black = formula ¦ Blue = hardcoded input ¦ Green = cross-sheet link ¦ Yellow = input cell
TIER PRICING ASSUMPTIONS (all rates from Assumptions sheet — edit there)
Storage Tier | Azure Tier | Azure $/GB/mo | Formula | AWS Class | AWS $/GB/mo (blended) | Formula | HubStor Mgmt % | Formula | Min Duration | Notes
Standard/Hot | Standard/Hot | 0.02 | Value | S3 Standard | 0.0235 | (Assumptions!C36+Assumptions!C37)/2 — avg US+EU | 34.28% | 0.002 | None | Active files; low % of total
Cool | Cool | 0.015 | 0.02 | S3 Standard-IA | 0.01275 | 0.0235 | 34.28% | 0.002 | 30 days | Retrieval fee applies
Cold | Cold | 0.01 | 0.015 | S3 Glacier IR | 0.00425 | 0.01275 | 34.28% | 0.002 | 90 days | Millisecond retrieval
Archive | Archive | 0.002 | 0.01 | S3 Deep Archive | 0.000995 | 0.00425 | 34.28% | 0.002 | 180 days | Dominant tier — 83% of data
MONTHLY COST COMPARISON BY STORAGE TIER
Tier | Usage (GiB) | Usage (TiB) | Formula: TiB | Azure Storage $/mo | Formula | HubStor Mgmt $/mo | Formula | Azure Total $/mo | Formula | AWS Storage $/mo | Formula | Monthly Saving $ | Formula
Standard/Hot | 15177.24 | 14.8215 | B13÷1024 | 326.0071 | B13×Assumptions CC23×1.074 (GiB→GB×$/GB) | 111.7552 | azure storage × HubStor mgmt% | 437.7624 | azure storage + hubstor mgmt fee | 383.0584 | B13×1.074×Blended Standard/Hot AWS price | 54.704 | Azure Total - AWS Storage = monthly saving
Cool | 165555.92 | 161.6757 | B14÷1024 | 2667.1059 | B14×Assumptions CC24×1.074 (GiB→GB×$/GB) | 914.2839 | azure storage × HubStor mgmt% | 3581.3898 | azure storage + hubstor mgmt fee | 2267.04 | B14×1.074×Standard-IA blended | 1314.3498 | Azure Total - AWS Storage = monthly saving
Cold | 3195.69 | 3.1208 | B15÷1024 | 34.3217 | B15×Assumptions CC25×1.074 (GiB→GB×$/GB) | 11.7655 | azure storage × HubStor mgmt% | 46.0872 | azure storage + hubstor mgmt fee | 14.5867 | B15×1.074×Glacier IR blended | 31.5005 | Azure Total - AWS Storage = monthly saving
Archive | 882775.79 | 862.0857 | B16÷1024 | 1896.2024 | B16×Assumptions CC26×1.074 (GiB→GB×$/GB) | 650.0182 | azure storage × HubStor mgmt% | 2546.2206 | azure storage + hubstor mgmt fee | 943.3607 | B16×1.074×Glacier Deep Archive blended | 1602.8599 | Azure Total - AWS Storage = monthly saving
STORAGE SUBTOTAL | 1066704.64 | 1041.7038 |  | 4923.6371 |  | 1687.8228 |  | 6611.4599 |  | 3608.0458 |  | 3003.4141
AWS INFRASTRUCTURE COSTS — Storage Gateway Appliance Architecture (On-prem → Appliance → S3)
Resource | Qty | Unit Cost /mo | Monthly ($) | Annual ($) | Notes
Storage Gateway Hardware Appliance (5 sites × amortised) | 5 | 470 | 2350 | 28200 | AWS-sold hardware appliance ~$16,920/unit ÷ 36mo = $470/site/mo. No EC2, no EBS needed.
S3 Transfer Acceleration (optional — set $0 for archive) | 1 | 0 | 0 | 0 | Only needed if upload speed over long-distance WAN is critical. Archive workloads: $0.
CloudWatch (monitoring, dashboards, alarms, logs) | 1 | 31 | 31 | 372 | Dashboards + custom metrics + CloudWatch alarms + log ingestion
AWS KMS — Customer Managed Keys (1 per region × 5) | 5 | 1 | 5 | 60 | $1/key/mo × 5 regions = $5/mo. Encrypts S3 objects and Gateway cache.
SNS — cost & health alert notifications | 1 | 2 | 2 | 24 | Alert topics for budget anomalies and Gateway connectivity issues
AWS Config — compliance rule evaluation | 1 | 10 | 10 | 120 | GxP/regulatory config rules on S3 buckets. Object Lock compliance checks.
S3 API Operations — ongoing PUTs/GETs (new archive writes) | 1 | 65 | 65 | 780 | Estimated monthly API cost for new data written from all 5 gateway sites
Glacier Deep Archive retrieval fees (ongoing, est. 0.5%/mo) | 1 | 86 | 86 | 1032 | 0.5% of 862 TiB retrieved/mo × $0.02/GB restore fee
S3 egress to internet (end-user retrieval, est.) | 1 | 39 | 39 | 468 | ~10% of retrieved data sent externally. Rest served within AWS/Gateway.
INFRASTRUCTURE SUBTOTAL |  |  | 2588 | 31056
TOTAL COST SUMMARY — HUBSTOR (CURRENT) vs AWS S3 COMPLETE REPLACEMENT
Line Item | Monthly ($) | Annual ($) | Saving vs HubStor | % Reduction | Notes
Current HubStor + Azure Blob (ALL-IN) | 35523.12 | 426277.44 | $0 | 0% | Actuals from Master Report
AWS S3 Storage Cost (all 5 tiers) | 3608.0458 | 43296.5492 | 31915.0742 | 89.84% | Pure S3 storage — Standard/IA/GlacierIR/DeepArchive
AWS Infrastructure (Gateway appliance + ops) | 2588 | 31056 |  |  | Appliance amortisation, KMS, CloudWatch, API ops, egress
AWS TOTAL (Storage + Infrastructure) | 6196.0458 | 74352.5492 | 29327.0742 | 82.56% | Complete like-for-like replacement of HubStor

## Migration Plan & Costs
ONE-TIME MIGRATION COSTS — COMPLETE ITEMIZED BREAKDOWN (All formulas shown)
All four cost components + AWS setup costs ¦ Black = formula ¦ Blue/Yellow = input ¦ Route: Azure → Public internet → S3 (NOT via VPN)
COMPONENT 1 — AZURE RETRIEVAL CHARGES (reading data out of Azure Blob before egress)
ℹ Standard/Hot: no retrieval fee. Cool=$0.01/GB. Cold=$0.03/GB. Archive=$0.022/GB (Standard rehydration, ~15hr wait — factor into timeline)
Azure Tier | GiB (input) | GB (decimal) | Formula: GB | Retrieval $/GB | Formula | Retrieval Cost ($) | Formula | Notes
Standard | 7775.51 | 8350.8977 | B7×Assumptions!C11 (GiB→GB) | 0 | 0 | 0 | No charge — Standard tier: read freely at no cost | No retrieval fee
Hot | 7401.73 | 7949.458 | B8×Assumptions!C11 (GiB→GB) | 0 | 0 | 0 | No charge — Hot tier: read freely at no cost | No retrieval fee
Cool | 165555.92 | 177807.0581 | B9×Assumptions!C11 (GiB→GB) | 0.01 | 0.01 | 1778.0706 | C9×E9 (GB × retrieval rate) | Per-GB read charge
Cold | 3195.69 | 3432.1711 | B10×Assumptions!C11 (GiB→GB) | 0.03 | 0.03 | 102.9651 | C10×E10 (GB × retrieval rate) | Per-GB read charge
Archive | 882775.79 | 948101.1985 | B11×Assumptions!C11 (GiB→GB) | 0.022 | 0.022 | 20858.2264 | C11×E11 (GB × retrieval rate) | Standard rehydration rate (15hr per batch)
SUBTOTAL — AZURE RETRIEVAL | [5 empty] | 22739.2621 | SUM(G7:G11) — sum all five tiers
COMPONENT 2 — AZURE EGRESS CHARGES (direct to S3 public endpoint — NOT via VPN)
ℹ VPN routing adds AWS transit/inspection costs. Use S3 public endpoints. Azure charges tiered egress: rates drop for higher volumes. First 100GB free.
Region Group | Volume (GB) | Formula: Volume | Tier1 $/GB ≤10TB | Tier2 $/GB 10-50TB | Tier3 $/GB 50-150TB | Tier4 $/GB >150TB | Egress Cost ($) | Formula | Notes
US Regions (EastUS2 + WestUS2) | 316261.8218 | Assumptions!C18 — US GiB × 1.074 | 0.087 | 0.083 | 0.07 | 0.05 | 19494.4 | eastus2+westus2 gib×1.074 then tiered: 100GB free + 9900GB×$0.087 + 40000GB×$0.083 + 100000GB×$0.070 + remainder×$0.050 | Virginia→us-east-1, Washington→us-west-2
EU Regions (UKSouth + WestEurope + GermanyWestCentral) | 829378.9616 | Assumptions!C19 — EU GiB × 1.074 | 0.087 | 0.083 | 0.07 | 0.05 | 45150.25 | eu gib×1.074 tiered: 100GB free + 9900GB×$0.087 + 40000GB×$0.083 + 100000GB×$0.070 + remainder×$0.050 | UK→eu-west-2, NL→eu-west-1, DE→eu-central-1
SUBTOTAL — AZURE EGRESS | [6 empty] | 64644.65 | SUM(H17:H18) — sum US+EU egress
COMPONENT 3 — AWS S3 PUT REQUEST CHARGES (ingress to AWS is free; API calls are not)
ℹ PUT rate varies by storage class. Glacier Deep Archive = $0.05/1K (10× Standard). Average file size is critical — adjust yellow cells. Object count = GiB×1024÷avg_MB.
Storage Class | Volume (GiB) | Avg File MB ← INPUT | Object Count | Formula: Object Count | PUT Rate ($/1K) | Formula | PUT Cost ($) | Formula | Notes
S3 Standard (Std+Hot) | 15177.24 | 10 | 1554149.376 | (B24 gib × 1024 MB/GiB) ÷ C24 (avg MB per file)) | 0.005 | 0.005 | 7.7707 | (object count ÷ 1000) × PUT rate) | Low avg size — active files
S3 Standard-IA (Cool) | 165555.92 | 50 | 3390585.2416 | (B25 gib × 1024 MB/GiB) ÷ C25 (avg MB per file)) | 0.01 | 0.01 | 33.9059 | (object count ÷ 1000) × PUT rate) | $0.01/1K — IA PUT rate higher
S3 Glacier IR (Cold) | 3195.69 | 200 | 16361.9328 | (B26 gib × 1024 MB/GiB) ÷ C26 (avg MB per file)) | 0.005 | 0.005 | 0.08181 | (object count ÷ 1000) × PUT rate) | Standard PUT rate
S3 Glacier Deep Archive | 882775.79 | 500 | 1807924.8179 | (B27 gib × 1024 MB/GiB) ÷ C27 (avg MB per file)) | 0.05 | 0.05 | 90.3962 | (object count ÷ 1000) × PUT rate) | ⚠ $0.05/1K — 10× Standard; file size critical
SUBTOTAL — S3 PUT REQUESTS | [6 empty] | 132.1546 | SUM(H24:H27) — sum all PUT tiers
COMPONENT 4 — POST-INGESTION LIFECYCLE TRANSITION CHARGES
ℹ BEST PRACTICE: PUT directly into target storage class using --storage-class flag in DataSync. This makes transition cost $0. Option B shown for reference only.
Option | Target Class | Object Count | Formula | Transition $/1K | Formula | Transition Cost ($) | Formula | Recommendation
OPTION A (recommended): PUT directly to target class | All classes | 6769021.3683 | Sum of all object counts from PUT section | 0 | 0 | 0 | 0 — PUT directly into target class: no lifecycle transition | ✅ Use --storage-class flag per DataSync task. Zero cost.
OPTION B: Land in Standard, transition to Standard-IA | Standard-IA | 3390585.2416 | Cool object count from PUT section row D | 0.01 | 0.01 | 33.9059 | (object count ÷ 1000) × transition rate) | Avoid — use Option A above
OPTION B: Land in Standard, transition to Deep Archive | Glacier Deep Archive | 1807924.8179 | Archive object count from PUT section row D | 0.05 | 0.05 | 90.3962 | (object count ÷ 1000) × transition rate) | ⚠ Most expensive — avoid for 882 TiB archive data
COMPONENT 5 — AWS ONE-TIME SETUP & MIGRATION EXECUTION COSTS (complete HubStor replacement)
Item | Qty | Formula: Qty | Unit Cost ($) | Formula | Total Cost ($) | Formula | Notes
AWS DataSync — data scanning/migration fee | 1145640.7834 | Assumptions!C15 (total GB decimal) | 0.0125 | Assumptions!C63 ($0.0125/GB scanned) | 14320.5098 | qty × Unit cost | One-time migration tool — $0.0125/GB for all data scanned
Storage Gateway VM setup & config (5 sites) | 5 | Assumptions!C54 (number of sites) | 500 | Estimated IT labor per site (internal cost) | 2500 | qty × Unit cost | Install Gateway VM, configure NFS/SMB shares, test connectivity
S3 bucket creation, lifecycle policies, tagging | 1 | Fixed | 500 | One-time AWS console/CLI setup | 500 | qty × Unit cost | 5 buckets × 5 regions, lifecycle rules, Object Lock config
IAM roles, policies, KMS key setup | 1 | Fixed | 500 | One-time security config | 500 | qty × Unit cost | Gateway IAM role, DataSync role, bucket policies, KMS CMKs
Testing, validation & UAT | 1 | Fixed | 3000 | Internal resource time estimate | 3000 | qty × Unit cost | Data integrity checks, retrieval tests, connector smoke tests
HubStor subscription decommission & contract mgmt | 1 | Fixed | 2000 | Legal/admin for contract termination | 2000 | qty × Unit cost | Notice period management, final data verification, sign-off
SUBTOTAL — AWS SETUP COSTS |  |  |  |  | 22820.5098 | SUM(F40:F45) — sum all setup costs
TOTAL ONE-TIME MIGRATION COST — GRAND TOTAL SUMMARY
Line Item | Amount ($) | Formula | % of Total | Formula | Notes
1. Azure Retrieval Charges | 22739.2621 | G12 (Component 1 subtotal) | 18.74% | B50÷Grand Total
2. Azure Egress Charges | 64644.65 | H19 (Component 2 subtotal) | 53.26% | B51÷Grand Total
3. AWS S3 PUT Requests | 132.1546 | H28 (Component 3 subtotal) | 0.1089% | B52÷Grand Total
4. Lifecycle Transitions | 0 | G33 — Component 4 Option A (=$0 if PUT directly) | 0% | B53÷Grand Total
5. AWS Setup & Execution Costs | 22820.5098 | F46 — Component 5 subtotal | 18.8% | B54÷Grand Total
Contingency (10%) | 11033.6577 | SUM(B50:B54)×10% contingency buffer | 9.091% | B55÷Grand Total
★ GRAND TOTAL — ONE-TIME MIGRATION COST |  | 121370.2342 | SUM(B50:B55) — all five components + contingency
ROI & PAYBACK ANALYSIS
Metric | Value | Formula | Notes
Total One-Time Migration Cost | 121370.2342 | 121370.2342
Monthly Saving (HubStor - AWS Total/mo) | 29327.0742 | Assumptions!C65 (HubStor monthly) minus Cost Comparison!B37 (AWS total) = true monthly saving
Payback Period (months) | 4.9912 | (Migration cost + AWS overlap in Phase 1) ÷ monthly saving = true payback from Jan 2027
Year 1 Net Saving (12mo saving - migration) | 230554.6566 | (monthly saving × 12) - migration cost)
4-Year Total Net Saving (Jan 2027–Dec 2030) | 1286329.3289 | (Monthly saving × 48 months) minus one-time migration cost = 4-year net saving

## Risks & Assumptions
RISKS & ASSUMPTIONS — COMPLETE HUBSTOR + AZURE BLOB REPLACEMENT WITH AWS S3
Must be reviewed and signed off before project commencement ¦ Owner = Cloud Architecture Team
KEY ASSUMPTIONS
# | Category | Assumption | Basis / Source | If Wrong — Impact | Owner | Status
A1 | Pricing | AWS list pricing held flat for 3-year model | AWS published list rates March 2026 | Costs could rise — actual savings may be lower | Cloud Arch | Confirmed
A2 | Pricing | HubStor non-storage fee = 34.3% of storage cost (=$9,068÷$26,455) | HubStor Master Report v5 actuals | Ratio may vary monthly — directionally correct | Finance | Confirmed
A3 | Pricing | Azure egress billed at public internet rates (not VPN) | Architecture decision — direct to S3 public endpoint | VPN routing adds AWS transit cost ($0.02/GB) — adds ~$18K | Cloud Arch | Decision required
A4 | Data | All 1,041.7 TiB migrated to AWS (no data deleted pre-migration) | HubStor Master Report v5 — all stors migrated | Smaller dataset = lower migration cost; larger = higher | Programme Mgr | TBC
A5 | Data | Archive avg file size = 500MB (PUT cost sensitivity) | Assumed; actual could range 1MB-2GB (see sensitivity table) | At 1MB avg: PUT cost rises by $45K; at 100MB: negligible | Data Team | Verify before migration
A6 | Data | 5% annual data growth rate | Conservative industry estimate for scientific archives | Higher growth = higher AWS costs but also higher HubStor costs | Data Team | TBC
A7 | Architecture | 5 Storage Gateway VMs required (1 per major site) | Site topology from Connector Details sheet — MWN, WLM, RNO, UK, EU | More sites = higher EC2/EBS cost; fewer = simpler but single-site risk | Cloud Arch | Review with sites
A8 | Architecture | File Gateway (NFS/SMB) replaces all HubStor connectors | HubStor connector list has 17+ connectors — all routed via Gateway | Connector incompatibility = custom integration effort | App Teams | Verify each connector
A9 | Architecture | Direct Connect NOT required — public internet sufficient | Gateway uses HTTPS/TLS; adequate for archive workloads | Bandwidth constraint at peak rehydration may slow retrieval | Network Team | Monitor in pilot
A10 | Migration | Archive rehydration takes 15hr per batch (Azure Standard priority) | Azure documentation — Standard priority SLA | Expedited priority ($0.03/GB extra) available if timeline too slow | Cloud Arch | Plan buffer weeks 3-4
A11 | Migration | DataSync used for US data; Rclone for EU (avoids AWS-specific tooling) | Best practice for cross-cloud migration | Tool failure = manual fallback; add 2-week buffer | Migration Team | TBC
A12 | Compliance | S3 Object Lock (Compliance mode) used for GxP/regulated data | GxP requirement — immutable storage for defined retention period | Incorrect retention period = compliance violation | QA/Regulatory | Legal review required
A13 | Compliance | Data residency preserved — UK data stays in eu-west-2 (London) | GDPR / UK data protection requirement | Wrong region = regulatory breach | Legal/Privacy | Confirmed in architecture
A14 | Compliance | German data stays in eu-central-1 (Frankfurt) | GDPR German data sovereignty requirement | Wrong region = regulatory breach | Legal/Privacy | Confirmed in architecture
A15 | Commercial | HubStor contract allows termination with 30-day notice | Assumed standard SaaS terms — verify contract | Longer notice = overlap billing period; add to migration cost | Legal | Verify contract ASAP
A16 | Commercial | Wasabi not selected — AWS chosen for S3 API compatibility and GxP compliance | Technical decision | Wasabi at $6.99/TB = slightly cheaper; recalculate if Wasabi selected | Cloud Arch | Decision confirmed
RISK REGISTER
# | Risk Description | Likelihood | Impact | Risk Score | Mitigation | Residual Risk | Owner
R1 | Archive rehydration bottleneck — 882 TiB of Archive data requires up to 15hr rehydration per batch. Migration could take 8-12 weeks for archive tier alone, causing HubStor overlap billing. | HIGH | HIGH | 🔴 CRITICAL | Start archive rehydration in Month 2 immediately. Run parallel batches. Budget for 2 months HubStor overlap (~$71K) in financial model. | MEDIUM | Cloud Arch
R2 | Azure egress cost overrun — Egress calculated at $64,645 but tiered pricing assumes linear volume. Actual rates depend on billing cycle timing. | MEDIUM | MEDIUM | 🟡 MODERATE | Negotiate Azure egress credits for large migration. Pre-announce to Azure account team. Consider doing migration over 2-3 billing cycles to stay in lower tiers. | LOW | Cloud Arch / Azure Rep
R3 | HubStor connector incompatibility — 17+ connectors across multiple sites may not work transparently with S3 File Gateway. DPI connectors (APO-PR-APP-*) may have custom metadata. | MEDIUM | HIGH | 🔴 HIGH | Pilot one connector type per site in Month 2 before full migration. Test DPI connectors specifically. Have HubStor support on standby. | MEDIUM | App Teams / HubStor
R4 | Data integrity loss during migration — File corruption or missing objects during Azure→S3 transfer. | LOW | CRITICAL | 🟡 MODERATE | MD5/ETag checksums validated by DataSync. Run post-migration inventory compare (S3 Inventory vs HubStor report). Do NOT decommission HubStor until 100% verified. | LOW | Migration Team
R5 | AWS Storage Gateway performance under load — Local cache (1TB EBS) may be insufficient for sites with high concurrent archive read requests. | MEDIUM | MEDIUM | 🟡 MODERATE | Monitor cache hit ratio from day 1. Increase EBS cache to 2TB if hit ratio <80%. Pre-warm cache for frequently accessed data. | LOW | Cloud Arch
R6 | Object Lock misconfiguration on GxP data — Incorrect retention period (too short or wrong mode) creates compliance gap. | LOW | CRITICAL | 🟡 MODERATE | Legal/QA review of retention periods before bucket creation. Use Compliance mode (not Governance). Test with non-regulated data first. | LOW | QA/Regulatory/Legal
R7 | Cost model underestimation — AWS S3 Glacier Deep Archive retrieval fees may be higher than estimated if archive access is more frequent than 0.5%/month. | MEDIUM | MEDIUM | 🟡 MODERATE | Monitor S3 retrieval metrics in CloudWatch from Month 1. Set Cost Anomaly Detection alerts at 120% of budget. Review quarterly. | LOW | Cloud Arch / Finance
R8 | HubStor contract lock-in — Contract may require >30 day notice or have early termination penalties. | MEDIUM | HIGH | 🔴 HIGH | Review HubStor contract IMMEDIATELY. If >30 day notice required, adjust timeline. Factor any penalties into migration cost. | MEDIUM | Legal / Finance
R9 | EU data sovereignty breach — Data temporarily routed outside correct region during migration. | LOW | CRITICAL | 🟡 MODERATE | Enforce bucket region from day 1 with SCP (Service Control Policy). No cross-region replication. Use AWS Config rule to alert on region violations. | LOW | Cloud Arch / Legal
R10 | Bandwidth saturation during migration — Simultaneous rehydration + egress from Azure may saturate site/DC internet links. | MEDIUM | MEDIUM | 🟡 MODERATE | Schedule migration transfers outside business hours. Set bandwidth limits in DataSync/Rclone. Start with smallest stor (RMS 914 GiB) as controlled pilot. | LOW | Network Team

## 6-Month Migration Plan
6-MONTH MIGRATION PLAN — COMPLETE HUBSTOR → AWS S3 REPLACEMENT
Phased approach: Pilot → US Regions → EU Regions → Cutover ¦ Data residency preserved throughout ¦ HubStor runs in parallel until Month 6
PHASE OVERVIEW — TIMELINE AT A GLANCE
Phase | Description | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Key Milestone | Owner | Budget Impact ($) | Status
Phase 0 | Foundation & Procurement | ██████ | [5 empty] | AWS accounts active, IAM ready, HubStor contract notice served | Cloud Arch | 0 | Not started
Phase 1 | Pilot Migration (RMS East US) |  | ██████ |  |  |  |  | RMS 914 GiB migrated; Gateway tested; data integrity verified | Migration Team | ~$500 AWS costs only | Not started
Phase 2 | US Regions (EastUS2 + WestUS2) |  |  | ██████ |  |  |  | 294 TiB US data migrated; US sites cut over to S3 Gateway | Migration Team | 0 | Not started
Phase 3 | EU UK Region (UKSouth) |  |  |  | ██████ |  |  | 374 TiB UK data migrated; UK sites cut over | Migration Team | 0 | Not started
Phase 4 | EU Continent (WestEurope + Germany) |  |  |  |  | ██████ |  | 398 TiB EU/DE data migrated; all EU sites cut over | Migration Team | 0 | Not started
Phase 5 | Cutover, Decommission & Optimisation | [5 empty] | ██████ | HubStor subscription cancelled; zero Azure Blob spend | Cloud Arch / Finance | First full month saving realised | Not started
PHASE 0 — FOUNDATION & PROCUREMENT (Month 1: Weeks 1-4)
Week | Category | Task | Owner | Detail / Notes | Success Criteria
Week 1 | Commercial | Review and serve HubStor contract termination notice (verify notice period) | Legal / Finance | Notice period clock starts. If >30 days, adjust plan. | CONTRACT NOTICE SERVED
Week 1 | AWS Setup | Create AWS accounts per region (us-east-1, us-west-2, eu-west-2, eu-west-1, eu-central-1) | Cloud Arch | 5 AWS accounts or 1 org with SCPs per region | Accounts active
Week 1 | AWS Setup | Configure IAM: DataSync role, Gateway role, S3 bucket policies, KMS CMKs (1 per region) | Cloud Arch | All permissions least-privilege; tested with CLI | IAM complete
Week 2 | AWS Setup | Create S3 buckets with naming convention, Object Lock (Compliance mode), versioning policy | Cloud Arch | Bucket policy blocks public access; Object Lock enabled on GxP buckets | Buckets created
Week 2 | AWS Setup | Configure S3 lifecycle rules: Archive→Glacier Deep Archive on upload; Cool→Standard-IA | Cloud Arch | Lifecycle rules prevent objects landing in wrong tier | Rules active
Week 2 | Monitoring | Deploy CloudWatch dashboards: cost, storage usage, Gateway health, DataSync job status | Cloud Arch | Alerts configured for 120% budget threshold | Dashboards live
Week 3 | Network | Gateway VM deployment — install on-prem at WLM (pilot site). Configure NFS/SMB share | Network + Cloud | VM: m5.xlarge compatible VM on-prem. Attach 1TB EBS cache. Test HTTPS to S3. | WLM Gateway online
Week 3 | Network | Configure AWS VPC Gateway Endpoint for S3 (free — eliminates NAT Gateway fees if EC2 used) | Cloud Arch | Endpoint policy restricts access to specific buckets | VPC endpoint active
Week 4 | Testing | End-to-end connectivity test: write test file via Gateway → verify in S3 bucket → retrieve | Migration Team | Checksum match confirms data integrity path | E2E test PASSED
Week 4 | Documentation | Finalise migration runbook per site. DataSync job scripts prepared. Rollback plan documented | Migration Team | Runbook peer-reviewed | Runbook signed off
PHASE 1 — PILOT MIGRATION: RMS EAST US FILES (Month 2: ~914 GiB)
Week | Category | Task | Owner | Detail / Notes | Success Criteria
Week 5 | Migration | Configure AWS DataSync: source=WLM-PR-FIL-05 Azure Blob, dest=S3 us-east-1 bucket | Migration Team | 3 DataSync tasks (3 connectors); --storage-class=STANDARD_IA for RMS data | DataSync jobs configured
Week 5 | Migration | Start DataSync transfer. Monitor CloudWatch for transfer rate, errors, throughput | Migration Team | Expected: ~200GB/hr → 914 GiB ≈ 5 hours. Run overnight. | Transfer started
Week 6 | Validation | Post-transfer: S3 Inventory report vs HubStor export — compare object counts and sizes | Migration Team | 100% object count match required before proceeding | Integrity VERIFIED
Week 6 | Validation | Retrieval test: retrieve 5 random files via S3 Gateway share. Verify content matches | App Teams | All 5 files open correctly; no corruption | Retrieval PASSED
Week 6 | Cutover | Update WLM-RMS connector to point to S3 File Gateway NFS share (change target path only) | App Teams / Network | Connector writes to S3 from this point; reads via Gateway cache | Connector switched
Week 7 | Monitoring | Monitor RMS connector for 1 week: write speed, retrieval latency, error rate | Cloud Arch | Target: <5s for cached reads; <30min for uncached archive fetch | 1-week soak PASS
Week 8 | Review | Pilot retrospective: document lessons, adjust runbook, confirm Phase 2 go/no-go | Programme Mgr | Signed go/no-go decision gate | GO/NO-GO DECISION
PHASE 2 — US REGIONS: EastUS2 + WestUS2 (Month 3: ~294 TiB)
Week | Category | Task | Owner | Detail / Notes | Success Criteria
Week 9 | Migration | Begin archive rehydration for Safety Assessment East US (119 TiB archive). Submit rehydration job. | Migration Team | Azure Standard rehydration = up to 15hr. Batch by stor group. | Rehydration started
Week 9 | Migration | Deploy Gateway VM at MWN site (Safety Assessment). Configure connectors. | Cloud Arch | Mirror WLM setup. Same EBS cache size. Test connectivity. | MWN Gateway ready
Week 9 | Migration | Deploy Gateway VM at RNO site (Safety Assessment West). Configure connectors. | Cloud Arch | RNO covers WestUS2 data. | RNO Gateway ready
Week 10 | Migration | Start DataSync jobs: Microbial East US (25 TiB), RMS sub-stores remaining | Migration Team | Run overnight. Monitor DataSync CloudWatch dashboard. | Microbial migrated
Week 10 | Migration | Start DataSync jobs: Safety Assessment East US (after rehydration completes) | Migration Team | 122 TiB total. Largest US store. May take 2-3 nights. | SA East migrated
Week 11 | Migration | Start DataSync jobs: Safety Assessment West US (72 TiB WestUS2 data) | Migration Team | RNO connector data. Run over 2 nights. | SA West migrated
Week 11 | Validation | S3 Inventory cross-check for all US stores. Fix any gaps. | Migration Team | Zero discrepancy required | US inventory matched
Week 12 | Cutover | Switch all US site connectors to S3 Gateway. Disable Azure write access to US Blob containers. | App Teams | Connectors: APO-PR-APP-02 to 09, MWN-PR-FIL-01, WLM-PR-FIL-05 | US sites LIVE on S3
PHASE 3 — EU UK: UKSouth (Month 4: ~374 TiB)
Week | Category | Task | Owner | Detail / Notes | Success Criteria
Week 13 | Migration | Deploy Gateway VM in UK DC (PTH/Portishead or EDI/Edinburgh). Configure eu-west-2 bucket. | Cloud Arch | UK data must stay in eu-west-2 (London). Enforce with SCP. | UK Gateway ready
Week 13 | Migration | Begin Early Discovery UK rehydration (242 TiB archive in UKSouth — largest single store) | Migration Team | Submit Azure rehydration. Expect 15-20 hours. Plan 2-3 day window. | Rehydration queued
Week 14 | Migration | Start DataSync: Portishead Discovery (26 TiB). Run overnight. | Migration Team | PTH-Discovery connector data. | PTH migrated
Week 14 | Migration | Start DataSync: Safety Assessment UK (525 GiB). Quick transfer. | Migration Team | EDI-SafetyAssessment — small store. | EDI migrated
Week 15 | Migration | Start DataSync: Early Discovery UK (325 TiB total after rehydration) | Migration Team | Largest EU store. Will take 3-4 nights. CRP (325 TiB) + HAR (17 TiB). | UK Early Discovery migrated
Week 16 | Validation | UK S3 Inventory cross-check. Validate Object Lock applied to regulated data. | Migration + QA | QA sign-off required for GxP stores | UK inventory + GxP PASS
Week 16 | Cutover | Switch UK connectors to S3 Gateway. Verify GDPR data residency in eu-west-2. | App Teams / Legal | Connectors: APO-PR-APP-03,04,11,12,14; MWN-PR-FIL-01 | UK LIVE on S3
PHASE 4 — EU CONTINENT: WestEurope + GermanyWestCentral (Month 5: ~398 TiB)
Week | Category | Task | Owner | Detail / Notes | Success Criteria
Week 17 | Migration | Deploy Gateway VMs: Leiden NL (LEI) → eu-west-1 bucket; Freiburg DE (FRI) → eu-central-1 | Cloud Arch | German data MUST use eu-central-1 (Frankfurt). SCP enforced. | EU/DE Gateways ready
Week 17 | Migration | Begin Early Discovery NL rehydration (258 TiB archive). Submit to Azure. | Migration Team | WestEurope LEI-EarlyDiscovery. Largest EU store. | NL rehydration queued
Week 18 | Migration | Start DataSync: Discovery NL (3.9 TiB), Safety Assessment NL (18 TiB), Discovery HU (35 GiB) | Migration Team | Smaller stores first. Validate before tackling large NL store. | Small EU stores migrated
Week 18 | Migration | Start DataSync: Discovery DE (49 TiB into eu-central-1/Frankfurt) | Migration Team | FRI-Discovery. German data stays in DE. Validate region after. | DE migrated
Week 19 | Migration | Start DataSync: Discovery FI (38 TiB into eu-west-1) | Migration Team | KUO-Discovery. Finnish data via Amsterdam region. | FI migrated
Week 19 | Migration | Start DataSync: Early Discovery NL (286 TiB after rehydration) | Migration Team | Biggest EU migration. Run over 4-5 nights. | NL Early Discovery migrated
Week 20 | Validation | Full EU inventory cross-check. German data residency confirmed. FR/NL/FI/HU data in eu-west-1. | Migration + Legal | Data residency audit report produced | EU inventory + residency PASS
Week 20 | Cutover | Switch all EU connectors to S3 Gateway. Disable Azure EU Blob write access. | App Teams | All APO and FIL connectors for EU sites | ALL EU LIVE on S3
PHASE 5 — CUTOVER, DECOMMISSION & OPTIMISATION (Month 6)
Week | Category | Task | Owner | Detail / Notes | Success Criteria
Week 21 | Cutover | Final validation: all sites reading/writing from S3 for 2 weeks. Zero Azure Blob writes. | Cloud Arch | CloudWatch confirms 0 bytes written to Azure | Zero-Azure confirmed
Week 21 | Cutover | Run full S3 Inventory vs original HubStor Master Report — final count match | Migration Team | 100% object count and size match required | FINAL INTEGRITY PASS
Week 21 | Commercial | Submit HubStor subscription cancellation. Provide data deletion confirmation if required. | Finance / Legal | Contract termination executed. Confirm no auto-renewal. | HubStor CANCELLED
Week 22 | Commercial | Terminate Azure Blob Storage accounts (all 5 regions). Download final invoices. | Finance / Cloud Arch | Azure cost stops. Final invoice received. | Azure Blob TERMINATED
Week 22 | Optimisation | Enable S3 Storage Lens — review storage efficiency, lifecycle policy effectiveness | Cloud Arch | Identify any objects in wrong tier; fix lifecycle rules | Storage Lens active
Week 22 | Optimisation | Enable Cost Anomaly Detection — alert if AWS bill exceeds $X,000 | Finance | Anomaly detector configured; tested with manual trigger | Cost alerts live
Week 23 | Monitoring | First clean month: AWS-only bill. Reconcile vs cost model. Report actual vs projected saving. | Finance | Report to stakeholders: actual vs $30,961 monthly saving target | Month 1 saving report
Week 24 | Closeout | Migration project retrospective. Update runbooks. Archive project docs. Celebrate! 🎉 | Programme Mgr | Lessons learned documented; team recognised | PROJECT CLOSED

## Financial Model (Jun26-Dec30)
FINANCIAL MODEL — Jun 2026 to Dec 2030 ¦ Migration Period + 4-Year AWS TCO
Jul 1 – Dec 31 2026: RAMPED migration — AWS grows as gateways come online, migration cost distributed by activity type ¦ HubStor reduces from Oct as Azure regions deleted ¦ Jan 2027–Dec 2030: AWS only
MODEL INPUTS — all linked to Assumptions & Cost Comparison (change values there)
HubStor + Azure monthly cost (current actuals) | 35523.12
AWS Total monthly — storage + Gateway appliance + all infra | 6196.0458
One-time migration cost (total) | 121370.2342
Annual data growth rate (applied from 2028 onwards) | 5%
Monthly saving once fully on AWS (B5 − B6) | 29327.0742
Migration period (months: Jun–Dec 2026) | 6
AWS costs already paid during migration overlap (Jul–Dec 2026) | 25007.64 | Sum of AWS ramp-up costs during migration (Jul–Dec). These must also be recovered from savings.
Payback — months from Jan 2027 (migration cost + AWS overlap ÷ monthly saving) | 4.9912 | 5.0 months from Jan 2027 ¦ Formula: (migration cost + Phase 1 AWS overlap) ÷ monthly saving ¦ ~May 2027
PHASE 1 — MIGRATION PERIOD (Jul 1, 2026 – Dec 31, 2026) ¦ AWS ramps up month by month ¦ HubStor steps down as Azure regions deleted from Oct
Migration cost distributed across 6 months by activity: data-transfer costs follow the data ramp ¦ gateway installs match each site go-live ¦ testing & decommission back-loaded to Nov–Dec
# | Calendar Month | HubStor + Azure ($) [ramps ↓ from Oct] | AWS Total ($) [ramps ↑ all 6 months] | Combined Spend ($) | Migration Cost ($) [distributed by activity] | Migration Cost — What's included | Net Cumulative Saving ($)
1 | Jul 2026 | 35523.12 | 1429.61 | 61006.78 | 24054.05 | AWS: 1 gateway online (US-East). 20% of data migrated to S3. /// Mig cost: S3/IAM setup + DataSync: 20% of data transfer costs + US-East gateway install | -59577.17
2 | Aug 2026 | 35523.12 | 2440.82 | 55316.97 | 17353.03 | AWS: 2 gateways live (US-East + US-West). 35% migrated. /// Mig cost: DataSync: 15% of data transfer costs + US-West gateway install | -112453.32
3 | Sep 2026 | 35523.12 | 3812.83 | 67891.01 | 28555.06 | AWS: 3 gateways live (US + UK). 60% migrated. /// Mig cost: DataSync: 25% of data transfer costs (largest batch — UK 374 TiB) + UK gateway install | -176531.5
4 | Oct 2026 | 31565.7 | 5004.44 | 59854.19 | 23284.05 | AWS: 4 gateways live (US + UK + EU-NL). 80% migrated. /// Mig cost: DataSync: 20% of data transfer costs + EU-NL gateway install + testing starts | -231381.25
5 | Nov 2026 | 11272.55 | 6123.89 | 32378.87 | 14982.43 | AWS: All 5 gateways at full capacity. 98% migrated. /// Mig cost: DataSync: 12% of data transfer costs + EU-DE gateway install + testing | -257636.23
6 | Dec 2026 | 1000 | 6196.05 | 20337.67 | 13141.62 | Final 8% data costs + testing/validation + HubStor decommission ($2,200) | -271777.85
6 mo | MIGRATION TOTAL Jul–Dec 2026 | 138135.06 | 12687.7 | 296785.49 | 93246.19 | ↑ Total investment = migration cost ($121,370) + AWS overlap ($24,791) = $146,161 ¦ Payback ~5 months from Jan 2027 ≈ Jun 2027 | -271777.85
Migration cost breakdown: Jul $24,054 (setup+20% data) ¦ Aug $17,353 (15% data) ¦ Sep $28,555 (25% data — UK batch) ¦ Oct $23,284 (20% data) ¦ Nov $14,982 (12% data+testing) ¦ Dec $13,142 (8% data+decomm) → Total = $121,370
PHASE 2 — AWS ONLY (Jan 2027 – Dec 2030) ¦ HubStor fully terminated. Azure Blob = $0. Pure AWS spend.
AWS storage grows with data volume: 5% per year from 2028. Column E = monthly saving vs old HubStor baseline ($35,523). Column H = running net cumulative saving carried forward from Dec 2026.
# | Calendar Month | HubStor + Azure ($) [= $0 from Jan 2027] | AWS Total ($) | Monthly Saving vs HubStor ($) | Cumul. Saving since Jan 2027 ($) | — | Net Cumulative Saving ($)
8 | Jan 2027 | 0 | 6196.0458 | 29327.0742 | 0 | 0 | -242450.7758
9 | Feb 2027 | 0 | 6196.0458 | 29327.0742 | 0 | 0 | -213123.7015
10 | Mar 2027 | 0 | 6196.0458 | 29327.0742 | 29327.0742 | 0 | -183796.6273
11 | Apr 2027 | 0 | 6196.0458 | 29327.0742 | 58654.1485 | 0 | -154469.5531
12 | May 2027 | 0 | 6196.0458 | 29327.0742 | 87981.2227 | 0 | -125142.4789
13 | Jun 2027 | 0 | 6196.0458 | 29327.0742 | 117308.2969 | 0 | -95815.4046
14 | Jul 2027 | 0 | 6196.0458 | 29327.0742 | 146635.3711 | 0 | -66488.3304
15 | Aug 2027 | 0 | 6196.0458 | 29327.0742 | 175962.4454 | 0 | -37161.2562
16 | Sep 2027 | 0 | 6196.0458 | 29327.0742 | 205289.5196 | 0 | -7834.1819
17 | Oct 2027 | 0 | 6196.0458 | 29327.0742 | 234616.5938 | 0 | 21492.8923
18 | Nov 2027 | 0 | 6196.0458 | 29327.0742 | 263943.6681 | 0 | 50819.9665
19 | Dec 2027 | 0 | 6196.0458 | 29327.0742 | 293270.7423 | 0 | 80147.0408
20 | Jan 2028 | 0 | 6505.8481 | 29017.2719 | 322597.8165 | 0 | 109164.3127
21 | Feb 2028 | 0 | 6505.8481 | 29017.2719 | 351924.8908 | 0 | 138181.5846
22 | Mar 2028 | 0 | 6505.8481 | 29017.2719 | 380942.1627 | 0 | 167198.8566
23 | Apr 2028 | 0 | 6505.8481 | 29017.2719 | 409959.4346 | 0 | 196216.1285
24 | May 2028 | 0 | 6505.8481 | 29017.2719 | 438976.7066 | 0 | 225233.4005
25 | Jun 2028 | 0 | 6505.8481 | 29017.2719 | 467993.9785 | 0 | 254250.6724
26 | Jul 2028 | 0 | 6505.8481 | 29017.2719 | 497011.2505 | 0 | 283267.9443
27 | Aug 2028 | 0 | 6505.8481 | 29017.2719 | 526028.5224 | 0 | 312285.2163
28 | Sep 2028 | 0 | 6505.8481 | 29017.2719 | 555045.7943 | 0 | 341302.4882
29 | Oct 2028 | 0 | 6505.8481 | 29017.2719 | 584063.0663 | 0 | 370319.7602
30 | Nov 2028 | 0 | 6505.8481 | 29017.2719 | 613080.3382 | 0 | 399337.0321
31 | Dec 2028 | 0 | 6505.8481 | 29017.2719 | 642097.6102 | 0 | 428354.304
32 | Jan 2029 | 0 | 6831.1405 | 28691.9795 | 671114.8821 | 0 | 457046.2836
33 | Feb 2029 | 0 | 6831.1405 | 28691.9795 | 700132.154 | 0 | 485738.2631
34 | Mar 2029 | 0 | 6831.1405 | 28691.9795 | 728824.1336 | 0 | 514430.2427
35 | Apr 2029 | 0 | 6831.1405 | 28691.9795 | 757516.1131 | 0 | 543122.2222
36 | May 2029 | 0 | 6831.1405 | 28691.9795 | 786208.0927 | 0 | 571814.2017
37 | Jun 2029 | 0 | 6831.1405 | 28691.9795 | 814900.0722 | 0 | 600506.1813
38 | Jul 2029 | 0 | 6831.1405 | 28691.9795 | 843592.0517 | 0 | 629198.1608
39 | Aug 2029 | 0 | 6831.1405 | 28691.9795 | 872284.0313 | 0 | 657890.1404
40 | Sep 2029 | 0 | 6831.1405 | 28691.9795 | 900976.0108 | 0 | 686582.1199
41 | Oct 2029 | 0 | 6831.1405 | 28691.9795 | 929667.9904 | 0 | 715274.0994
42 | Nov 2029 | 0 | 6831.1405 | 28691.9795 | 958359.9699 | 0 | 743966.079
43 | Dec 2029 | 0 | 6831.1405 | 28691.9795 | 987051.9494 | 0 | 772658.0585
44 | Jan 2030 | 0 | 7172.6975 | 28350.4225 | 1015743.929 | 0 | 801008.481
45 | Feb 2030 | 0 | 7172.6975 | 28350.4225 | 1044435.9085 | 0 | 829358.9035
46 | Mar 2030 | 0 | 7172.6975 | 28350.4225 | 1072786.331 | 0 | 857709.3261
47 | Apr 2030 | 0 | 7172.6975 | 28350.4225 | 1101136.7535 | 0 | 886059.7486
48 | May 2030 | 0 | 7172.6975 | 28350.4225 | 1129487.1761 | 0 | 914410.1711
49 | Jun 2030 | 0 | 7172.6975 | 28350.4225 | 1157837.5986 | 0 | 942760.5936
50 | Jul 2030 | 0 | 7172.6975 | 28350.4225 | 1186188.0211 | 0 | 971111.0161
51 | Aug 2030 | 0 | 7172.6975 | 28350.4225 | 1214538.4436 | 0 | 999461.4386
52 | Sep 2030 | 0 | 7172.6975 | 28350.4225 | 1242888.8661 | 0 | 1027811.8611
53 | Oct 2030 | 0 | 7172.6975 | 28350.4225 | 1271239.2886 | 0 | 1056162.2837
54 | Nov 2030 | 0 | 7172.6975 | 28350.4225 | 1299589.7111 | 0 | 1084512.7062
55
ANNUAL SUMMARY
Period | Calendar Year | HubStor + Azure ($) | AWS Total ($) | Gross Saving ($) | Migration / One-time ($) | Net Saving ($) | Cumul. Net Saving ($)
Phase 1 | Jul–Dec 2026 (migration) | 150407.61 | 25007.64 | - | 121370.24 | -271777.85 | -271777.85
Year 1 | Jan–Dec 2027 | 0 | 61960.4577 | 364316.9823 | 0 | 364316.9823 | 92539.1323
Year 2 | Jan–Dec 2028 | 0 | 77450.5721 | 348826.8679 | 0 | 348826.8679 | 441366.0002
Year 3 | Jan–Dec 2029 | 0 | 81323.1007 | 344954.3393 | 0 | 344954.3393 | 786320.3394
Year 4 | Jan–Dec 2030 | 0 | 85389.2558 | 340888.1842 | 0 | 340888.1842 | 1127208.5237
TOTAL | Jun 2026 – Dec 2030 | 150407.61 | 164418.6698 | 713143.8502 | 121370.24 | 1127208.5237 | 1127208.5237

## Architecture & Connectivity
AWS S3 TARGET ARCHITECTURE — CONNECTIVITY & ACCESS DESIGN
Full HubStor replacement ¦ S3 File Gateway replaces all HubStor connectors ¦ Data residency preserved per region
STORAGE GATEWAY — HOW SITES CONNECT TO S3 (replaces HubStor connector agents)
Pattern | AWS S3 File Gateway (NFS/SMB shares) → replaces every HubStor connector agent at each site. S3-compatible. No application changes needed.
What it is | A VM (VMware / Hyper-V / KVM) deployed on-prem at each site. Presents NFS or SMB shares to local applications. Data written to shares is automatically uploaded to S3 as objects with compression and encryption.
Archiving flow | Application saves file → File Gateway share → Gateway caches locally → Compresses & uploads to S3 bucket (correct storage class via lifecycle rule) → File stays accessible via share (cached read).
Retrieval flow | User requests file from Gateway share → Gateway checks local 1TB EBS cache → If cached: instant return → If not cached: fetches from S3 (Standard-IA: ms; Glacier IR: ms; Deep Archive: restore first ~12-48hr) → Returns file.
Sites & VMs | 5 Gateway VMs required: • WLM (EastUS2) → us-east-1 • RNO (WestUS2) → us-west-2 • UK sites (UKSouth) → eu-west-2 • NL/EU sites (WestEurope) → eu-west-1 • DE site (GermanyWestCentral) → eu-central-1
HubStor connectors replaced | All 17+ DPI connectors (APO-PR-APP-*), NAS connectors (MWN-PR-FIL-01, WLM-PR-FIL-05), and test connectors replaced by gateway shares. One Gateway per site serves all connectors at that site.
Migration tool | AWS DataSync for bulk one-time migration (Azure Blob → S3). DataSync handles checksums, retry, parallelism. Post-migration: Gateway handles all incremental writes; DataSync not needed.
S3 BUCKET STRATEGY
Bucket per region (5 buckets) | us-east-1: company-archive-us-east / us-west-2: company-archive-us-west / eu-west-2: company-archive-uk / eu-west-1: company-archive-eu / eu-central-1: company-archive-de
Prefix / key structure | s3://company-archive-{region}/{site-code}/{stor-name}/{year}/{month}/{filename} e.g., s3://company-archive-uk/CRP/EarlyDiscovery/2024/03/sample.raw
Storage class mapping | Standard/Hot → S3 Standard ¦ Cool → S3 Standard-IA (lifecycle Day 0) ¦ Cold → S3 Glacier Instant Retrieval ¦ Archive → S3 Glacier Deep Archive (PUT directly via --storage-class)
Lifecycle rules | Lifecycle rule 1: Objects with tag tier=cool → Standard-IA immediately. Rule 2: Objects with tag tier=archive → Glacier Deep Archive immediately. Rule 3: Incomplete multipart uploads → abort after 7 days.
Object Lock (GxP data) | Enable S3 Object Lock in Compliance mode on buckets holding GxP-regulated data (Safety Assessment, Microbial). Retention period = defined by QA/Regulatory team. Objects cannot be deleted or modified during retention.
Versioning | Enable ONLY on compliance/GxP buckets. Do NOT enable on pure archive buckets (versioning doubles storage cost for every overwrite).
Encryption | SSE-S3 (AES-256) at zero extra cost as baseline. Upgrade to SSE-KMS for GxP data requiring audit trail of key access. 1 KMS CMK per region = $5/month total.
VPC Gateway Endpoint | Deploy free S3 VPC Gateway Endpoint in each AWS region to route S3 traffic within AWS backbone — eliminates NAT Gateway data processing charges if any EC2-based processing is added later.
CONNECTIVITY OPTIONS
Option A — HTTPS/TLS (Recommended, chosen for this design) | Gateway VM uploads to S3 public endpoint over port 443 (HTTPS). Data is encrypted in transit (TLS 1.2+). No additional cost. All current sites have reliable internet. This is the chosen architecture.
Option B — AWS Site-to-Site VPN (optional add-on) | ~$0.05/hr per VPN connection = $36/mo. Use if security policy requires private connectivity. Can be added after cutover. Transit cost ~$0.01/GB within AWS. NOT required for launch.
Option C — AWS Direct Connect (optional premium) | Dedicated 1Gbps circuit ~$200-500/mo port cost. Use only if bandwidth becomes a demonstrated bottleneck after 3 months on Option A. Overkill for archive workloads.
Recommendation | Launch with Option A. Monitor Gateway CloudWatch metric WriteBytesPerSecond. If consistently >50MB/s sustained and latency is causing issues, evaluate Option B as next step.
REGION MAPPING — AZURE → AWS (data residency preserved)
Azure EastUS2 (Virginia, USA) | → AWS us-east-1 (N. Virginia) ¦ Sites: MWN, WLM ¦ Safety Assessment East, Microbial, RMS
Azure WestUS2 (Washington, USA) | → AWS us-west-2 (Oregon) ¦ Sites: RNO ¦ Safety Assessment West
Azure UKSouth (London, UK) | → AWS eu-west-2 (London) ¦ Sites: CRP, HAR, PTH, EDI ¦ UK data stays in UK ✓
Azure WestEurope (Amsterdam, NL) | → AWS eu-west-1 (Ireland) ¦ Sites: LEI, HER, GRO, KUO, SZG, FRE, LYO, EVR ¦ EU data stays in EU ✓
Azure GermanyWestCentral (Frankfurt) | → AWS eu-central-1 (Frankfurt) ¦ Sites: FRI ¦ German data stays in Germany (GDPR) ✓
GDPR / Data Sovereignty | No data crosses borders. UK data: eu-west-2 (London). German data: eu-central-1 (Frankfurt). All EU data in EU. S3 bucket region is enforced by SCP (Service Control Policy) blocking bucket creation in wrong regions.