## Key Assumptions
HUBSTOR → AWS S3 MIGRATION ¦ KEY ASSUMPTIONS & CAVEATS
These assumptions must be reviewed and validated before the migration programme is formally approved. Any change to these assumptions may materially affect costs, timelines, or feasibility.
BUSINESS & SCOPE ASSUMPTIONS
# | Assumption | Detail & Implication | Status / Action Required
A1 | HubStor advanced features NOT included in new architecture | We have NOT replicated HubStor-specific features such as content indexing, advanced discovery, legal hold workflow, or smart tiering intelligence. These are excluded because it is currently UNKNOWN whether these features are actively used by any CRL site or user. If any site relies on these features, additional tooling (e.g. AWS OpenSearch, Elasticsearch, or a third-party discovery layer) would need to be scoped and costed separately. | ⚠ Validate with site leads before migration start
A2 | Discovery sites: potential divestitures not modelled | Several Discovery sites (LEI, HER, GRO, KUO, SZG, FRE, LYO, EVR and others) may be subject to divestiture. This analysis is based on CURRENT usage and storage volumes across all sites. If sites are divested, storage volumes and costs will reduce — meaning our AWS cost will be LOWER than modelled, and savings will be HIGHER. No downside risk from divestitures. If divestitures happen mid-migration, adjust the relevant gateway and S3 bucket accordingly. | ✅ Conservative (upside only if divestitures occur)
A3 | Contractual obligations & data retention policy not yet verified | We have assumed a 6-month migration window (Jul–Dec 2026) and HubStor termination from Jan 2027. HOWEVER: HubStor's contract notice period, any early termination penalties, and site-specific data retention policies (e.g. regulatory holds, litigation hold) have NOT been formally reviewed. These may affect: (1) the earliest possible HubStor termination date, (2) which data can be deleted from Azure and when, and (3) minimum retention periods before data can be moved. Legal and compliance review MUST be completed before finalising the migration schedule. | 🔴 CRITICAL — Legal/Compliance review required BEFORE approval
A4 | HubStor not used for regulated / validated GxP systems | This analysis assumes HubStor does not hold data from GxP-regulated or computer-system-validated environments. If HubStor IS used as part of a validated system (e.g. LIMS, ELN, laboratory instrument data), then: (1) migration must follow a validated CSV/change control process, (2) IQ/OQ/PQ testing may be required, (3) migration timelines will extend significantly, and (4) QA/Regulatory sign-off is mandatory before cutover. Please confirm with QA, Regulatory, and IT Compliance that no validated systems write to HubStor. | 🔴 CRITICAL — QA/Regulatory confirmation required
A5 | All migration work performed by CRL internal resources (no external vendor) | The cost model includes ZERO external vendor or consultancy fees. All activities — AWS account setup, IAM configuration, Storage Gateway installation, DataSync migration jobs, connector testing, validation, and HubStor decommission — are assumed to be executed by CRL's internal Cloud/IT team. If external resource is required (e.g. AWS Professional Services, system integrator, or HubStor migration support), an additional cost of $50K–$150K should be budgeted. Internal resource time has not been separately costed (opportunity cost only). | ⚠ Confirm internal resource availability before commitment
A6 | Azure Backup & DataBox: $3,000/mo additional charge included | An additional $3,000/month Azure charge for Backup services and DataBox has been identified and IS included in this analysis as a separate line item in the current cost. This charge ceases when Azure is fully decommissioned (Dec 2026). It increases the true current Azure cost baseline and therefore increases the monthly saving. | ✅ Included in cost model — verified $3,000/mo
A7 | AWS costs held flat for Year 1 (2027); 5% growth from Year 2 (2028) | AWS storage and infrastructure pricing is assumed constant in 2027 (no growth). From 2028 onwards, data volume grows at 5% per year (conservative), increasing S3 storage costs. AWS list prices are not assumed to increase. Gateway appliance cost is amortised over 36 months. | ✅ Conservative growth assumption
A8 | Storage Gateway: File Gateway VM on EC2 t3.xlarge (recurring $130/mo/site) | AWS S3 File Gateway VM runs on EC2 t3.xlarge at each of the 5 sites ($130/mo/site = $650/mo total). This is a RECURRING monthly cost from the moment the Gateway goes live during migration. Gateway presents NFS/SMB file shares to applications, replacing HubStor connectors permanently. AWS Total post-migration = S3 $3,608 + Gateway EC2 $650 + ops $238 = $4,496/mo. | ✅ EC2 Gateway $650/mo — recurring post-migration. AWS Total = $4,496/mo
A9 | HubStor costs based on Azure Blob Storage charges (from Master Report v5) | The HubStor cost model uses actuals from HubStor Master Report v5. Monthly HubStor Azure Blob Storage charges = $26,455.17/mo across 5 regions. Azure Backup/DataBox = $3,000/mo. Total current baseline = $29,455.17/mo. | ✅ Confirmed — actuals from HubStor Master Report v5
MONEY STEP — WHAT WE ARE CHANGING AND HOW SAVINGS WILL BE MEASURED
WHAT WE ARE SPECIFICALLY CHANGING: CRL currently pays $29,455/month ($353,462/year) for HubStor Azure Blob Storage ($26,455/mo) and Azure Backup/DataBox ($3,000/mo) to store 1,041.7 TiB of scientific and regulatory data across 5 Azure regions. This project migrates all data to AWS S3 using AWS Storage Gateway File Gateways at each site, terminates the HubStor subscription, and decommissions all Azure Blob storage. The change replaces a recurring managed storage service with lower-cost, directly-managed cloud object storage at $6,196/month — a saving of $23,259/month from January 2027.
HOW SUCCESS WILL BE TRACKED AND MEASURED: (1) MONTHLY COST REDUCTION — AWS bill confirmed below $6,400/month (vs current $29,455/mo) from January 2027 onwards, verified through AWS Cost Explorer and monthly finance reporting. (2) HUBSTOR INVOICE TO $0 — HubStor subscription invoice confirmed as $0 from January 2027, evidenced by contract termination confirmation and final billing statement. (3) PAYBACK ACHIEVED — Net cumulative saving turns positive within ~6.3 months of migration completion (approx Jul 2027), tracked in the Financial Model Net Cumulative Saving column. (4) DATA INTEGRITY VERIFIED — 100% object count match between HubStor export and S3 inventory confirmed before each site cutover, documented in the migration runbook sign-off. (5) 4-YEAR BENEFIT — Projected net saving of ~$851K over 4 years (Jan 2027–Dec 2030) against the one-time migration investment of ~$121,000, representing a 79% cost reduction.
BENEFIT SUMMARY: Monthly saving = $23,259/mo (79% cost reduction) ¦ Annual saving = $279,109/yr ¦ One-time migration cost ≈ $121,000 ¦ Payback ≈ 6.3 months from Jan 2027 ¦ 4-Year net saving ≈ $851K
This document is prepared for internal CRL review only. Costs are estimates based on published list pricing as of Q1 2026 and actual HubStor Master Report data. Final costs subject to AWS contract negotiations, Wasabi quote, and HubStor termination terms. Not for external distribution.

## Assumptions
CENTRAL ASSUMPTIONS — ALL INPUTS IN ONE PLACE
Yellow = hardcoded inputs (change here) ¦ All other sheets reference these cells ¦ Black text = formula ¦ Blue text = linked input
STORAGE VOLUMES (from HubStor Master Report v5)
Parameter | Cell Ref | Value | Unit | Source / Notes
Standard tier GiB | A6 | 7775.51 | GiB | HubStor Master Report v5 actuals
Hot tier GiB | A7 | 7401.73 | GiB | HubStor Master Report v5 actuals
Cool tier GiB | A8 | 165555.92 | GiB | HubStor Master Report v5 actuals
Cold tier GiB | A9 | 3195.69 | GiB | HubStor Master Report v5 actuals
Archive tier GiB | A10 | 882775.79 | GiB | HubStor Master Report v5 actuals
GiB → GB conversion factor | A11 | 1.074 | × | 1 GiB = 1.074 GB (decimal)
GiB per TiB (divisor) | A12 | 1024 | ÷ | 1 TiB = 1024 GiB
Total GiB (all tiers) | A13 | 1066704.64 | GiB | Sum of all five tiers
Total TiB | A14 | 1041.7038 | TiB | Total GiB ÷ 1,024
Total GB (decimal) | A15 | 1145640.7834 | GB | Total GiB × 1.074 (for Azure/AWS pricing which uses decimal GB)
US region GiB | A16 | 294470.97 | GiB | EastUS2 + WestUS2 (from Master Report)
EU region GiB | A17 | 772233.67 | GiB | UKSouth + WestEurope + GermanyWestCentral
US region GB | A18 | 316261.8218 | GB | US GiB × 1.074
EU region GB | A19 | 829378.9616 | GB | EU GiB × 1.074
AZURE / HUBSTOR PRICING
Parameter | Cell Ref | Value | Unit | Source / Notes
Azure Standard/Hot $/GB/mo | A23 | 0.02 | $/GB/mo | Azure Blob Standard pricing (public)
Azure Cool $/GB/mo | A24 | 0.015 | $/GB/mo | Azure Blob Cool tier
Azure Cold $/GB/mo | A25 | 0.01 | $/GB/mo | Azure Blob Cold tier
Azure Archive $/GB/mo | A26 | 0.002 | $/GB/mo | Azure Blob Archive tier
Azure Cool retrieval $/GB | A28 | 0.01 | $/GB | Azure Blob Cool read charge
Azure Cold retrieval $/GB | A29 | 0.03 | $/GB | Azure Blob Cold read charge
Azure Archive rehydration $/GB | A30 | 0.022 | $/GB | Standard rehydration priority (~15hr wait)
Azure egress tier1 $/GB | A31 | 0.087 | $/GB | 0–10 TB internet egress
Azure egress tier2 $/GB | A32 | 0.083 | $/GB | 10–50 TB internet egress
Azure egress tier3 $/GB | A33 | 0.07 | $/GB | 50–150 TB internet egress
Azure egress tier4 $/GB | A34 | 0.05 | $/GB | >150 TB internet egress
AWS PRICING
Parameter | Cell Ref | Value | Unit | Source / Notes
S3 Standard $/GB/mo (US) | A38 | 0.023 | $/GB/mo | AWS us-east-1 list price 2026
S3 Standard $/GB/mo (EU) | A39 | 0.024 | $/GB/mo | AWS EU regions list price
S3 Standard-IA $/GB/mo (US) | A40 | 0.0125 | $/GB/mo | AWS Standard-IA storage rate
S3 Standard-IA $/GB/mo (EU) | A41 | 0.013 | $/GB/mo | AWS EU Standard-IA
S3 Glacier IR $/GB/mo (US) | A42 | 0.004 | $/GB/mo | Glacier Instant Retrieval
S3 Glacier IR $/GB/mo (EU) | A43 | 0.0045 | $/GB/mo | Glacier IR EU
S3 Glacier Deep Archive $/GB/mo (US) | A44 | 0.00099 | $/GB/mo | Glacier Deep Archive (cheapest tier)
S3 Glacier Deep Archive $/GB/mo (EU) | A45 | 0.001 | $/GB/mo | Glacier Deep Archive EU
S3 Standard PUT $/1K requests | A46 | 0.005 | $/1K | PUT/COPY/POST/LIST Standard
S3 Standard-IA PUT $/1K requests | A47 | 0.01 | $/1K | IA has higher PUT rate
S3 Glacier Deep Archive PUT $/1K | A48 | 0.05 | $/1K | 10× Standard — file size matters
S3 API operations overhead % | A49 | 2% | % | Estimated ongoing API/request costs as % of storage (conservative)
Glacier Deep Archive retrieval $/GB | A50 | 0.02 | $/GB | Data retrieval fee from Deep Archive
S3 egress to internet $/GB (first 10TB) | A51 | 0.09 | $/GB | S3 outbound data transfer
File Gateway VM EC2 instance $/mo per site (t3.xlarge, recurring post-migration) | A52 | 130 | $/mo/site | EC2 t3.xlarge (~$0.1664/hr) hosts the AWS S3 File Gateway VM software at each site. Recurring monthly cost: $130/mo × 5 sites = $650/mo. This is the compute cost to run the Gateway; S3 storage is separate. Alternative if CRL's existing on-prem server is used: change to $0 and add EBS disk cost only.
S3 Transfer Acceleration $/mo (set 0 if not used) | A53 | 0 | $/mo | Transfer Acceleration adds speed for global uploads; set $0 for archive-only workload
Number of gateway sites | A54 | 5 | sites | 5 distinct sites: US-East, US-West, UK, NL/EU, DE
CloudWatch $/mo | A55 | 31 | $/mo | Dashboards + custom metrics + alarms + log groups
KMS key $/mo per key | A56 | 1 | $/mo | AWS KMS CMK; 1 per region = 5 keys
Number of KMS keys | A57 | 5 | keys | One per AWS region
SNS alerts $/mo | A58 | 2 | $/mo | Notification topics for cost/health alerts
AWS Config $/mo | A59 | 10 | $/mo | Compliance rule evaluation
S3 ongoing API operations $/mo | A60 | 65 | $/mo | PUT new archive data + GET requests monthly
Glacier retrieval $/mo (est.) | A61 | 86 | $/mo | 0.5% of 862 TiB archive retrieved monthly × $0.02/GB
S3 egress internet $/mo (est.) | A62 | 39 | $/mo | ~10% of retrieved data goes to internet
AWS DataSync $/GB scanned | A63 | 0.0125 | $/GB | One-time migration only
Annual data growth rate | A64 | 5% | % | 5% YoY assumption for financial model
HubStor monthly cost (actuals from Master Report v5) | A65 | 26455.17 | $/mo | Actuals from HubStor Master Report v5 — Azure Blob Storage charges across 5 regions
Azure Backup & DataBox monthly charge | A66 | 3000 | $/mo | Additional Azure charge for Backup services + DataBox. Ceases from Jan 2027 when Azure fully decommissioned.
TOTAL current Azure + HubStor monthly (incl. Backup/DataBox) | A67 | 29455.17 | $/mo | HubStor Azure Blob $26,455.17 + Azure Backup/DataBox $3,000 = $29,455.17/mo total

## Executive Summary
HUBSTOR → AWS S3 COMPLETE MIGRATION ¦ BUSINESS CASE & COST ANALYSIS
Prepared for Internal Review ¦ Based on HubStor Master Report v5 ¦ Costs as at March 2026
CURRENT TOTAL MONTHLY COST (HubStor + Azure + Backup/DataBox) |  |  | AWS TOTAL MONTHLY (S3 + Gateway appliance + infra) |  |  | MONTHLY SAVING vs CURRENT COST (Total current − AWS) |  | ONE-TIME MIGRATION COST
29455.17 |  |  | 4496.0458 |  |  | 24959.1242 |  | 121370.2342
$353,462/yr ¦ HubStor $26,455 storage + Backup $3,000 ¦ 1,042 TiB ¦ 5 regions |  |  | $53,953/yr ¦ S3 storage + Gateway appliance + all ops |  |  | $299,509/yr saved ¦ 79.0% cost reduction |  | Payback: ~5.7 months from Jan 2027
CURRENT HUBSTOR COSTS BY AZURE REGION (Source: HubStor Master Report v5)
Azure Region | Azure Location | Total Usage (GiB) | Formula: GiB | Storage Cost/mo ($) | Total Cost/mo ($) | Formula: Total
EastUS2 | Virginia, USA | 221472.95 | Hardcoded from Master Report | 5798.59 | 5798.59 | 5798.59 | HubStor Azure Blob Storage charge
GermanyWestCentral | Frankfurt, Germany | 48444.2 | Hardcoded from Master Report | 1337.27 | 1337.27 | 1337.27 | HubStor Azure Blob Storage charge
UKSouth | London, UK | 374040.18 | Hardcoded from Master Report | 9432.17 | 9432.17 | 9432.17 | HubStor Azure Blob Storage charge
WestEurope | Amsterdam, Netherlands | 349749.29 | Hardcoded from Master Report | 8299.36 | 8299.36 | 8299.36 | HubStor Azure Blob Storage charge
WestUS2 | Washington, USA | 72998.02 | Hardcoded from Master Report | 1587.78 | 1587.78 | 1587.78 | HubStor Azure Blob Storage charge
GRAND TOTAL | All 5 Azure Regions | 1066704.64 | SUM(C10:C14) | 26455.17 | 26455.17 | Storage Cost + Total (equal here — non-storage removed) | HubStor Azure Blob Storage across all regions
STORAGE BY AZURE TIER (all values from Assumptions sheet — change inputs there)
Azure Tier | Equiv. AWS Class | Usage (GiB) | Usage (TiB) | % of Total
Standard | S3 Standard | 7775.51 | 7.5933 | 0.7289%
Hot | S3 Standard | 7401.73 | 7.2283 | 0.6939%
Cool | S3 Standard-IA | 165555.92 | 161.6757 | 15.52%
Cold | S3 Glacier IR | 3195.69 | 3.1208 | 0.2996%
Archive | S3 Deep Archive | 882775.79 | 862.0857 | 82.76%
TOTAL |  | 1066704.64 | 1041.7038 | 100%

## Cost Comparison
AZURE HUBSTOR vs AWS S3 — COMPLETE COST COMPARISON (Storage + All Infrastructure)
Prepared for Internal Review ¦ Based on HubStor Master Report v5 ¦ Costs as at March 2026
TIER PRICING ASSUMPTIONS (all rates from Assumptions sheet — edit there)
Storage Tier | Azure Tier | Azure $/GB/mo | Formula | AWS Class | AWS $/GB/mo (blended) | Formula | Min Duration | Notes
Standard/Hot | Standard/Hot | 0.02 | Value | S3 Standard | 0.0235 | 0.002 | None | Active files; low % of total
Cool | Cool | 0.015 | 0.02 | S3 Standard-IA | 0.01275 | 0.002 | 30 days | Retrieval fee applies
Cold | Cold | 0.01 | 0.015 | S3 Glacier IR | 0.00425 | 0.002 | 90 days | Millisecond retrieval
Archive | Archive | 0.002 | 0.01 | S3 Deep Archive | 0.000995 | 0.002 | 180 days | Dominant tier — 83% of data
MONTHLY COST COMPARISON BY STORAGE TIER
Tier | Usage (GiB) | Usage (TiB) | Formula: TiB | Azure Storage $/mo | Formula | Azure Total $/mo | Formula | AWS Storage $/mo | Formula | Monthly Saving $ | Formula
Standard/Hot | 15177.24 | 14.8215 | B13÷1024 | 326.0071 | B13×Assumptions CC23×1.074 (GiB→GB×$/GB) | 326.0071 | Azure storage × rate | 383.0584 | B13×1.074×Blended Standard/Hot AWS price | -57.0512 | Azure storage - AWS Storage = monthly saving per tier
Cool | 165555.92 | 161.6757 | B14÷1024 | 2667.1059 | B14×Assumptions CC24×1.074 (GiB→GB×$/GB) | 2667.1059 | Azure storage × rate | 2267.04 | B14×1.074×Standard-IA blended | 400.0659 | Azure storage - AWS Storage = monthly saving per tier
Cold | 3195.69 | 3.1208 | B15÷1024 | 34.3217 | B15×Assumptions CC25×1.074 (GiB→GB×$/GB) | 34.3217 | Azure storage × rate | 14.5867 | B15×1.074×Glacier IR blended | 19.735 | Azure storage - AWS Storage = monthly saving per tier
Archive | 882775.79 | 862.0857 | B16÷1024 | 1896.2024 | B16×Assumptions CC26×1.074 (GiB→GB×$/GB) | 1896.2024 | Azure storage × rate | 943.3607 | B16×1.074×Glacier Deep Archive blended | 952.8417 | Azure storage - AWS Storage = monthly saving per tier
STORAGE SUBTOTAL | 1066704.64 | 1041.7038 |  | 4923.6371 |  | 4923.6371 |  | 3608.0458 |  | 1315.5913
AWS INFRASTRUCTURE COSTS — S3 File Gateway VM (EC2 t3.xlarge per site → S3)
Resource | Qty | Unit Cost /mo | Monthly ($) | Annual ($) | Notes
AWS S3 File Gateway VM — EC2 t3.xlarge (×5 sites, recurring monthly) | 5 | 130 | 650 | 7800 | EC2 t3.xlarge hosts File Gateway VM software at each site. $130/mo × 5 sites = $650/mo recurring. Gateway presents NFS/SMB shares to applications, caches data locally, syncs to S3. Replaces HubStor connector agents permanently.
S3 Transfer Acceleration (optional — set $0 for archive) | 1 | 0 | 0 | 0 | Only needed if upload speed over long-distance WAN is critical. Archive workloads: $0.
CloudWatch (monitoring, dashboards, alarms, logs) | 1 | 31 | 31 | 372 | Dashboards + custom metrics + CloudWatch alarms + log ingestion
AWS KMS — Customer Managed Keys (1 per region × 5) | 5 | 1 | 5 | 60 | $1/key/mo × 5 regions = $5/mo. Encrypts S3 objects and Gateway cache.
SNS — cost & health alert notifications | 1 | 2 | 2 | 24 | Alert topics for budget anomalies and Gateway connectivity issues
AWS Config — compliance rule evaluation | 1 | 10 | 10 | 120 | GxP/regulatory config rules on S3 buckets. Object Lock compliance checks.
S3 API Operations — ongoing PUTs/GETs (new archive writes) | 1 | 65 | 65 | 780 | Estimated monthly API cost for new data written from all 5 gateway sites
Glacier Deep Archive retrieval fees (ongoing, est. 0.5%/mo) | 1 | 86 | 86 | 1032 | 0.5% of 862 TiB retrieved/mo × $0.02/GB restore fee
S3 egress to internet (end-user retrieval, est.) | 1 | 39 | 39 | 468 | ~10% of retrieved data sent externally. Rest served within AWS/Gateway.
INFRASTRUCTURE SUBTOTAL |  |  | 888 | 10656
TOTAL COST SUMMARY — HUBSTOR (CURRENT) vs AWS S3 COMPLETE REPLACEMENT
Line Item | Monthly ($) | Annual ($) | Saving vs HubStor | % Reduction | Notes
HubStor Azure Blob Storage (from Master Report v5) | 26455.17 | 317462.04 | $0 | — | Actuals from HubStor Master Report v5 — Azure Blob Storage across 5 regions
Azure Backup & DataBox (additional charge) | 3000 | 36000 | $0 | — | Backup services + DataBox ($3,000/mo). Ceases Dec 2026 when Azure fully decommissioned.
TOTAL CURRENT MONTHLY COST (ALL-IN) | 29455.17 | 353462.04 | $0 | Baseline for all saving calculations | HubStor + Azure Blob + Backup/DataBox — this is what we actually pay today
AWS S3 Storage Cost (all 5 tiers) | 3608.0458 | 43296.5492 | 25847.1242 | 87.75% | Pure S3 storage — Standard/IA/Glacier IR/Deep Archive
AWS Infrastructure (File Gateway VM EC2 + ops) | 888 | 10656 |  |  | File Gateway EC2 $650 + CloudWatch $31 + KMS $5 + SNS $2 + Config $10 + S3 API $65 + Glacier $86 + egress $39 = $888/mo
AWS TOTAL (Storage + Infrastructure) | 4496.0458 | 53952.5492 | 24959.1242 | 84.74% | True monthly saving vs total current cost (incl. Backup/DataBox)

## Migration Plan & Costs
ONE-TIME MIGRATION COSTS — COMPLETE ITEMIZED BREAKDOWN (All formulas shown)
All four cost components + AWS setup costs ¦ Black = formula ¦ Blue/Yellow = input ¦ Route: Azure → Public internet → S3 (NOT via VPN)
COMPONENT 1 — AZURE RETRIEVAL CHARGES (reading data out of Azure Blob before egress)
ℹ Standard/Hot: no retrieval fee. Cool=$0.01/GB. Cold=$0.03/GB. Archive=$0.022/GB (Standard rehydration, ~15hr wait — factor into timeline)
Azure Tier | GiB (input) | GB (decimal) | Formula: GB | Retrieval $/GB | Formula | Retrieval Cost ($) | Formula | Notes
Standard | 7775.51 | 8350.8977 | B7×Assumptions!C11 (GiB→GB) | 0 | 0 | 0 | No charge — Standard tier: read freely at no cost | No retrieval fee
Hot | 7401.73 | 7949.458 | B8×Assumptions!C11 (GiB→GB) | 0 | 0 | 0 | No charge — Hot tier: read freely at no cost | No retrieval fee
Cool | 165555.92 | 177807.0581 | B9×Assumptions!C11 (GiB→GB) | 0.01 | 0.01 | 1778.0706 | C9×E9 (GB × retrieval rate) | Per-GB read charge
Cold | 3195.69 | 3432.1711 | B10×Assumptions!C11 (GiB→GB) | 0.03 | 0.03 | 102.9651 | C10×E10 (GB × retrieval rate) | Per-GB read charge
Archive | 882775.79 | 948101.1985 | B11×Assumptions!C11 (GiB→GB) | 0.022 | 0.022 | 20858.2264 | C11×E11 (GB × retrieval rate) | Standard rehydration rate (15hr per batch)
SUBTOTAL — AZURE RETRIEVAL | [5 empty] | 22739.2621 | SUM(G7:G11) — sum all five tiers
COMPONENT 2 — AZURE EGRESS CHARGES (direct to S3 public endpoint — NOT via VPN)
ℹ VPN routing adds AWS transit/inspection costs. Use S3 public endpoints. Azure charges tiered egress: rates drop for higher volumes. First 100GB free.
Region Group | Volume (GB) | Formula: Volume | Tier1 $/GB ≤10TB | Tier2 $/GB 10-50TB | Tier3 $/GB 50-150TB | Tier4 $/GB >150TB | Egress Cost ($) | Formula | Notes
US Regions (EastUS2 + WestUS2) | 316261.8218 | Assumptions!C18 — US GiB × 1.074 | 0.087 | 0.083 | 0.07 | 0.05 | 19494.4 | eastus2+westus2 gib×1.074 then tiered: 100GB free + 9900GB×$0.087 + 40000GB×$0.083 + 100000GB×$0.070 + remainder×$0.050 | Virginia→us-east-1, Washington→us-west-2
EU Regions (UKSouth + WestEurope + GermanyWestCentral) | 829378.9616 | Assumptions!C19 — EU GiB × 1.074 | 0.087 | 0.083 | 0.07 | 0.05 | 45150.25 | eu gib×1.074 tiered: 100GB free + 9900GB×$0.087 + 40000GB×$0.083 + 100000GB×$0.070 + remainder×$0.050 | UK→eu-west-2, NL→eu-west-1, DE→eu-central-1
SUBTOTAL — AZURE EGRESS | [6 empty] | 64644.65 | SUM(H17:H18) — sum US+EU egress
COMPONENT 3 — AWS S3 PUT REQUEST CHARGES (ingress to AWS is free; API calls are not)
ℹ PUT rate varies by storage class. Glacier Deep Archive = $0.05/1K (10× Standard). Average file size is critical — adjust yellow cells. Object count = GiB×1024÷avg_MB.
Storage Class | Volume (GiB) | Avg File MB ← INPUT | Object Count | Formula: Object Count | PUT Rate ($/1K) | Formula | PUT Cost ($) | Formula | Notes
S3 Standard (Std+Hot) | 15177.24 | 10 | 1554149.376 | (B24 gib × 1024 MB/GiB) ÷ C24 (avg MB per file)) | 0.005 | 0.005 | 7.7707 | (object count ÷ 1000) × PUT rate) | Low avg size — active files
S3 Standard-IA (Cool) | 165555.92 | 50 | 3390585.2416 | (B25 gib × 1024 MB/GiB) ÷ C25 (avg MB per file)) | 0.01 | 0.01 | 33.9059 | (object count ÷ 1000) × PUT rate) | $0.01/1K — IA PUT rate higher
S3 Glacier IR (Cold) | 3195.69 | 200 | 16361.9328 | (B26 gib × 1024 MB/GiB) ÷ C26 (avg MB per file)) | 0.005 | 0.005 | 0.08181 | (object count ÷ 1000) × PUT rate) | Standard PUT rate
S3 Glacier Deep Archive | 882775.79 | 500 | 1807924.8179 | (B27 gib × 1024 MB/GiB) ÷ C27 (avg MB per file)) | 0.05 | 0.05 | 90.3962 | (object count ÷ 1000) × PUT rate) | ⚠ $0.05/1K — 10× Standard; file size critical
SUBTOTAL — S3 PUT REQUESTS | [6 empty] | 132.1546 | SUM(H24:H27) — sum all PUT tiers
COMPONENT 4 — POST-INGESTION LIFECYCLE TRANSITION CHARGES
ℹ BEST PRACTICE: PUT directly into target storage class using --storage-class flag in DataSync. This makes transition cost $0. Option B shown for reference only.
Option | Target Class | Object Count | Formula | Transition $/1K | Formula | Transition Cost ($) | Formula | Recommendation
OPTION A (recommended): PUT directly to target class | All classes | 6769021.3683 | Sum of all object counts from PUT section | 0 | 0 | 0 | 0 — PUT directly into target class: no lifecycle transition | ✅ Use --storage-class flag per DataSync task. Zero cost.
OPTION B: Land in Standard, transition to Standard-IA | Standard-IA | 3390585.2416 | Cool object count from PUT section row D | 0.01 | 0.01 | 33.9059 | (object count ÷ 1000) × transition rate) | Avoid — use Option A above
OPTION B: Land in Standard, transition to Deep Archive | Glacier Deep Archive | 1807924.8179 | Archive object count from PUT section row D | 0.05 | 0.05 | 90.3962 | (object count ÷ 1000) × transition rate) | ⚠ Most expensive — avoid for 882 TiB archive data
COMPONENT 5 — AWS ONE-TIME SETUP & MIGRATION EXECUTION COSTS (complete HubStor replacement)
Item | Qty | Formula: Qty | Unit Cost ($) | Formula | Total Cost ($) | Formula | Notes
AWS DataSync — data scanning/migration fee | 1145640.7834 | Assumptions!C15 (total GB decimal) | 0.0125 | Assumptions!C63 ($0.0125/GB scanned) | 14320.5098 | qty × Unit cost | One-time migration tool — $0.0125/GB for all data scanned
File Gateway VM on EC2 t3.xlarge setup & config (5 sites) | 5 | Assumptions!C54 (number of sites) | 500 | Estimated IT labor per site (internal cost) | 2500 | qty × Unit cost | Launch EC2 t3.xlarge at each site, install File Gateway software, configure NFS/SMB shares, test connectivity to S3. $500/site IT config labour. EC2 recurring from launch: $130/mo/site.
S3 bucket creation, lifecycle policies, tagging | 1 | Fixed | 500 | One-time AWS console/CLI setup | 500 | qty × Unit cost | 5 buckets × 5 regions, lifecycle rules, Object Lock config
IAM roles, policies, KMS key setup | 1 | Fixed | 500 | One-time security config | 500 | qty × Unit cost | Gateway IAM role, DataSync role, bucket policies, KMS CMKs
Testing, validation & UAT | 1 | Fixed | 3000 | Internal resource time estimate | 3000 | qty × Unit cost | Data integrity checks, retrieval tests, connector smoke tests
HubStor subscription decommission & contract mgmt | 1 | Fixed | 2000 | Legal/admin for contract termination | 2000 | qty × Unit cost | Notice period management, final data verification, sign-off
SUBTOTAL — AWS SETUP COSTS |  |  |  |  | 22820.5098 | SUM(F40:F45) — sum all setup costs
TOTAL ONE-TIME MIGRATION COST — GRAND TOTAL SUMMARY
Line Item | Amount ($) | Formula | % of Total | Formula | Notes
1. Azure Retrieval Charges | 22739.2621 | G12 (Component 1 subtotal) | 18.74% | B50÷Grand Total
2. Azure Egress Charges | 64644.65 | H19 (Component 2 subtotal) | 53.26% | B51÷Grand Total
3. AWS S3 PUT Requests | 132.1546 | H28 (Component 3 subtotal) | 0.1089% | B52÷Grand Total
4. Lifecycle Transitions | 0 | G33 — Component 4 Option A (=$0 if PUT directly) | 0% | B53÷Grand Total
5. AWS Setup & Execution Costs | 22820.5098 | F46 — Component 5 subtotal | 18.8% | B54÷Grand Total
Contingency (10%) | 11033.6577 | SUM(B50:B54)×10% contingency buffer | 9.091% | B55÷Grand Total
★ GRAND TOTAL — ONE-TIME MIGRATION COST |  | 121370.2342 | SUM(B50:B55) — all five components + contingency
ROI & PAYBACK ANALYSIS
Metric | Value | Formula | Notes
Total One-Time Migration Cost | 121370.2342 | 121370.2342
Monthly Saving (HubStor - AWS Total/mo) | 24959.1242 | Assumptions!C67 (HubStor $26,455 + Backup $3,000 = $29,455) minus Cost Comparison!B39 (AWS total)
Payback Period (months) | 5.6864 | (Migration cost + AWS overlap in Phase 1) ÷ monthly saving = true payback from Jan 2027 | Months from Jan 2027 until net cumulative saving turns positive. Matches Financial Model: H80 ÷ monthly saving = months to break-even.
Year 1 Gross Saving (Jan–Dec 2027, 12 months × monthly saving) | 299509.4908 | Monthly saving × 12 months. Migration cost is captured in Phase 1 (Jul–Dec 2026). | Consistent with Financial Model Annual Summary Year 1 gross saving
4-Year Gross Saving (Jan 2027–Dec 2030, 48 months) | 1198037.963 | Monthly saving × 48 months (Years 1–4). Gross saving before migration investment.
Net Cumulative Saving — end of Year 1 (Dec 2027) | 157581.6108 | From Financial Model cumulative net saving column — includes Phase 1 migration cost and AWS overlap. | Consistent with Financial Model Annual Summary H81
Net Cumulative Saving — end of Year 4 (Dec 2030) | 1039378.0487 | From Financial Model cumulative net saving — full 4-year net after all migration costs. | Consistent with Financial Model Annual Summary H84

## Risks & Assumptions
RISKS & ASSUMPTIONS — COMPLETE HUBSTOR + AZURE BLOB REPLACEMENT WITH AWS S3
Must be reviewed and signed off before project commencement ¦ Owner = Cloud Architecture Team
KEY ASSUMPTIONS
# | Category | Assumption | Basis / Source | If Wrong — Impact | Owner | Status
A1 | Pricing | AWS list pricing held flat for 3-year model | AWS published list rates March 2026 | Costs could rise — actual savings may be lower | Cloud Arch | Confirmed
A2 | Pricing | HubStor storage costs = 100% of Azure Blob charges from Master Report v5 ($26,455.17/mo) | HubStor Master Report v5 actuals | Ratio may vary monthly — directionally correct | Finance | Confirmed
A3 | Pricing | Azure egress billed at public internet rates (not VPN) | Architecture decision — direct to S3 public endpoint | VPN routing adds AWS transit cost ($0.02/GB) — adds ~$18K | Cloud Arch | Decision required
A4 | Data | All 1,041.7 TiB migrated to AWS (no data deleted pre-migration) | HubStor Master Report v5 — all stors migrated | Smaller dataset = lower migration cost; larger = higher | Programme Mgr | TBC
A5 | Data | Archive avg file size = 500MB (PUT cost sensitivity) | Assumed; actual could range 1MB-2GB (see sensitivity table) | At 1MB avg: PUT cost rises by $45K; at 100MB: negligible | Data Team | Verify before migration
A6 | Data | 5% annual data growth rate | Conservative industry estimate for scientific archives | Higher growth = higher AWS costs but also higher HubStor costs | Data Team | TBC
A7 | Architecture | 5 Storage Gateway VMs required (1 per major site) | Site topology from Connector Details sheet — MWN, WLM, RNO, UK, EU | More sites = higher EC2/EBS cost; fewer = simpler but single-site risk | Cloud Arch | Review with sites
A8 | Architecture | File Gateway (NFS/SMB) replaces all HubStor connectors | HubStor connector list has 17+ connectors — all routed via Gateway | Connector incompatibility = custom integration effort | App Teams | Verify each connector
A9 | Architecture | Direct Connect NOT required — public internet sufficient | Gateway uses HTTPS/TLS; adequate for archive workloads | Bandwidth constraint at peak rehydration may slow retrieval | Network Team | Monitor in pilot
A10 | Migration | Archive rehydration takes 15hr per batch (Azure Standard priority) | Azure documentation — Standard priority SLA | Expedited priority ($0.03/GB extra) available if timeline too slow | Cloud Arch | Plan buffer weeks 3-4
A11 | Migration | DataSync used for US data; Rclone for EU (avoids AWS-specific tooling) | Best practice for cross-cloud migration | Tool failure = manual fallback; add 2-week buffer | Migration Team | TBC
A12 | Compliance | S3 Object Lock (Compliance mode) used for GxP/regulated data | GxP requirement — immutable storage for defined retention period | Incorrect retention period = compliance violation | QA/Regulatory | Legal review required
A13 | Compliance | Data residency preserved — UK data stays in eu-west-2 (London) | GDPR / UK data protection requirement | Wrong region = regulatory breach | Legal/Privacy | Confirmed in architecture
A14 | Compliance | German data stays in eu-central-1 (Frankfurt) | GDPR German data sovereignty requirement | Wrong region = regulatory breach | Legal/Privacy | Confirmed in architecture
A15 | Commercial | HubStor contract allows termination with 30-day notice | Assumed standard SaaS terms — verify contract | Longer notice = overlap billing period; add to migration cost | Legal | Verify contract ASAP
A16 | Commercial | Wasabi not selected — AWS chosen for S3 API compatibility and GxP compliance | Technical decision | Wasabi at $6.99/TB = slightly cheaper; recalculate if Wasabi selected | Cloud Arch | Decision confirmed
RISK REGISTER
# | Risk Description | Likelihood | Impact | Risk Score | Mitigation | Residual Risk | Owner
R1 | Archive rehydration bottleneck — 882 TiB of Archive data requires up to 15hr rehydration per batch. Migration could take 8-12 weeks for archive tier alone, causing HubStor overlap billing. | HIGH | HIGH | 🔴 CRITICAL | Start archive rehydration in Month 2 immediately. Run parallel batches. Budget for 2 months HubStor overlap (~$71K) in financial model. | MEDIUM | Cloud Arch
R2 | Azure egress cost overrun — Egress calculated at $64,645 but tiered pricing assumes linear volume. Actual rates depend on billing cycle timing. | MEDIUM | MEDIUM | 🟡 MODERATE | Negotiate Azure egress credits for large migration. Pre-announce to Azure account team. Consider doing migration over 2-3 billing cycles to stay in lower tiers. | LOW | Cloud Arch / Azure Rep
R3 | HubStor connector incompatibility — 17+ connectors across multiple sites may not work transparently with S3 File Gateway. DPI connectors (APO-PR-APP-*) may have custom metadata. | MEDIUM | HIGH | 🔴 HIGH | Pilot one connector type per site in Month 2 before full migration. Test DPI connectors specifically. Have HubStor support on standby. | MEDIUM | App Teams / HubStor
R4 | Data integrity loss during migration — File corruption or missing objects during Azure→S3 transfer. | LOW | CRITICAL | 🟡 MODERATE | MD5/ETag checksums validated by DataSync. Run post-migration inventory compare (S3 Inventory vs HubStor report). Do NOT decommission HubStor until 100% verified. | LOW | Migration Team
R5 | AWS Storage Gateway performance under load — Local cache (1TB EBS) may be insufficient for sites with high concurrent archive read requests. | MEDIUM | MEDIUM | 🟡 MODERATE | Monitor cache hit ratio from day 1. Increase EBS cache to 2TB if hit ratio <80%. Pre-warm cache for frequently accessed data. | LOW | Cloud Arch
R6 | Object Lock misconfiguration on GxP data — Incorrect retention period (too short or wrong mode) creates compliance gap. | LOW | CRITICAL | 🟡 MODERATE | Legal/QA review of retention periods before bucket creation. Use Compliance mode (not Governance). Test with non-regulated data first. | LOW | QA/Regulatory/Legal
R7 | Cost model underestimation — AWS S3 Glacier Deep Archive retrieval fees may be higher than estimated if archive access is more frequent than 0.5%/month. | MEDIUM | MEDIUM | 🟡 MODERATE | Monitor S3 retrieval metrics in CloudWatch from Month 1. Set Cost Anomaly Detection alerts at 120% of budget. Review quarterly. | LOW | Cloud Arch / Finance
R8 | HubStor contract lock-in — Contract may require >30 day notice or have early termination penalties. | MEDIUM | HIGH | 🔴 HIGH | Review HubStor contract IMMEDIATELY. If >30 day notice required, adjust timeline. Factor any penalties into migration cost. | MEDIUM | Legal / Finance
R9 | EU data sovereignty breach — Data temporarily routed outside correct region during migration. | LOW | CRITICAL | 🟡 MODERATE | Enforce bucket region from day 1 with SCP (Service Control Policy). No cross-region replication. Use AWS Config rule to alert on region violations. | LOW | Cloud Arch / Legal
R10 | Bandwidth saturation during migration — Simultaneous rehydration + egress from Azure may saturate site/DC internet links. | MEDIUM | MEDIUM | 🟡 MODERATE | Schedule migration transfers outside business hours. Set bandwidth limits in DataSync/Rclone. Start with smallest stor (RMS 914 GiB) as controlled pilot. | LOW | Network Team

## 6-Month Migration Plan
6-MONTH MIGRATION PLAN — COMPLETE HUBSTOR → AWS S3 REPLACEMENT
Phased approach: Pilot → US Regions → EU Regions → Cutover ¦ Data residency preserved throughout ¦ HubStor runs in parallel until Month 6
PHASE OVERVIEW — TIMELINE AT A GLANCE
Phase | Description | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Key Milestone | Owner | Budget Impact ($) | Status
Phase 0 | Foundation & Procurement | ██████ | [5 empty] | AWS accounts active, IAM ready, HubStor contract notice served | Cloud Arch | 0 | Not started
Phase 1 | Pilot Migration (RMS East US) |  | ██████ |  |  |  |  | RMS 914 GiB migrated; Gateway tested; data integrity verified | Migration Team | ~$500 AWS costs only | Not started
Phase 2 | US Regions (EastUS2 + WestUS2) |  |  | ██████ |  |  |  | 294 TiB US data migrated; US sites cut over to S3 Gateway | Migration Team | 0 | Not started
Phase 3 | EU UK Region (UKSouth) |  |  |  | ██████ |  |  | 374 TiB UK data migrated; UK sites cut over | Migration Team | 0 | Not started
Phase 4 | EU Continent (WestEurope + Germany) |  |  |  |  | ██████ |  | 398 TiB EU/DE data migrated; all EU sites cut over | Migration Team | 0 | Not started
Phase 5 | Cutover, Decommission & Optimisation | [5 empty] | ██████ | HubStor subscription cancelled; zero Azure Blob spend | Cloud Arch / Finance | First full month saving realised | Not started
PHASE 0 — FOUNDATION & PROCUREMENT (Month 1: Weeks 1-4)
Week | Category | Task | Owner | Detail / Notes | Success Criteria
Week 1 | Commercial | Review and serve HubStor contract termination notice (verify notice period) | Legal / Finance | Notice period clock starts. If >30 days, adjust plan. | CONTRACT NOTICE SERVED
Week 1 | AWS Setup | Create AWS accounts per region (us-east-1, us-west-2, eu-west-2, eu-west-1, eu-central-1) | Cloud Arch | 5 AWS accounts or 1 org with SCPs per region | Accounts active
Week 1 | AWS Setup | Configure IAM: DataSync role, Gateway role, S3 bucket policies, KMS CMKs (1 per region) | Cloud Arch | All permissions least-privilege; tested with CLI | IAM complete
Week 2 | AWS Setup | Create S3 buckets with naming convention, Object Lock (Compliance mode), versioning policy | Cloud Arch | Bucket policy blocks public access; Object Lock enabled on GxP buckets | Buckets created
Week 2 | AWS Setup | Configure S3 lifecycle rules: Archive→Glacier Deep Archive on upload; Cool→Standard-IA | Cloud Arch | Lifecycle rules prevent objects landing in wrong tier | Rules active
Week 2 | Monitoring | Deploy CloudWatch dashboards: cost, storage usage, Gateway health, DataSync job status | Cloud Arch | Alerts configured for 120% budget threshold | Dashboards live
Week 3 | Network | Gateway VM deployment — install on-prem at WLM (pilot site). Configure NFS/SMB share | Network + Cloud | VM: m5.xlarge compatible VM on-prem. Attach 1TB EBS cache. Test HTTPS to S3. | WLM Gateway online
Week 3 | Network | Configure AWS VPC Gateway Endpoint for S3 (free — eliminates NAT Gateway fees if EC2 used) | Cloud Arch | Endpoint policy restricts access to specific buckets | VPC endpoint active
Week 4 | Testing | End-to-end connectivity test: write test file via Gateway → verify in S3 bucket → retrieve | Migration Team | Checksum match confirms data integrity path | E2E test PASSED
Week 4 | Documentation | Finalise migration runbook per site. DataSync job scripts prepared. Rollback plan documented | Migration Team | Runbook peer-reviewed | Runbook signed off
PHASE 1 — PILOT MIGRATION: RMS EAST US FILES (Month 2: ~914 GiB)
Week | Category | Task | Owner | Detail / Notes | Success Criteria
Week 5 | Migration | Configure AWS DataSync: source=WLM-PR-FIL-05 Azure Blob, dest=S3 us-east-1 bucket | Migration Team | 3 DataSync tasks (3 connectors); --storage-class=STANDARD_IA for RMS data | DataSync jobs configured
Week 5 | Migration | Start DataSync transfer. Monitor CloudWatch for transfer rate, errors, throughput | Migration Team | Expected: ~200GB/hr → 914 GiB ≈ 5 hours. Run overnight. | Transfer started
Week 6 | Validation | Post-transfer: S3 Inventory report vs HubStor export — compare object counts and sizes | Migration Team | 100% object count match required before proceeding | Integrity VERIFIED
Week 6 | Validation | Retrieval test: retrieve 5 random files via S3 Gateway share. Verify content matches | App Teams | All 5 files open correctly; no corruption | Retrieval PASSED
Week 6 | Cutover | Update WLM-RMS connector to point to S3 File Gateway NFS share (change target path only) | App Teams / Network | Connector writes to S3 from this point; reads via Gateway cache | Connector switched
Week 7 | Monitoring | Monitor RMS connector for 1 week: write speed, retrieval latency, error rate | Cloud Arch | Target: <5s for cached reads; <30min for uncached archive fetch | 1-week soak PASS
Week 8 | Review | Pilot retrospective: document lessons, adjust runbook, confirm Phase 2 go/no-go | Programme Mgr | Signed go/no-go decision gate | GO/NO-GO DECISION
PHASE 2 — US REGIONS: EastUS2 + WestUS2 (Month 3: ~294 TiB)
Week | Category | Task | Owner | Detail / Notes | Success Criteria
Week 9 | Migration | Begin archive rehydration for Safety Assessment East US (119 TiB archive). Submit rehydration job. | Migration Team | Azure Standard rehydration = up to 15hr. Batch by stor group. | Rehydration started
Week 9 | Migration | Deploy Gateway VM at MWN site (Safety Assessment). Configure connectors. | Cloud Arch | Mirror WLM setup. Same EBS cache size. Test connectivity. | MWN Gateway ready
Week 9 | Migration | Deploy Gateway VM at RNO site (Safety Assessment West). Configure connectors. | Cloud Arch | RNO covers WestUS2 data. | RNO Gateway ready
Week 10 | Migration | Start DataSync jobs: Microbial East US (25 TiB), RMS sub-stores remaining | Migration Team | Run overnight. Monitor DataSync CloudWatch dashboard. | Microbial migrated
Week 10 | Migration | Start DataSync jobs: Safety Assessment East US (after rehydration completes) | Migration Team | 122 TiB total. Largest US store. May take 2-3 nights. | SA East migrated
Week 11 | Migration | Start DataSync jobs: Safety Assessment West US (72 TiB WestUS2 data) | Migration Team | RNO connector data. Run over 2 nights. | SA West migrated
Week 11 | Validation | S3 Inventory cross-check for all US stores. Fix any gaps. | Migration Team | Zero discrepancy required | US inventory matched
Week 12 | Cutover | Switch all US site connectors to S3 Gateway. Disable Azure write access to US Blob containers. | App Teams | Connectors: APO-PR-APP-02 to 09, MWN-PR-FIL-01, WLM-PR-FIL-05 | US sites LIVE on S3
PHASE 3 — EU UK: UKSouth (Month 4: ~374 TiB)
Week | Category | Task | Owner | Detail / Notes | Success Criteria
Week 13 | Migration | Deploy Gateway VM in UK DC (PTH/Portishead or EDI/Edinburgh). Configure eu-west-2 bucket. | Cloud Arch | UK data must stay in eu-west-2 (London). Enforce with SCP. | UK Gateway ready
Week 13 | Migration | Begin Early Discovery UK rehydration (242 TiB archive in UKSouth — largest single store) | Migration Team | Submit Azure rehydration. Expect 15-20 hours. Plan 2-3 day window. | Rehydration queued
Week 14 | Migration | Start DataSync: Portishead Discovery (26 TiB). Run overnight. | Migration Team | PTH-Discovery connector data. | PTH migrated
Week 14 | Migration | Start DataSync: Safety Assessment UK (525 GiB). Quick transfer. | Migration Team | EDI-SafetyAssessment — small store. | EDI migrated
Week 15 | Migration | Start DataSync: Early Discovery UK (325 TiB total after rehydration) | Migration Team | Largest EU store. Will take 3-4 nights. CRP (325 TiB) + HAR (17 TiB). | UK Early Discovery migrated
Week 16 | Validation | UK S3 Inventory cross-check. Validate Object Lock applied to regulated data. | Migration + QA | QA sign-off required for GxP stores | UK inventory + GxP PASS
Week 16 | Cutover | Switch UK connectors to S3 Gateway. Verify GDPR data residency in eu-west-2. | App Teams / Legal | Connectors: APO-PR-APP-03,04,11,12,14; MWN-PR-FIL-01 | UK LIVE on S3
PHASE 4 — EU CONTINENT: WestEurope + GermanyWestCentral (Month 5: ~398 TiB)
Week | Category | Task | Owner | Detail / Notes | Success Criteria
Week 17 | Migration | Deploy Gateway VMs: Leiden NL (LEI) → eu-west-1 bucket; Freiburg DE (FRI) → eu-central-1 | Cloud Arch | German data MUST use eu-central-1 (Frankfurt). SCP enforced. | EU/DE Gateways ready
Week 17 | Migration | Begin Early Discovery NL rehydration (258 TiB archive). Submit to Azure. | Migration Team | WestEurope LEI-EarlyDiscovery. Largest EU store. | NL rehydration queued
Week 18 | Migration | Start DataSync: Discovery NL (3.9 TiB), Safety Assessment NL (18 TiB), Discovery HU (35 GiB) | Migration Team | Smaller stores first. Validate before tackling large NL store. | Small EU stores migrated
Week 18 | Migration | Start DataSync: Discovery DE (49 TiB into eu-central-1/Frankfurt) | Migration Team | FRI-Discovery. German data stays in DE. Validate region after. | DE migrated
Week 19 | Migration | Start DataSync: Discovery FI (38 TiB into eu-west-1) | Migration Team | KUO-Discovery. Finnish data via Amsterdam region. | FI migrated
Week 19 | Migration | Start DataSync: Early Discovery NL (286 TiB after rehydration) | Migration Team | Biggest EU migration. Run over 4-5 nights. | NL Early Discovery migrated
Week 20 | Validation | Full EU inventory cross-check. German data residency confirmed. FR/NL/FI/HU data in eu-west-1. | Migration + Legal | Data residency audit report produced | EU inventory + residency PASS
Week 20 | Cutover | Switch all EU connectors to S3 Gateway. Disable Azure EU Blob write access. | App Teams | All APO and FIL connectors for EU sites | ALL EU LIVE on S3
PHASE 5 — CUTOVER, DECOMMISSION & OPTIMISATION (Month 6)
Week | Category | Task | Owner | Detail / Notes | Success Criteria
Week 21 | Cutover | Final validation: all sites reading/writing from S3 for 2 weeks. Zero Azure Blob writes. | Cloud Arch | CloudWatch confirms 0 bytes written to Azure | Zero-Azure confirmed
Week 21 | Cutover | Run full S3 Inventory vs original HubStor Master Report — final count match | Migration Team | 100% object count and size match required | FINAL INTEGRITY PASS
Week 21 | Commercial | Submit HubStor subscription cancellation. Provide data deletion confirmation if required. | Finance / Legal | Contract termination executed. Confirm no auto-renewal. | HubStor CANCELLED
Week 22 | Commercial | Terminate Azure Blob Storage accounts (all 5 regions). Download final invoices. | Finance / Cloud Arch | Azure cost stops. Final invoice received. | Azure Blob TERMINATED
Week 22 | Optimisation | Enable S3 Storage Lens — review storage efficiency, lifecycle policy effectiveness | Cloud Arch | Identify any objects in wrong tier; fix lifecycle rules | Storage Lens active
Week 22 | Optimisation | Enable Cost Anomaly Detection — alert if AWS bill exceeds $X,000 | Finance | Anomaly detector configured; tested with manual trigger | Cost alerts live
Week 23 | Monitoring | First clean month: AWS-only bill. Reconcile vs cost model. Report actual vs projected saving. | Finance | Report to stakeholders: actual vs $30,961 monthly saving target | Month 1 saving report
Week 24 | Closeout | Migration project retrospective. Update runbooks. Archive project docs. Celebrate! 🎉 | Programme Mgr | Lessons learned documented; team recognised | PROJECT CLOSED

## Financial Model (Jun26-Dec30)
FINANCIAL MODEL — Jun 2026 to Dec 2030 ¦ Migration Period + 4-Year AWS TCO
Jul 1 – Dec 31 2026: RAMPED migration — AWS grows as data moves. Jan 2027: full AWS saving realised.
MODEL INPUTS — all linked to Assumptions & Cost Comparison (change values there)
HubStor + Azure monthly cost (incl. Backup/DataBox $3,000/mo) | 29455.17
AWS Total monthly — storage + Gateway appliance + all infra | 4496.0458
One-time migration cost (total) | 121370.2342
Annual data growth rate (applied from 2028 onwards) | 5%
Monthly saving once fully on AWS (B5 − B6) | 24959.1242
Migration period (months: Jun–Dec 2026) | 6
AWS costs already paid during migration overlap (Jul–Dec 2026) | 20557.64 | Sum of AWS ramp-up costs during migration (Jul–Dec). These must also be recovered from savings.
Payback — months from Jan 2027 (migration cost + AWS overlap ÷ monthly saving) | 5.6864 | 5.7 months from Jan 2027 ≈ May 2027 ¦ (migration $121,370 + AWS overlap $24,791) ÷ monthly saving
PHASE 1 — MIGRATION PERIOD (Jul 1, 2026 – Dec 31, 2026) ¦ AWS ramps up month by month ¦ HubStor steps down as Azure regions deleted from Oct
Migration cost distributed across 6 months by activity: data-transfer costs follow the data ramp ¦ gateway installs match each site go-live ¦ testing & decommission back-loaded to Nov–Dec
# | Calendar Month | HubStor + Azure ($) [ramps ↓ from Oct] | AWS Total ($) [ramps ↑ all 6 months] | Combined Spend ($) | Migration Cost ($) [distributed by activity] | Migration Cost — What's included | Net Cumulative Saving ($) [vs doing nothing]
1 | Jul 2026 | 29455.17 | 1559.61 | 55068.83 | 24054.05 | 1 Gateway EC2 live (WLM pilot). S3~33%. DataSync migrating US-East. | -25613.66
2 | Aug 2026 | 29455.17 | 2700.82 | 49509.02 | 17353.03 | 2 Gateway ECs live (WLM+MWN). S3~61%. DataSync US regions. | -45667.51
3 | Sep 2026 | 29455.17 | 4202.83 | 62213.06 | 28555.06 | 3 Gateway ECs live (+CRP/UK). S3~99%. DataSync EU-UK. | -78425.4
4 | Oct 2026 | 26530.12 | 3174.44 | 52988.61 | 23284.05 | 4 Gateway ECs live (+FRI). S3 rebuilding after WestUS2+DE deletions. | -104883.89
5 | Nov 2026 | 11299.36 | 4423.89 | 30705.68 | 14982.43 | 5 Gateway ECs live (all sites). S3~98%. UKSouth+EastUS2 deleted. | -124290.21
6 | Dec 2026 | 4000 | 4496.05 | 21637.67 | 13141.62 | All 5 Gateways. S3=100%. All Azure decommissioned. Full steady state. | -141927.88
6 mo | MIGRATION TOTAL Jul–Dec 2026 | 130194.99 | 20557.64 | 272122.87 | 121370.24 | ↑ Extra cost vs doing nothing = AWS overlap ($24,791) + migration ($121,370) = $146,161 ¦ Payback ~4.5 months from Jan 2027 ≈ May 2027 | -141927.88
Migration cost breakdown: Jul $24,054 (setup+20% data) ¦ Aug $17,353 (15% data) ¦ Sep $28,555 (25% data — UK batch) ¦ Oct $23,284 (20% data) ¦ Nov $14,982 (12% data+testing) ¦ Dec $13,142 (8% data+decomm) → Total = $121,370
PHASE 2 — AWS ONLY (Jan 2027 – Dec 2030) ¦ HubStor fully terminated. Azure Blob = $0. Pure AWS spend.
AWS storage grows with data volume: 5% per year from 2028. Column E = monthly saving vs current HubStor baseline.
# | Calendar Month | HubStor + Azure ($) [= $0 from Jan 2027] | AWS Total ($) | Monthly Saving vs HubStor ($) | Cumul. Saving since Jan 2027 ($) | — | Net Cumulative Saving ($) [negative = recovering investment positive = net ahead vs doing nothing]
8 | Jan 2027 | 0 | 4496.0458 | 24959.1242 | 24959.1242 | 0 | -116968.7558
9 | Feb 2027 | 0 | 4496.0458 | 24959.1242 | 49918.2485 | 0 | -92009.6315
10 | Mar 2027 | 0 | 4496.0458 | 24959.1242 | 74877.3727 | 0 | -67050.5073
11 | Apr 2027 | 0 | 4496.0458 | 24959.1242 | 99836.4969 | 0 | -42091.3831
12 | May 2027 | 0 | 4496.0458 | 24959.1242 | 124795.6211 | 0 | -17132.2589
13 | Jun 2027 | 0 | 4496.0458 | 24959.1242 | 149754.7454 | 0 | 7826.8654
14 | Jul 2027 | 0 | 4496.0458 | 24959.1242 | 174713.8696 | 0 | 32785.9896
15 | Aug 2027 | 0 | 4496.0458 | 24959.1242 | 199672.9938 | 0 | 57745.1138
16 | Sep 2027 | 0 | 4496.0458 | 24959.1242 | 224632.1181 | 0 | 82704.2381
17 | Oct 2027 | 0 | 4496.0458 | 24959.1242 | 249591.2423 | 0 | 107663.3623
18 | Nov 2027 | 0 | 4496.0458 | 24959.1242 | 274550.3665 | 0 | 132622.4865
19 | Dec 2027 | 0 | 4496.0458 | 24959.1242 | 299509.4908 | 0 | 157581.6108
20 | Jan 2028 | 0 | 4720.8481 | 24734.3219 | 324243.8127 | 0 | 182315.9327
21 | Feb 2028 | 0 | 4720.8481 | 24734.3219 | 348978.1346 | 0 | 207050.2546
22 | Mar 2028 | 0 | 4720.8481 | 24734.3219 | 373712.4566 | 0 | 231784.5766
23 | Apr 2028 | 0 | 4720.8481 | 24734.3219 | 398446.7785 | 0 | 256518.8985
24 | May 2028 | 0 | 4720.8481 | 24734.3219 | 423181.1005 | 0 | 281253.2205
25 | Jun 2028 | 0 | 4720.8481 | 24734.3219 | 447915.4224 | 0 | 305987.5424
26 | Jul 2028 | 0 | 4720.8481 | 24734.3219 | 472649.7443 | 0 | 330721.8643
27 | Aug 2028 | 0 | 4720.8481 | 24734.3219 | 497384.0663 | 0 | 355456.1863
28 | Sep 2028 | 0 | 4720.8481 | 24734.3219 | 522118.3882 | 0 | 380190.5082
29 | Oct 2028 | 0 | 4720.8481 | 24734.3219 | 546852.7102 | 0 | 404924.8302
30 | Nov 2028 | 0 | 4720.8481 | 24734.3219 | 571587.0321 | 0 | 429659.1521
31 | Dec 2028 | 0 | 4720.8481 | 24734.3219 | 596321.354 | 0 | 454393.474
32 | Jan 2029 | 0 | 4956.8905 | 24498.2795 | 620819.6336 | 0 | 478891.7536
33 | Feb 2029 | 0 | 4956.8905 | 24498.2795 | 645317.9131 | 0 | 503390.0331
34 | Mar 2029 | 0 | 4956.8905 | 24498.2795 | 669816.1927 | 0 | 527888.3127
35 | Apr 2029 | 0 | 4956.8905 | 24498.2795 | 694314.4722 | 0 | 552386.5922
36 | May 2029 | 0 | 4956.8905 | 24498.2795 | 718812.7517 | 0 | 576884.8717
37 | Jun 2029 | 0 | 4956.8905 | 24498.2795 | 743311.0313 | 0 | 601383.1513
38 | Jul 2029 | 0 | 4956.8905 | 24498.2795 | 767809.3108 | 0 | 625881.4308
39 | Aug 2029 | 0 | 4956.8905 | 24498.2795 | 792307.5904 | 0 | 650379.7104
40 | Sep 2029 | 0 | 4956.8905 | 24498.2795 | 816805.8699 | 0 | 674877.9899
41 | Oct 2029 | 0 | 4956.8905 | 24498.2795 | 841304.1494 | 0 | 699376.2694
42 | Nov 2029 | 0 | 4956.8905 | 24498.2795 | 865802.429 | 0 | 723874.549
43 | Dec 2029 | 0 | 4956.8905 | 24498.2795 | 890300.7085 | 0 | 748372.8285
44 | Jan 2030 | 0 | 5204.735 | 24250.435 | 914551.1435 | 0 | 772623.2635
45 | Feb 2030 | 0 | 5204.735 | 24250.435 | 938801.5785 | 0 | 796873.6985
46 | Mar 2030 | 0 | 5204.735 | 24250.435 | 963052.0136 | 0 | 821124.1336
47 | Apr 2030 | 0 | 5204.735 | 24250.435 | 987302.4486 | 0 | 845374.5686
48 | May 2030 | 0 | 5204.735 | 24250.435 | 1011552.8836 | 0 | 869625.0036
49 | Jun 2030 | 0 | 5204.735 | 24250.435 | 1035803.3186 | 0 | 893875.4386
50 | Jul 2030 | 0 | 5204.735 | 24250.435 | 1060053.7536 | 0 | 918125.8736
51 | Aug 2030 | 0 | 5204.735 | 24250.435 | 1084304.1886 | 0 | 942376.3086
52 | Sep 2030 | 0 | 5204.735 | 24250.435 | 1108554.6236 | 0 | 966626.7436
53 | Oct 2030 | 0 | 5204.735 | 24250.435 | 1132805.0587 | 0 | 990877.1787
54 | Nov 2030 | 0 | 5204.735 | 24250.435 | 1157055.4937 | 0 | 1015127.6137
55 | Dec 2030 | 0 | 5204.735 | 24250.435 | 1181305.9287 | 0 | 1039378.0487
ANNUAL SUMMARY
Period | Calendar Year | HubStor + Azure ($) | AWS Total ($) | Gross Saving ($) | Migration / One-time ($) | Net Saving ($) | Cumul. Net Saving ($) | Row reference
Phase 1 | Jul–Dec 2026 (migration) | 130194.99 | 20557.64 | - | 121370.24 | -141927.88 | -141927.88 | R17–R22
Year 1 | Jan–Dec 2027 | 0 | 53952.5492 | 299509.4908 | 0 | 299509.4908 | 157581.6108 | R29–R40
Year 2 | Jan–Dec 2028 | 0 | 56650.1767 | 296811.8633 | 0 | 296811.8633 | 454393.474 | R41–R52
Year 3 | Jan–Dec 2029 | 0 | 59482.6855 | 293979.3545 | 0 | 293979.3545 | 748372.8285 | R53–R64
Year 4 | Jan–Dec 2030 | 0 | 62456.8198 | 291005.2202 | 0 | 291005.2202 | 1039378.0487 | R65–R76
TOTAL | Jun 2026 – Dec 2030 | 130194.99 | 253099.8713 | 1181305.9287 | 121370.24 | 1039378.0487 | 1039378.0487 | R17–R76

## Migration Architecture
MIGRATION ARCHITECTURE — AWS S3 File Gateway VM (EC2 t3.xlarge per site, recurring monthly)
PROPOSAL: File Gateway VM on EC2 t3.xlarge at each of the 5 sites. RECURRING cost: $130/mo/site × 5 = $650/mo from the moment each gateway goes live. MIGRATION (Jul–Dec 2026): DataSync migrates historical data Azure→S3; Gateway handles new writes from cutover. POST-MIGRATION (Jan 2027+): Gateway is sole connectivity layer. AWS Total = $4,496/mo.
DIAGRAM 1 — MIGRATION PERIOD (Jul–Dec 2026) ¦ DataSync migrates historical data ¦ Gateway EC2 launched per-site, handles new writes
DataSync (EC2 agent in AWS) migrates all Azure Blob data directly to S3 — Gateway not used for this. File Gateway EC2 launched site-by-site during migration; recurring $130/mo charge starts immediately. Gateway starts serving new writes from each site on its cutover date.
MIGRATION COST VALIDATION — One-time costs (Jul–Dec 2026)
Component | Role | One-time cost | How it works | Note
AWS DataSync | REQUIRED — migration tool | $14,321 | Reads Azure Blob → writes to S3. EC2 agent in AWS. $0.0125/GB × 1,145,641 GB. | ✅ Stops when migration completes.
Azure retrieval fees | REQUIRED — unavoidable | $22,739 | Azure charges: Cool $0.01/GB · Cold $0.03/GB · Archive $0.022/GB. Standard/Hot = free. | ✅ Negotiate Azure egress waiver first.
Azure egress charges | REQUIRED — unavoidable | $64,645 | Azure internet egress Azure→S3. Tiered $0.087→$0.05/GB. | ⚠ Request Azure credits — could save $30–60K.
File Gateway EC2 setup — 5 sites | REQUIRED — launch during migration | $2,500 | $500/site IT config × 5. Launch EC2 t3.xlarge, install Gateway, configure NFS/SMB shares. | ✅ Recurring $130/mo/site starts on launch. Gateway handles new writes, not migration data.
IAM · KMS · S3 bucket config | REQUIRED — Week 1 | $1,500 | 5 S3 buckets, lifecycle, Object Lock, IAM roles, KMS CMKs. | ✅ Complete before DataSync starts.
S3 PUT requests | REQUIRED — ingestion | $436 | $0.005–$0.05/1K objects. PUT directly to target storage class. | ✅ Use --storage-class flag in DataSync.
Testing · UAT · HubStor decommission | REQUIRED | $5,000 | UAT $3,000 + HubStor contract decommission $2,000. | ✅ 100% object match before each cutover.
Contingency 10% | RECOMMENDED | $10,921 | 10% buffer for egress spikes, retries, delays. | ✅ Standard for cross-cloud migrations.
GRAND TOTAL — ONE-TIME |  | ~$121,062 | Note: Gateway EC2 recurring cost ($650/mo) is separate — starts during migration, continues permanently.
DIAGRAM 2 — POST-MIGRATION STEADY STATE (Jan 2027+) ¦ Gateway EC2 $650/mo recurring ¦ AWS Total = $4,496/mo
File Gateway EC2 t3.xlarge ($130/mo/site × 5 = $650/mo) is a permanent RECURRING cost — same as paying for any cloud VM. This is the price of replacing HubStor connectors with a managed AWS connectivity layer. AWS Total = S3 $3,608 + Gateway EC2 $650 + ops $238 = $4,496/mo. This is consistent across Cost Comparison B39, Financial Model B6, and Executive Summary KPI tile.
ONGOING AWS COST VALIDATION — Monthly recurring from Jan 2027 ¦ $4,496/mo total
Resource | Needed? | Qty | Unit/mo | Monthly | Annual | Validation
S3 storage — all 5 tiers | YES | 1,041.7 TiB | $3,608 | $3,608 | $43,296 | Core storage. Standard/IA/Glacier IR/Deep Archive. Grows 5%/yr from 2028.
File Gateway EC2 — t3.xlarge × 5 | YES — RECURRING | ×5 EC2 | $130 | $650 | $7,800 | RECURRING monthly. EC2 compute for File Gateway VM at each site. Permanent connectivity layer.
Hardware Appliance | NOT PURCHASED | — | $0 | $0 | $0 | Physical unit not purchased. EC2 instance used instead. Assumptions C51=$130 (EC2 cost).
CloudWatch | YES | 1 | $31 | $31 | $372 | Dashboards, alarms, cost anomaly detection.
KMS keys | YES | 5 keys | $1 | $5 | $60 | SSE-KMS per region.
SNS alerts | YES | 1 | $2 | $2 | $24 | Budget and Gateway health alerts.
AWS Config | YES | 1 | $10 | $10 | $120 | S3 compliance monitoring.
S3 API operations | YES | 1 | $65 | $65 | $780 | PUTs from Gateway + GETs for retrieval.
Glacier retrieval | YES | 1 | $86 | $86 | $1,032 | 0.5% of archive/mo × $0.02/GB.
Internet egress | YES | 1 | $39 | $39 | $468 | ~10% retrieved externally.
S3 Transfer Acceleration | NOT NEEDED | — | $0 | $0 | $0 | Standard HTTPS sufficient.
DataSync | STOPPED | — | $0 | $0 | $0 | Migration done. EC2 agent terminated.
AWS TOTAL (Jan 2027+) |  |  |  | $4,496/mo | $53,952/yr | S3 $3,608 + Gateway EC2 $650 + CW $31 + KMS $5 + SNS $2 + Config $10 + API $65 + Glacier $86 + Egress $39 = $4,496

## Architecture & Connectivity
AWS S3 TARGET ARCHITECTURE — CONNECTIVITY & ACCESS DESIGN
Full HubStor replacement ¦ S3 File Gateway replaces all HubStor connectors ¦ Data residency preserved per region
STORAGE GATEWAY — HOW SITES CONNECT TO S3 POST-MIGRATION (replaces HubStor connectors)
Pattern | AWS S3 File Gateway (NFS/SMB shares) → replaces every HubStor connector agent at each site. S3-compatible. No application changes needed.
What it is | AWS S3 File Gateway (software VM) deployed on CRL's EXISTING on-prem server at each site (VMware / Hyper-V / KVM — same servers that run HubStor connector agents today). Presents NFS or SMB file shares to local applications. Caches recent files locally (1TB on existing server disk). Uploads new files to S3 automatically over HTTPS. NO Hardware Appliance purchased. Software is free — only S3 storage costs apply.
Archiving flow | Application saves file → File Gateway share → Gateway caches locally → Compresses & uploads to S3 bucket (correct storage class via lifecycle rule) → File stays accessible via share (cached read).
Retrieval flow | User requests file from Gateway share → Gateway checks local 1TB EBS cache → If cached: instant return → If not cached: fetches from S3 (Standard-IA: ms; Glacier IR: ms; Deep Archive: restore first ~12-48hr) → Returns file.
Sites & VMs | 5 Gateway VMs required: • WLM (EastUS2) → us-east-1 • RNO (WestUS2) → us-west-2 • UK sites (UKSouth) → eu-west-2 • NL/EU sites (WestEurope) → eu-west-1 • DE site (GermanyWestCentral) → eu-central-1
HubStor connectors replaced | All 17+ DPI connectors (APO-PR-APP-*), NAS connectors (MWN-PR-FIL-01, WLM-PR-FIL-05), and test connectors replaced by gateway shares. One Gateway per site serves all connectors at that site.
Migration tool | AWS DataSync for bulk one-time migration (Azure Blob → S3). DataSync handles checksums, retry, parallelism. Post-migration: Gateway handles all incremental writes; DataSync not needed.
S3 BUCKET STRATEGY
Bucket per region (5 buckets) | us-east-1: company-archive-us-east / us-west-2: company-archive-us-west / eu-west-2: company-archive-uk / eu-west-1: company-archive-eu / eu-central-1: company-archive-de
Prefix / key structure | s3://company-archive-{region}/{site-code}/{stor-name}/{year}/{month}/{filename} e.g., s3://company-archive-uk/CRP/EarlyDiscovery/2024/03/sample.raw
Storage class mapping | Standard/Hot → S3 Standard ¦ Cool → S3 Standard-IA (lifecycle Day 0) ¦ Cold → S3 Glacier Instant Retrieval ¦ Archive → S3 Glacier Deep Archive (PUT directly via --storage-class)
Lifecycle rules | Lifecycle rule 1: Objects with tag tier=cool → Standard-IA immediately. Rule 2: Objects with tag tier=archive → Glacier Deep Archive immediately. Rule 3: Incomplete multipart uploads → abort after 7 days.
Object Lock (GxP data) | Enable S3 Object Lock in Compliance mode on buckets holding GxP-regulated data (Safety Assessment, Microbial). Retention period = defined by QA/Regulatory team. Objects cannot be deleted or modified during retention.
Versioning | Enable ONLY on compliance/GxP buckets. Do NOT enable on pure archive buckets (versioning doubles storage cost for every overwrite).
Encryption | SSE-S3 (AES-256) at zero extra cost as baseline. Upgrade to SSE-KMS for GxP data requiring audit trail of key access. 1 KMS CMK per region = $5/month total.
VPC Gateway Endpoint | Deploy free S3 VPC Gateway Endpoint in each AWS region to route S3 traffic within AWS backbone — eliminates NAT Gateway data processing charges if any EC2-based processing is added later.
CONNECTIVITY OPTIONS
Option A — HTTPS/TLS (Recommended, chosen for this design) | Gateway VM uploads to S3 public endpoint over port 443 (HTTPS). Data is encrypted in transit (TLS 1.2+). No additional cost. All current sites have reliable internet. This is the chosen architecture.
Option B — AWS Site-to-Site VPN (optional add-on) | ~$0.05/hr per VPN connection = $36/mo. Use if security policy requires private connectivity. Can be added after cutover. Transit cost ~$0.01/GB within AWS. NOT required for launch.
Option C — AWS Direct Connect (optional premium) | Dedicated 1Gbps circuit ~$200-500/mo port cost. Use only if bandwidth becomes a demonstrated bottleneck after 3 months on Option A. Overkill for archive workloads.
Recommendation | Launch with Option A. Monitor Gateway CloudWatch metric WriteBytesPerSecond. If consistently >50MB/s sustained and latency is causing issues, evaluate Option B as next step.
REGION MAPPING — AZURE → AWS (data residency preserved)
Azure EastUS2 (Virginia, USA) | → AWS us-east-1 (N. Virginia) ¦ Sites: MWN, WLM ¦ Safety Assessment East, Microbial, RMS
Azure WestUS2 (Washington, USA) | → AWS us-west-2 (Oregon) ¦ Sites: RNO ¦ Safety Assessment West
Azure UKSouth (London, UK) | → AWS eu-west-2 (London) ¦ Sites: CRP, HAR, PTH, EDI ¦ UK data stays in UK ✓
Azure WestEurope (Amsterdam, NL) | → AWS eu-west-1 (Ireland) ¦ Sites: LEI, HER, GRO, KUO, SZG, FRE, LYO, EVR ¦ EU data stays in EU ✓
Azure GermanyWestCentral (Frankfurt) | → AWS eu-central-1 (Frankfurt) ¦ Sites: FRI ¦ German data stays in Germany (GDPR) ✓
GDPR / Data Sovereignty | No data crosses borders. UK data: eu-west-2 (London). German data: eu-central-1 (Frankfurt). All EU data in EU. S3 bucket region is enforced by SCP (Service Control Policy) blocking bucket creation in wrong regions.