## Discovery & Arivis Decommission
DISCOVERY DATA, ARIVIS, E3 LICENSES & SCHRÖDINGER ¦ AWS/AZURE DECOMMISSION ¦ FINANCIAL BUSINESS CASE
Prepared for Internal Review ¦ March 2026 ¦ Base case: Decommission all cost items. E3 Licenses (800 × $30/mo) & Schrödinger Azure ($1,800/mo): savings from Apr 2027 (employee transition). Arivis: customer pays from Apr 2027, fully decommissioned Q1 2028. Discovery AWS S3: purging/migration Q3 2027 – Q1 2028, savings from Q2 2028. SharePoint: 20TB freed — storage benefit only, no cost saving.
AWS ARIVIS (customer pays Apr 2027; fully decommissioned Q1 2028) |  | DISCOVERY AWS S3 (purging Q3 2027 – Q1 2028) |  | E3 LICENSES (800 × $30/mo from Apr 2027) |  | 5-YEAR NET SAVING (base case — 2026-2030)
$8,800 |  | $2,870 |  | $24,000 |  | $1,651,710
$8,800/mo native AWS (EC2+S3) customer takes over Apr 2027 |  | $2,870/mo 753.6 TiB post-migration purged Q1 2028 after sign-off |  | $24,000/mo 800 E3 licences × $30/mo saving from Apr 2027 |  | Gross $1,651,710 2026=$0 baseline Payback < 1 month
SCHRÖDINGER AZURE (2 RGs — from Apr 2027) |  | SHAREPOINT & OTHERS ¦ Note only — no cost saving
$1,800 |  | SharePoint 20TB storage freed — no direct cost impact, but free storage capacity available for other use.
$1,800/mo Schrödinger 2 RGs Azure saving from Apr 2027 |  | Storage benefit only. No recurring cost saving. Excluded from all financial calculations in this analysis.
Assumptions : "If direct migration decision made Oct 2026 (Azure/HubStor → customer storage), that migration expense is part of a separate initiative — NOT in this analysis. Only incremental AWS S3 bucket cost savings counted here."
SECTION 2 — 5-YEAR FINANCIAL PLAN (2026 – Dec 2030)
5-year plan: 2026–2030. 2026: No activity — baseline year ($0 saving). Arivis: customer assumes cost from Apr 2027, fully decommissioned Q1 2028 ($8,800/mo saving). E3 Licenses: 800 × $30 = $24,000/mo saving from Apr 2027 (employee transition). Schrödinger Azure: $1,800/mo saving from Apr 2027. Discovery AWS S3: $2,870/mo saving from Q2 2028 (purging/migration completes Q1 2028). SharePoint: 20TB freed — storage benefit only, no cost saving.
Period | Quarter | Arivis (AWS Cost) | E3 Licenses (Service Cost) | Schrödinger (Azure Cost) | Discovery (AWS S3 Cost) | Monthly Saving | Quarterly / Cumulative Saving
Q1 2027 | Jan-Mar 2027 (all still running — no savings) | $8,800 | -- | -- | $2,870 | -- | --
Q2 2027 | Apr-Jun 2027 ARIVIS → CUSTOMER E3 & SCHRÖDINGER START | Eliminated ($8,800 saved) | Eliminated ($24,000 saved) | Eliminated ($1,800 saved) | $2,870 | $34,600/mo | $103,800 / $103,800
Q3 2027 | Jul-Sep 2027 DISCOVERY PURGING STARTS (Arivis/E3/Schrödinger saving) | Eliminated ($8,800 saved) | Eliminated ($24,000 saved) | Eliminated ($1,800 saved) | $2,870 | $34,600/mo | $103,800 / $207,600
Q4 2027 | Oct-Dec 2027 DISCOVERY STILL PURGING (SharePoint — storage freed, no cost saving) | Eliminated ($8,800 saved) | Eliminated ($24,000 saved) | Eliminated ($1,800 saved) | $2,870 | $34,600/mo | $103,800 / $311,400
Q1 2028 | Jan-Mar 2028 ARIVIS FULLY DECOMMISSIONED DISCOVERY FINAL PURGE | Eliminated ($8,800 saved) | Eliminated ($24,000 saved) | Eliminated ($1,800 saved) | $2,870 | $34,600/mo | $103,800 / $415,200
2027 TOTAL | Jan-Dec 2027 | $79,200 (9 months) | $216,000 (9 months) | $16,200 (9 months) | $0 (still purging) | $311,400 | Cumulative: $311,400
Year | Period | Arivis Saving | E3 Licenses Saving | Schrödinger Saving | Discovery Saving | Gross Annual Saving | Cumulative Saving
2026 | Jan-Dec 2026 | $0 | $0 | $0 | $0 | $0 | $0
2027 | Jan-Dec 2027 | $79,200 | $216,000 | $16,200 | $0 | $311,400 | $311,400
2028 | Jan-Dec 2028 | $105,600 | $288,000 | $21,600 | $25,830 | $441,030 | $752,430
2029 | Jan-Dec 2029 | $105,600 | $288,000 | $21,600 | $34,440 | $449,640 | $1,202,070
2030 | Jan-Dec 2030 | $105,600 | $288,000 | $21,600 | $34,440 | $449,640 | $1,651,710
5-YR TOTAL | 2026–2030 | $396,000 | $1,080,000 | $81,000 | $94,710 | $1,651,710 | $1,651,710
PAYBACK < 1 month ($34,600 saving from first full month Apr 2027 — no purge cost) |  |  |  | FULL ANNUAL SAVING (from Q2 2028): $449,640/yr 5-YR GROSS: $1,651,710 5-YR NET: $1,651,710
FINANCIAL SUMMARY & RECOMMENDED ACTIONS |  |  |  |  | Value at risk: $34,600/mo until E3 & Schrödinger confirmed (Apr 2027 target)
Current combined cost | $37,470/month ($8,800 Arivis + $24,000 E3 + $1,800 Schrödinger + $2,870 Discovery) Note: SharePoint $250 excluded — storage benefit only, no cost saving. |  |  |  | Every month of inaction = $11,920 of avoidable spend.
Arivis decommission | Apr 2027: Customer assumes cost ¦ Q1 2028: Fully transferred/decommissioned from AWS |  |  |  | $8,800/mo saving from Apr 2027 (customer takes over).
E3 Licenses (800 × $30/mo) | Apr 2027 — employee transition to customer/new platform |  |  |  | $24,000/mo saving from Apr 2027.
Schrödinger Azure (2 RGs) | Apr 2027 — Azure RGs decommissioned |  |  |  | $1,800/mo saving from Apr 2027.
Discovery purging/migration target | Q3 2027 – Q1 2028 — written sign-off from all 12 site owners |  |  |  | $2,870/mo saving from Q2 2028.
SharePoint & Others | 20TB storage freed — storage benefit only. No recurring cost saving. |  |  |  | No financial saving. Excluded from all calculations.
Full monthly saving (from Q2 2028) | $37,470/month = $449,640/year |  |  |  | All 4 cost items decommissioned (SP excluded — no cost saving).
5-year gross saving (2026-2030) | $1,651,710 |  |  |  | 2026=$0 baseline. Savings start Q2 2027. SharePoint excluded.
5-year NET saving (base case) | $1,651,710 (gross saving — zero purge cost) |  |  |  | Pure service eliminations. No purge cost. Payback < 1 month.
RECOMMENDED ACTIONS | 1. Confirm E3 employee transition date with customer — target Apr 2027 2. Confirm Schrödinger Azure RG decommission with customer — target Apr 2027 3. Arivis: obtain written customer confirmation; initiate AWS cost handover Apr 2027; plan full decommission Q1 2028 4. Initiate sign-off process for all 12 Discovery site owners immediately (LEI, HER, GRO, KUO, SZG, FRE, LYO, EVR, FRI, CRP, HAR, PTH) 5. Legal: prepare data destruction certificate template for Discovery S3 purge