## Discovery & Arivis Decommission
DISCOVERY DATA & ARIVIS ¦ AWS DECOMMISSION ¦ FINANCIAL BUSINESS CASE
Prepared for Internal Review ¦ March 2026 ¦ Base case: PURGE both items from AWS (no data transfer). Arivis: purged Q2 2027 on new company confirmation. Discovery: purged Q3 2027 after data owner sign-off. Conditional: if new company requires data, add $30K migration + 1Q Discovery slip.
AWS ARIVIS (purged Q2 2027) |  | DISCOVERY AWS S3 (purged Q3 2027) |  | COMBINED MONTHLY SAVING (from Q3 2027 onwards) |  | 5-YEAR NET SAVING (base case — purge only)
$8,800 |  | $2,870 |  | $11,670 |  | $656,580
$8,800/mo native AWS (EC2+S3) purged Apr 2027 on new company confirmation |  | $2,870/mo 753.6 TiB post-migration purged Jul 2027 after sign-off |  | $140,040/yr from July 2027 pure AWS cost elimination |  | Gross $656,580 No purge cost Payback < 1 day
SECTION 1 — WHAT IS BEING PURGED AND WHEN
| AWS Arivis |  |  |  | Discovery Data — AWS S3
What it is | Arivis image analysis platform. Originally implemented natively on AWS (EC2 + S3). Active running service. |  |  |  | 753.6 TiB of Discovery site scientific data on AWS S3 (post-migration). LEI, HER, GRO, KUO, SZG, FRE, LYO, EVR · FRI · CRP, HAR, PTH
Monthly AWS cost | $8,800/month (EC2 + S3 — active AWS bill) |  |  |  | $2,870/month (S3 Standard / IA / Glacier — post-migration estimate)
Why purged | New company platform replaces Arivis capability. AWS instance and data no longer required once new company confirms. |  |  |  | Post-migration data no longer required on AWS. New company has confirmed they do not need this data.
Key prerequisite | Written confirmation from new company that they do not need Arivis data or functionality from AWS. This is the single gate for purge. |  |  |  | Written sign-off from ALL 12 site data owners: LEI, HER, GRO, KUO, SZG, FRE, LYO, EVR, FRI, CRP, HAR, PTH Confirming data is not required and can be permanently deleted.
What happens to data | AWS Arivis EC2 instance terminated. All S3 data deleted after confirmed backup by Arivis team. Irreversible. |  |  |  | All 753.6 TiB permanently deleted from AWS S3. Deletion certificate issued. Irreversible.
Target date | Q2 2027 (April 2027) |  |  |  | Q3 2027 (July 2027)
One-time cost | $0 (No data transfer. EC2 termination and S3 delete are standard AWS operations.) |  |  |  | $0 (No data transfer. S3 delete API calls have negligible cost.)
SECTION 2 — 5-YEAR FINANCIAL PLAN (Q2 2027 – Dec 2031)
Base case: purge only, no migration. Arivis saving from Q2 2027 ($8,800/mo). Discovery saving from Q3 2027 ($2,870/mo). Full $11,670/mo from July 2027. Conditional scenario shown separately below.
Period | Quarter | Arivis $8,800/mo | Discovery $2,870/mo | Total AWS Cost | Monthly Saving | Quarterly Saving | Cumul. Saving
Q1 2027 | Jan-Mar 2027 (both still running) | $8,800 | $2,870 | $11,670/mo | -- | -- | --
Q2 2027 | Apr-Jun 2027 ARIVIS PURGED | $0 | $2,870 | $2,870/mo | $8,800/mo | $26,400 | $26,400
Q3 2027 | Jul-Sep 2027 DISCOVERY PURGED | $0 | $0 | $0/mo | $11,670/mo | $35,010 | $61,410
Q4 2027 | Oct-Dec 2027 | $0 | $0 | $0/mo | $11,670/mo | $35,010 | $96,420
2027 TOTAL | Jan-Dec 2027 | $0 | $0 | $0 | Avg $8,035/mo | $96,420 | $96,420
Year | Period | Arivis Saving | Discovery Saving | Gross Annual Saving | One-time Cost | Net Annual Saving | Cumulative Net Saving
2027 | Jan-Dec 2027 | $79,200 | $17,220 | $96,420 | $0 | $96,420 | $96,420
2028 | Jan-Dec 2028 | $105,600 | $34,440 | $140,040 | One-time Cost | $140,040 | $236,460
2029 | Jan-Dec 2029 | $105,600 | $34,440 | $140,040 | -- | $140,040 | $376,500
2030 | Jan-Dec 2030 | $105,600 | $34,440 | $140,040 | -- | $140,040 | $516,540
2031 | Jan-Dec 2031 | $105,600 | $34,440 | $140,040 | -- | $140,040 | $656,580
5-YR TOTAL | 2027-2031 | $501,600 | $154,980 | $656,580 | $0 | $656,580 | $656,580
PAYBACK < 1 week ($11,670 first full month saving — no purge cost) |  |  |  | ANNUAL SAVING (from Q3 2027): $140,040/yr 5-YR GROSS: $656,580 5-YR NET: $656,580
$0
CONDITIONAL SCENARIO — If New Company Requires the Data
If the new company confirms they REQUIRE Discovery or Arivis data: add one-time migration cost of $30,000 (data export/transfer) AND Discovery purge slips by 1 quarter to Q4 2027. Arivis purge date unchanged (Q2 2027 — AWS infrastructure only).
Item | Base Case (purge only) | Conditional (new company needs data) | Difference | Note
Arivis purge date | Q2 2027 (Apr) | Q2 2027 (Apr) | No change | Arivis is AWS infrastructure. Purge unaffected by data requirement.
Discovery purge date | Q3 2027 (Jul) | Q4 2027 (Oct) | Slips 1 quarter | 1 extra quarter of Discovery S3 cost = $2,870 × 3 = $8,610.
Additional migration cost | $0 | $30,000 | −$30,000 | Data export / transfer to new company platform. One-time.
Total one-time cost | $0 | ~$30,000 | −$30,000 | Migration cost only. No purge labour cost.
2027 gross saving | $96,420 | $87,810 | −$8,610 | 1Q Discovery slip reduces 2027 saving.
2027 net saving | $92,420 | $53,810 | −$38,610 | After purge cost + migration cost.
5-year gross saving | $656,580 | $647,970 | −$8,610 | Only 2027 is affected — 2028 onwards identical.
5-year NET saving | $652,580 | $613,970 | −$38,610 | Net impact of data requirement = $38,610 reduction.
Payback | < 1 week | ~3 months | Longer payback | $34K one-time vs $11,670/mo full saving from Q4 2027.
CONCLUSION: Even if the new company requires data, the 5-year net saving remains $613,970 — still a very strong business case. The migration cost of $30,000 is recovered in under 3 months. This analysis should not materially change the decision to proceed.
SECTION 3 — KEY ASSUMPTIONS & RISKS
Assumptions
# | Assumption | Basis / Detail | Financial Impact if Wrong | Status
A1 | Arivis was natively implemented on AWS (EC2+S3) | Arivis has run on AWS since original implementation — not a migrated workload. Decommission is straightforward: terminate EC2, delete S3 data. No data transfer from another platform required. | No impact — confirmed fact. | Confirmed
A2 | Arivis AWS cost = $8,800/mo (EC2 + S3, no licence) | Active AWS bill covering EC2 compute and S3 storage only. Verify current figure from live AWS Cost Explorer before presenting externally. | Each $1,000/mo variance = $60,000 over 5 years. | Confirmed — verify from billing
A3 | New company has confirmed they do NOT need the data (key assumption) | This is the fundamental assumption underpinning the purge decision. Both Arivis and Discovery purge require explicit written confirmation from the new company that they do not require access to or copies of this data. If they need the data, see Conditional Scenario in Section 2. | If new company DOES need data: add $30,000 migration cost + Discovery slips 1Q → net 5-yr saving reduces by $38,610 but remains $613,970. | CRITICAL — written confirmation required
A4 | Arivis purged Q2 2027 — triggered by new company confirmation | No fixed calendar date. Triggered when new company provides written confirmation. EC2 termination and S3 deletion takes days once confirmed. Q2 2027 is the plan assumption. | Each quarter of delay = $26,400 avoidable cost. | Warning — track new company weekly
A5 | Discovery AWS S3 cost = $2,870/mo | Estimated AWS S3 storage cost for 753.6 TiB post-migration across Standard/IA/Glacier tiers. Monitor actual from AWS Cost Explorer once migration is live. | Each $1,000/mo variance = $60,000 over 5 years. Set anomaly alert at $4,000/mo. | Confirmed estimate — monitor
A6 | Discovery purged Q3 2027 — requires sign-off from all 12 site owners | LEI, HER, GRO, KUO, SZG, FRE, LYO, EVR, FRI, CRP, HAR, PTH must each provide written approval confirming data is not required and can be permanently deleted. Initiate this process immediately — gathering 12 approvals takes time. | Without sign-off: purge cannot proceed. Each quarter of delay = $8,610 avoidable cost. | CRITICAL — initiate sign-off now
A7 | Purge only — no data transfer unless new company requests it | Both Arivis and Discovery data will be permanently deleted from AWS. No vendor migration, no egress fees, no ingestion costs. If the new company requires data, the Conditional Scenario in Section 2 applies ($30K additional cost). | If conditional scenario triggered: net 5-yr saving reduces by $38,610 to $613,970. Still strongly positive. | Confirmed — purge is the plan
A8 | AWS pricing held flat 2027-2031 | S3 and EC2 pricing assumed constant. AWS has historically reduced storage prices. This is a conservative assumption that understates potential savings. | If AWS prices fall (likely): actual savings higher than modelled. | Conservative — upside only
Top 5 Risks
# | Risk | Likelihood | Impact | Score | Mitigation | Residual | Owner
R1 | New company confirmation delayed beyond Q2 2027 Arivis purge solely triggered by new company written confirmation. Each quarter of delay = $26,400 avoidable AWS cost. | HIGH | HIGH | CRITICAL | Escalate to Programme Director. Engage new company with specific deadline. Include live AWS Arivis cost in every client onboarding status update. Each week without confirmation is a quantified financial loss. | MEDIUM | Programme Director / New Company
R2 | New company states they need the data (conditional scenario triggered) If new company requires Discovery or Arivis data, $30K migration cost applies and Discovery purge slips 1 quarter. Net 5-yr saving reduces by $38,610. | MEDIUM | MEDIUM | MODERATE | Obtain written confirmation from new company on data requirements as first action — before any purge planning. If data is needed, activate conditional scenario budget ($30K). Still a very strong business case either way. | LOW | Programme Director / New Company
R3 | Discovery data purged without full governance sign-off 753.6 TiB permanently deleted without written approval from all 12 site data owners. Irreversible. GxP / GDPR breach possible. | LOW | CRITICAL | HIGH | Mandatory written sign-off from all 12 site owners before deletion. QA and Legal to review and sign off on destruction certificate. Initiate sign-off process immediately — do not wait for technical readiness. | LOW | Legal / QA / Data Owners
R4 | Arivis purge before new company platform is operational Research teams lose image analysis capability. No rollback possible after deletion. | LOW | HIGH | HIGH | Hard rule: new company platform must be live and user-validated for minimum 2 weeks before AWS EC2 termination and data deletion. | LOW | Cloud Arch / Arivis Team
R5 | Sign-off process for Discovery takes longer than expected Gathering written approval from 12 site owners across multiple countries may take several months. | MEDIUM | MEDIUM | MODERATE | Initiate sign-off process immediately — parallel to technical preparation. Legal to issue standard sign-off template. Track per-site completion weekly. Do not let sign-off become the critical path. | LOW | Programme Mgr / Legal
FINANCIAL SUMMARY & RECOMMENDED ACTIONS
Current combined AWS cost | $11,670/month ($8,800 Arivis + $2,870 Discovery S3) |  |  |  | Every month of inaction = $11,670 of avoidable spend.
Arivis purge target | Q2 2027 (April) — triggered by new company written confirmation |  |  |  | $8,800/mo saving from Apr 2027. 75% of total combined saving.
Discovery purge target | Q3 2027 (July) — written sign-off from all 12 site owners |  |  |  | Additional $2,870/mo from Jul 2027.
Full monthly saving (from Q3 2027) | $11,670/month = $140,040/year |  |  |  | Pure AWS cost elimination. No migration, no transfer fees.
One-time cost (base case) | $0 (no migration, no egress, no vendor fees) |  |  |  | No egress fees. No vendor fees. No IT labour charge.
Conditional: if new company needs data | +$30,000 migration cost + Discovery slips to Q4 2027 |  |  |  | Net 5-yr saving reduces by $38,610 → still $613,970. Strong ROI.
2027 gross saving (base case) | $96,420 (Arivis 9mo + Discovery 6mo) |  |  |  | Net $92,420 after purge cost.
5-year gross saving (2027-2031) | $656,580 |  |  |  | No migration cost. Pure service eliminations.
5-year NET saving (base case) | $652,580 (gross saving — zero purge cost) |  |  |  | Conditional scenario: $613,970. Both scenarios strongly positive.
RECOMMENDED ACTIONS | 1. Obtain written confirmation from new company — do they need any data? (gates everything) 2. Initiate sign-off process for all 12 Discovery site owners immediately 3. Legal: prepare data destruction certificate template 4. If new company needs data: budget $30K migration cost, activate conditional plan |  |  |  | Value at risk: $26,400 per quarter of new company confirmation delay