## Executive Summary
DISCOVERY SITES — HubStor → ON-PREM RESTORE ¦ Archive→Hot→Download ¦ NO AWS ¦ Germany first (PoC)
All archive data rehydrated to Azure Hot tier, then downloaded to respective on-prem sites. No AWS/S3. Azure Backup: proportional 70% share only. Germany PoC: May–Jul 2026.
ARCHITECTURE: Azure Blob (Archive/Cool/Cold) → Rehydrate to Azure Hot tier → AzCopy/Data Box download → On-prem NAS at each site ¦ HubStor decommissioned per site after 2-month grace ¦ NO AWS, NO Storage Gateway, NO Snowball ¦ ⚠ Large sites (Early NL 280 TiB, Early UK 335 TiB) require Azure Data Box Heavy — internet download impractical
CURRENT MONTHLY COST (HubStor + Backup 70% share) | POST-MIGRATION MONTHLY COST (On-prem only — zero Azure/HubStor) | FULL MONTHLY SAVING (Everything eliminated) | ONE-TIME MIGRATION COST (Rehydration + Hot storage + Egress)
$26,907/mo | $0/mo | $26,907/mo | $101,278
HubStor $24,807 + Backup $2,100/mo | All Azure Blob + HubStor licences cancelled | $322,881/yr ¦ 100% elimination | Payback: 3.8 months ¦ Data Box for large sites replaces egress
DISCOVERY SITES — STORAGE VOLUMES & CURRENT COSTS (Source: HubStor_Discovery.xlsx)
Site / Stor | Region | Total GiB | Total TiB | Arch GiB | Arch % | Monthly Cost ($) | Connectors
Discovery DE Files ★ PoC | Azure Germany West Central | 48444.2 | 47.3088 | 27777.02 | 57.34% | 1749.09 | 11
Early Discovery UK Files | Azure UK South | 343136.4 | 335.0941 | 259846.09 | 75.73% | 11581.08 | 43
Portishead Discovery UK | Azure UK South | 30378.19 | 29.6662 | 13987.21 | 46.04% | 1015.05 | 5
Early Discovery NL Files | Azure West Europe | 286607.02 | 279.8897 | 258259.67 | 90.11% | 9149.32 | 22
Discovery NL Files | Azure West Europe | 3949.53 | 3.857 | 3596.16 | 91.05% | 123.64 | 2
Discovery FI Files | Azure West Europe | 34060.12 | 33.2618 | 18747.67 | 55.04% | 1186.94 | 19
Discovery HU Files | Azure West Europe | 33.85 | 0.033057 | 0.1 | 0.2954% | 1.66 | 1
TOTAL |  | 746609.31 | 729.1107 | 582213.92 | 77.98% | 24806.78 | 103
AZURE BACKUP — DISCOVERY PROPORTIONAL SHARE (70.0% = $2,100/mo)
Azure Backup total: $3,000/mo covers all sites. Discovery share = 70.0% (746,609 GiB ÷ 1,066,705 GiB) = $2,100/mo. This cost is eliminated when all Discovery Azure Blob containers are deleted. Azure Backup itself is NOT in scope for this migration — requires separate investigation before any action.
ONE-TIME COST BREAKDOWN BY COMPONENT
Component | Amount ($) | Notes
Archive + Cool + Cold rehydration fees | 15480.2926 | $0.022/GB archive, $0.01/GB cool, $0.03/GB cold rehydration
Azure Hot tier storage (avg 1 month while downloading) | 15816.1523 | Data sits in Hot tier during download window
Azure egress to on-prem (tiered internet rates) | 43774.2199 | ⚠ Large sites: replace with Data Box — $0 egress. Egress cost reduced in practice.
On-prem NAS prep + AzCopy scripts + validation labour | 17000 | 7 sites × ~$2K NAS/script setup + $3K central validation
Contingency (10%) | 9207.0665 | Standard project buffer
★ GRAND TOTAL ONE-TIME COST | 101277.7313

## Assumptions
CENTRAL ASSUMPTIONS — DISCOVERY MIGRATION ¦ Yellow = input ¦ Architecture: Archive→Hot→On-prem ¦ No AWS
STORAGE VOLUMES (HubStor_Discovery.xlsx)
Parameter | Ref | Value | Unit | Source / Notes
Standard tier GiB |  | 7775.51 | GiB | Discovery actuals
Hot tier GiB |  | 2513.86 | GiB | Discovery actuals
Cool tier GiB |  | 150910.33 | GiB | Discovery actuals
Cold tier GiB |  | 3195.69 | GiB | Discovery actuals
Archive tier GiB |  | 582213.92 | GiB | Discovery actuals — 78% of total
GiB → GB conversion |  | 1.074 | × | 1 GiB = 1.074 GB
Total GiB (Discovery) |  | 746609.31 | GiB | Sum all tiers
Total TiB |  | 729.1107 | TiB | ÷ 1024
AZURE BACKUP — PROPORTIONAL SHARE
Parameter | Ref | Value | Unit | Source / Notes
Azure Backup total monthly |  | 3000 | $/mo | Full charge — disc + non-disc
Discovery GiB |  | 746609.31 | GiB | From Discovery file
Total GiB (all sites) |  | 1066704.64 | GiB | Master Report v5 grand total
Discovery ratio |  | 0.6999 |  | 746,609 ÷ 1,066,705
Azure Backup — Discovery share |  | 2100 | $/mo | $3,000 × 70.0%
TOTAL current monthly |  | 26906.78 | $/mo | HubStor + proportional Backup
AZURE PRICING — REHYDRATION & EGRESS
Parameter | Ref | Value | Unit | Source / Notes
Archive rehydration $/GB (Standard priority) |  | 0.022 | $/GB | ~15hr per batch. $0.01/GB expedited if needed.
Cool retrieval $/GB |  | 0.01 | $/GB | Per-GB read charge
Cold retrieval $/GB |  | 0.03 | $/GB | Per-GB read charge
Hot tier storage $/GB/mo |  | 0.02 | $/GB/mo | Temporary hot tier while downloading
Azure egress tier1 $/GB (0–10 TB) |  | 0.087 | $/GB | Internet download from Azure
Azure egress tier2 $/GB (10–50 TB) |  | 0.083 | $/GB | Volume discount tier
Azure egress tier3 $/GB (50–150 TB) |  | 0.07 | $/GB | Volume discount tier
Azure egress tier4 $/GB (>150 TB) |  | 0.05 | $/GB | Highest volume discount
Azure Data Box Heavy — flat fee |  | 2400 | $ | 100TB device. Zero egress. For large sites (>50 TiB).
DOWNLOAD SPEED & TIME ASSUMPTIONS
Parameter | Ref | Value | Unit | Source / Notes
Assumed download speed (conservative) |  | 200 | Mbps | ~90 GB/hr = 2.2 TiB/day continuous
Assumed download speed (optimistic) |  | 500 | Mbps | ~225 GB/hr = 5.4 TiB/day continuous
DE site download est. (47 TiB @ 200Mbps) |  | 22 | days | Round-the-clock. Fits in PoC Month 2.
FI site download est. (33 TiB @ 200Mbps) |  | 15 | days | Fits in 15-day window if link stable.
PTH UK download est. (30 TiB @ 200Mbps) |  | 13 | days | Fits in 15-day window.
Early NL download est. (280 TiB @ 200Mbps) |  | 130 | days | ⚠ USE DATA BOX HEAVY (2 devices)
Early UK download est. (335 TiB @ 200Mbps) |  | 155 | days | ⚠ USE DATA BOX HEAVY (3 devices)
AZURE DATA BOX HEAVY — LARGE SITE STRATEGY
Parameter | Ref | Value | Unit | Source / Notes
Data Box Heavy capacity |  | 100 | TiB usable | 100TB device — azure copies internally, ships
Data Box Heavy cost |  | 2400 | $/device | Flat fee. Zero egress. Includes return shipping.
Devices for Early NL (280 TiB) |  | 3 | devices | 3 × $2,400 = $7,200 vs $19,072 internet egress
Devices for Early UK (335 TiB) |  | 4 | devices | 4 × $2,400 = $9,600 vs $22,108 internet egress
Total Data Box saving vs internet egress |  | 24380 | $ | ($19,072+$22,108) − ($7,200+$9,600) = $24,380 saving

## Migration Plan & Costs
ONE-TIME MIGRATION COSTS — DISCOVERY SITES ¦ Architecture: Archive→Hot→On-prem ¦ No AWS
COMPONENT 1 — AZURE REHYDRATION CHARGES (moving data from Archive/Cool/Cold → Hot before download)
Standard rehydration priority: ~15hr per batch. Archive: $0.022/GB. Cool: $0.010/GB. Cold: $0.030/GB. Standard and Hot tiers: no rehydration fee.
Tier | GiB | GB (×1.074) | Retrieval $/GB | Rehydration Cost ($) | Notes
Standard | 7775.51 | 8350.8977 | 0 | 0 | Already hot — no fee
Hot | 2513.86 | 2699.8856 | 0 | 0 | Already hot — no fee
Cool | 150910.33 | 162077.6944 | 0.01 | 1620.7769 | Per-GB read charge to move to Hot
Cold | 3195.69 | 3432.1711 | 0.03 | 102.9651 | Per-GB read charge to move to Hot
Archive | 582213.92 | 625297.7501 | 0.022 | 13756.5505 | Standard rehydration — ~15hr/batch
SUBTOTAL — REHYDRATION |  |  |  | 15480.2926
COMPONENT 2 — AZURE HOT TIER STORAGE (while data sits in Hot waiting for download)
After rehydration, data must be downloaded within the billing period. Assume average 1 month in Hot tier. Larger sites may span 2 months. Hot = $0.020/GB/mo.
Data in Hot tier | Volume (GB) | Rate $/GB/mo | Months | Hot Storage Cost ($) | Notes
Arch+Cool+Cold (rehydrated to Hot) | 790807.6156 | 0.02 | 1 | 15816.1523 | Conservative 1-month avg; large sites may be 2 months
SUBTOTAL — HOT STORAGE |  |  |  | 15816.1523
COMPONENT 3 — EGRESS & DATA TRANSFER TO ON-PREM (internet egress or Data Box Heavy for large sites)
⚠ Sites >50 TiB should use Azure Data Box Heavy ($2,400/device, 100TB, ZERO egress fee). Early NL (280 TiB): 3 devices = $7,200. Early UK (335 TiB): 4 devices = $9,600. Saves $24,380 vs internet egress.
Site | GiB | GB Total | Method | Transfer Cost ($) | Notes
Discovery DE | 48444.2 | 52029.0708 | Internet AzCopy | 4323.335 | 47 TiB — internet feasible in ~23 days
Discovery HU | 33.85 | 36.3549 | Internet AzCopy | 0 | <1 GiB — trivial
Discovery NL (small) | 3949.53 | 4241.7952 | Internet AzCopy | 360.3362 | 3.9 TiB — ~2 days internet
Discovery FI | 34060.12 | 36580.5689 | Internet AzCopy | 3067.4872 | 33 TiB — ~15 days internet
Portishead UK | 30378.19 | 32626.1761 | Internet AzCopy | 2739.2726 | 30 TiB — ~13 days internet
Early Discovery NL ⚠ | 286607.02 | 307815.9395 | Data Box Heavy ×3 | 7200 | 280 TiB — Data Box: 3×$2,400=$7,200 vs $19,072 internet
Early Discovery UK ⚠ | 343136.4 | 368528.4936 | Data Box Heavy ×4 | 9600 | 335 TiB — Data Box: 4×$2,400=$9,600 vs $22,108 internet
SUBTOTAL — TRANSFER |  |  |  | 27290.431
COMPONENT 4 — ON-PREM SETUP & VALIDATION
Item | Qty | Unit ($) |  | Total ($) | Notes
On-prem NAS prep + AzCopy install per site | 7 | 1000 |  | 7000 | Verify NAS capacity (allow 1.5× GiB for dedup reversal), install AzCopy, test connectivity to Azure
Checksum validation scripts + metadata export | 1 | 2000 |  | 2000 | SHA256 baseline before download, validate after. HubStor catalog export for compliance records.
Stub recall per site | 7 | 500 |  | 3500 | Run HubStor stub recall before cutting over each connector
Testing + UAT + lessons doc | 1 | 3000 |  | 3000 | End-to-end validation, file-open checks, connector smoke tests
SUBTOTAL — SETUP |  |  |  | 15500
GRAND TOTAL — ONE-TIME MIGRATION COST
1. Rehydration (Archive→Hot) | 15480.2926
2. Hot tier storage (temp, during download) | 15816.1523
3. Transfer to on-prem (internet + Data Box) | 27290.431
4. On-prem setup + validation | 15500
Contingency (10%) | 7408.6876
★ GRAND TOTAL | 81495.5634
ROI & PAYBACK ANALYSIS
Current monthly cost (baseline) | 26906.78
Post-migration monthly cost (zero — all Azure/HubStor eliminated) | 0
Monthly saving | 26906.78
Annual saving | 322881.36
Payback (months from decommission) | 3
Year 1 net saving (annual − migration cost) | 241385.7966
3-year cumulative net saving | 887148.5166

## Migration Timeline
DISCOVERY MIGRATION TIMELINE ¦ Germany PoC: May–Jul 2026 ¦ 15 days/site Aug onwards ¦ Large sites via Data Box Heavy
Architecture: Azure Blob (Archive→Hot) → AzCopy/Data Box → On-prem NAS. NO AWS. HubStor decommissioned per site after 2-month grace period. Azure Backup: separate investigation.
⚠ DOWNLOAD TIME WARNING: Early Discovery NL (280 TiB) and Early Discovery UK (335 TiB) are too large for internet download within 15 days. STRATEGY: Use Azure Data Box Heavy (100TB/device). Azure copies internally, ships device to UK/NL DC. Zero egress. Allow 6-week windows for these sites. Start rehydration 30 days before planned download window.
Phase | Site / Activity | Start | End | Days | GiB | TiB | Cost/mo | DL hrs @200M | Key Activities | Owner | Decommission | Status
PoC M1 | Discovery DE — Foundation & Rehydration | 01 May 2026 | 31 May 2026 | 31d | — | — | — | — | Engage Azure AE (egress waiver). Inventory all FRI-Discovery stubs. Provision on-prem NAS (min 60 TiB free for post-dedup). Submit archive rehydration job to Azure Hot. No downloads yet — rehydration takes time. | Cloud Arch + Azure AE | — | Not Started
PoC M2 | Discovery DE — Download & Validate | 01 Jun 2026 | 30 Jun 2026 | 30d | — | — | — | — | Download rehydrated data from Azure Hot to on-prem NAS via AzCopy/Azure Storage Explorer. ~47 TiB at 200 Mbps ≈ 23 days continuous. Run stub recall in parallel. SHA256 checksum validation. First 100 GB sample checked before full download. | Migration Team + DE Admin | — | Not Started
PoC M3 | Discovery DE — Validate, Cutover & Lessons | 01 Jul 2026 | 31 Jul 2026 | 31d | 48444.2 | 47.3088 | 1749.09 | ~578 | Complete download + full checksum validation. Switch FRI-Discovery connector to local NAS share. Monitor 2 weeks. HubStor agent removed from Freiburg servers. PoC retrospective. Runbook updated for remaining sites. | Migration Team + DE Admin | 30 Sep 2026 | Not Started
Ph1 | Discovery HU — tiny store | 01 Aug 2026 | 15 Aug 2026 | 15d | 33.85 | 0.033057 | 1.66 | — | Negligible size (33 GiB). Rehydrate (archive ≈0). Download direct via AzCopy (<1 hr). Validate. Remove HubStor agent. Quick win. | Migration Team | 15 Oct 2026 | Not Started
Ph2 | Discovery NL — Groningen | 16 Aug 2026 | 31 Aug 2026 | 16d | 3949.53 | 3.857 | 123.64 | ~47 | 3.9 TiB — mostly archive. Rehydrate (3.5 TiB archive ≈ 15hr). Download ~47 hrs at 200 Mbps. Validate checksums. 2 connectors (GRO-Discovery). Remove agents. | Migration Team | 31 Oct 2026 | Not Started
Ph3 | Discovery FI — Kuopio | 01 Sep 2026 | 15 Sep 2026 | 15d | 34060.12 | 33.2618 | 1186.94 | ~406 | 33 TiB. Mixed tiers (cool+cold+archive). Rehydrate archive (18.3 TiB). Cold rehydration ($0.03/GB). Download ~400 hrs — requires sustained 200 Mbps link for 17 days. 19 connectors (KUO-Discovery). Consider AzCopy parallel threads. Flag if bandwidth insufficient: request Azure ExpressRoute quote. | Migration Team | 15 Nov 2026 | Not Started
Ph4 | Portishead Discovery UK | 16 Sep 2026 | 30 Sep 2026 | 15d | 30378.19 | 29.6662 | 1015.05 | ~362 | 30 TiB — mixed std+hot+cool+archive. Standard tier already hot (no rehydration). Rehydrate archive 14 TiB (~15hr). Download ~363 hrs. 5 connectors (PTH-Discovery). Data residency: UK on-prem. | Migration Team | 30 Nov 2026 | Not Started
Ph5 | Early Discovery NL — Leiden ⚠ LARGE | 01 Oct 2026 | 31 Oct 2026 | 31d | 286607.02 | 279.8897 | 9149.32 | ~3,420 | ⚠ 280 TiB — 90% archive. Rehydrate 252 TiB (CRITICAL: submit rehydration in batches starting Sep 1 — takes 5-7 days). Download ~3,420 hrs at 200 Mbps = 143 days. RECOMMEND: Azure Data Box Heavy (100TB) ordered to ship data physically. 2 devices cover 280 TiB. Zero egress fee. 22 connectors (LEI-EarlyDiscovery). Allow 6-week window. | Migration Team + Legal | 31 Dec 2026 | Not Started
Ph6 | Early Discovery UK ⚠ LARGEST | 01 Nov 2026 | 15 Dec 2026 | 45d | 343136.4 | 335.0941 | 11581.08 | ~4,094 | ⚠ 335 TiB — largest site. 43 connectors (CRP+HAR). MUST use Azure Data Box Heavy (2-3 devices). Download via internet would take ~170 days — impractical. Rehydrate 260 TiB in batches (start Oct 15). Physical device transfer: Azure copies to Data Box, ships to UK DC. Copy to on-prem NAS. Zero egress fee on Data Box. Allow 6-week window. | Migration Team + Legal | 28 Feb 2027 | Not Started
Ph7 | Full Validation & Decommission | 01 Jan 2027 | 31 Jan 2027 | 31d | — | — | — | — | Final integrity check all sites. HubStor agent removal verified at all sites. Cancel ALL HubStor/Cohesity licences. Delete Azure Blob containers per site (after 2-month grace). Cancel Azure Backup discovery share (separate decision). Project closed. | Finance + Legal | — | Not Started
SITE DECOMMISSION SCHEDULE — 2-month grace per site after data confirmed on-prem
Site | Region | Data Confirmed On-prem | Grace Period | HubStor Decommission | HubStor Agent Removed | Azure Blob Deleted | Note
Discovery DE ★ PoC | GermanyWestCentral | 31 Jul 2026 | 2 months | 30 Sep 2026 | 30 Sep 2026 | 30 Sep 2026 | PoC — first decommission
Discovery HU | WestEurope | 15 Aug 2026 | 2 months | 15 Oct 2026 | 15 Oct 2026 | 15 Oct 2026 | Tiny store
Discovery NL (Groningen) | WestEurope | 31 Aug 2026 | 2 months | 31 Oct 2026 | 31 Oct 2026 | 31 Oct 2026 | Small store
Discovery FI | WestEurope | 15 Sep 2026 | 2 months | 15 Nov 2026 | 15 Nov 2026 | 15 Nov 2026 | 19 connectors
Portishead Discovery UK | UKSouth | 30 Sep 2026 | 2 months | 30 Nov 2026 | 30 Nov 2026 | 30 Nov 2026 | 5 connectors
Early Discovery NL (Leiden) | WestEurope | 30 Nov 2026 | 2 months | 31 Jan 2027 | 31 Jan 2027 | 31 Jan 2027 | ⚠ Data Box Heavy — extended window
Early Discovery UK | UKSouth | 15 Dec 2026 | 2 months | 28 Feb 2027 | 28 Feb 2027 | 28 Feb 2027 | ⚠ Largest site — Data Box Heavy
ALL SITES — Full HubStor Decommission | All | 15 Dec 2026 | 2 months | 28 Feb 2027 | 28 Feb 2027 | 28 Feb 2027 | Cancel ALL licences. Azure Backup: separate.

## Financial Model
FINANCIAL MODEL — Discovery Sites ¦ May 2026 – Apr 2027 ¦ HubStor ramps to zero as sites decommission
No AWS cost. Migration cost front-loaded (May–Sep). HubStor eliminated site by site. Saving realised as each site decommissions.
MODEL INPUTS
Current monthly baseline (HubStor + Backup 70%) | 26906.78
Post-migration monthly cost (zero — no AWS) | 0
One-time migration cost (total) | 101277.7313
Metric | May 2026 | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | Total / Note
HubStor + Backup share ($) | 26906.78 | 26906.78 | 26906.78 | 26906.78 | 26906.78 | 25157.69 | 25032.39 | 22830.4 | 22830.4 | 13681.08 | 2100 | 2100 | 248265.86
One-time Migration Cost ($) | 30383.3194 | 25319.4328 | 20255.5463 | 15191.6597 | 10127.7731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101277.7313
Total Monthly Outgoing ($) | 57290.0994 | 52226.2128 | 47162.3263 | 42098.4397 | 37034.5531 | 25157.69 | 25032.39 | 22830.4 | 22830.4 | 13681.08 | 2100 | 2100 | 349543.5913
Monthly Saving vs Baseline ($) | -30383.3194 | -25319.4328 | -20255.5463 | -15191.6597 | -10127.7731 | 1749.09 | 1874.39 | 4076.38 | 4076.38 | 13225.7 | 24806.78 | 24806.78 | -26662.2313
Cumulative Net Saving ($) | -30383.3194 | -55702.7522 | -75958.2985 | -91149.9582 | -101277.7313 | -99528.6413 | -97654.2513 | -93577.8713 | -89501.4913 | -76275.7913 | -51469.0113 | -26662.2313 | -26662.2313

## Detailed Migration Plan
DETAILED MIGRATION PLAN — DISCOVERY SITES ¦ Archive→Hot→On-prem ¦ No AWS ¦ Germany PoC 3 months
Week | Category | Task | Owner | Detail / Notes | Success Criteria
POC MONTH 1 — GERMANY FOUNDATION (May 1–31, 2026) ¦ No data moved — engagement + rehydration started
Wk1 | Commercial | Engage Azure AE: confirm internet egress pricing, negotiate waiver or discount for Discovery migration. FastTrack Migration eligibility check. | Legal + Cloud Arch | Egress is the biggest variable cost. Get written pricing before committing. Ask about Azure Migrate support. | Azure AE engaged
Wk1 | Inventory | HubStor admin: export full FRI-Discovery connector inventory — all 11 connectors, mount paths, archive policies, stub counts per connector. | HubStor Admin | Critical for planning. Understand which connectors are active vs. inactive. | Connector inventory done
Wk1 | Inventory | Run HubStor capacity estimation for DE store: what is the post-dedup, post-decompress size? 47 TiB in Azure may be 60–140 TiB on-prem. | HubStor Admin | CRITICAL before NAS provisioning. Contact Cohesity AE for export size estimation tool. | Capacity estimate done
Wk2 | Infrastructure | Provision on-prem NAS at Freiburg site: minimum 1.5× estimated post-dedup size (at least 70 TiB free). Confirm 200+ Mbps internet bandwidth for Azure downloads. | DE IT + Network Team | NAS must be ready before Month 2 downloads. Bandwidth test: run AzCopy benchmark to Azure. | NAS ready, bandwidth tested
Wk2 | Rehydration | Submit archive rehydration job for FRI-Discovery to Azure Hot tier. Standard priority: $0.022/GB, ~15hr per batch. Submit all 11 connector batches staggered. | HubStor Admin + Azure Admin | Do NOT wait for full rehydration before starting Month 2 — batch and overlap. Monitor in Azure Portal > Storage > Lifecycle. | Rehydration jobs submitted
Wk2 | Stub Recall | Run HubStor stub recall for all FRI-Discovery connectors. Stubs point to HubStor — must be full files before removing agent. | HubStor Admin + DE Admin | Run parallel to rehydration. Log all stub files recalled. | Stub recall started
Wk3 | Engagement | Cohesity AE: formal kick-off for decommission planning. Confirm decommission process, notice period, export runbook. State: full Discovery decommission by Feb 2027. | Programme Mgr | Get written decommission runbook. Confirm notice period does not block Dec 2026 target. | Cohesity engaged
Wk3 | Compliance | Legal team: review Discovery data retention policy, legal holds, eDiscovery obligations. Some Discovery data may have regulatory holds — must not be deleted. | Legal + Compliance | Sign-off required before any Azure Blob deletion. Flag any data under legal hold. | Compliance review started
Wk4 | Testing | AzCopy connectivity test: download 10 GB test batch from Azure Hot (FRI-Discovery) to Freiburg NAS. Measure actual throughput. Validate checksum. | Migration Team + DE Admin | Real throughput may differ from theoretical. Adjust download timeline accordingly. | Throughput MEASURED
Wk4 | Metadata | Export HubStor metadata catalog for FRI-Discovery (CSV/XML): all items, retention dates, custodians, legal holds. Store permanently for compliance. | HubStor Admin | This catalog is the compliance record after HubStor is decommissioned. Must be retained. | Catalog exported
POC MONTH 2 — GERMANY DOWNLOAD & VALIDATE (Jun 1–30, 2026) ¦ ~47 TiB download to Freiburg NAS
Wk5 | Download | Begin full AzCopy download of FRI-Discovery from Azure Hot to Freiburg NAS. Run AzCopy with --recursive --preserve-smb-info. Use parallel threads (--concurrency 32). | Migration Team + DE Admin | 47 TiB at 200 Mbps ≈ 23 days continuous. Start immediately — must complete before Month 3. | Download started
Wk5 | Download | Generate SHA256 checksums for all downloaded files on NAS as they arrive. Compare against Azure Blob MD5 hashes. | Migration Team | Automate with checksum script. Any mismatch: re-download that object. | Checksums running
Wk6 | Download | Monitor download progress daily. Check AzCopy log for errors. Verify Hot tier objects are still available (not auto-tiered back). | DE Admin | Set Azure lifecycle rule to pin Hot tier during migration window. Alert if objects move. | Download 50% milestone
Wk7 | Validation | Download complete. Run full checksum comparison: NAS vs Azure Blob MD5. 100% match required. | Migration Team | Zero discrepancy. If any mismatch: re-download and recheck. | CHECKSUM VERIFIED
Wk7 | Validation | Open 20 representative files of each type (PDF, DOCX, images, case files) from NAS. Confirm readable and uncorrupted. | DE Admin + App Teams | All files open correctly. No corruption. Test search/index if applicable. | Files readable on NAS
Wk8 | Validation | Confirm on-prem NAS is accessible to all users/applications that previously accessed FRI-Discovery via HubStor share. Update any hardcoded paths. | App Teams + DE Admin | Applications must work from NAS before HubStor agent is removed. | App access confirmed
POC MONTH 3 — GERMANY CUTOVER & LESSONS (Jul 1–31, 2026) ¦ HubStor agent removed, PoC signed off
Wk9 | Cutover | Switch all 11 FRI-Discovery connectors from HubStor share to local NAS share. Update connector target paths. Monitor for 1 week. | DE Admin + App Teams | New writes go to NAS. Reads served from NAS. HubStor no longer used. | Connectors switched
Wk9 | Cutover | Monitor FRI-Discovery NAS for 2 weeks: write performance, read latency, storage growth. Zero errors. | Cloud Arch + DE Admin | Target: equivalent performance to HubStor. Alert on errors. | 2-week soak PASS
Wk10 | Decommission | Remove HubStor agent from all Freiburg servers. Disable FRI-Discovery connectors in HubStor console. | HubStor Admin + DE Admin | Do NOT delete Azure Blob containers yet — 2-month grace period starts now (ends Sep 30). | HubStor agent REMOVED
Wk12 | PoC Closeout | PoC retrospective: document throughput achieved, NAS sizing accuracy, dedup expansion ratio, lessons for remaining sites. Update runbook. | Programme Mgr | Signed retrospective. Updated runbook circulated. Per-site NAS size estimates revised. | POC SIGNED OFF ✓
PHASE 1 — DISCOVERY HU (Aug 1–15, 2026) ¦ 33 GiB ¦ trivial
Wk13 | Migration | Rehydrate (archive ≈0.1 GiB — negligible). AzCopy download 33 GiB — completes in minutes. | Migration Team | Quickest site. Good confidence builder for remaining sites. | HU downloaded
Wk13 | Cutover | Switch SZG-Discovery connector to NAS. Validate. Remove HubStor agent. | App Teams + HU Admin | 1 connector. Quick validation. | HU LIVE on NAS
PHASE 2 — DISCOVERY NL SMALL (Aug 16–31, 2026) ¦ 3.9 TiB ¦ Groningen
Wk14 | Migration | Rehydrate 3.5 TiB archive (~15hr). AzCopy download 3.9 TiB ≈ 47 hrs at 200 Mbps. 2 connectors (GRO-Discovery). | Migration Team | Run overnight. Monitor AzCopy log. | NL-small downloaded
Wk15 | Cutover | Switch GRO-Discovery connectors to NAS. Validate. Remove HubStor agents. | App Teams + NL Admin | 2 connectors. Both tested. | NL-small LIVE on NAS
PHASE 3 — DISCOVERY FI (Sep 1–15, 2026) ¦ 33 TiB ¦ Kuopio ¦ 19 connectors
Wk16 | Migration | Rehydrate: 18.7 TiB archive + 3.2 TiB cold (⚠ cold = $0.03/GB). Submit rehydration batches by KUO-Discovery connector staggered. Stub recall for all 19 connectors. | Migration Team + FI Admin | Cold rehydration is expensive per-GB. Budget confirmed. Rehydration window: ~2 days for all batches. | FI rehydration started
Wk16 | Migration | AzCopy download FI to Kuopio NAS. 33 TiB ≈ 400 hrs — requires sustained link 16+ days. Start immediately after rehydration. | Migration Team | Monitor daily. Alert if speed drops below 100 Mbps. Consider AzCopy premium bandwidth or ExpressRoute if bottleneck. | FI download started
Wk17 | Cutover | FI download complete (may overlap into Sep 16 Phase 4 window). Validate checksums. Switch 19 KUO connectors to NAS. | Migration Team + FI Admin | Validate before connector switch. May need 1-day extension. | FI LIVE on NAS
PHASE 4 — PORTISHEAD DISCOVERY UK (Sep 16–30, 2026) ¦ 30 TiB ¦ 5 connectors
Wk18 | Migration | Rehydrate: 14 TiB archive (~15hr). Standard tier (7.7 TiB) needs no rehydration. AzCopy download 30 TiB ≈ 363 hrs. | Migration Team + UK Admin | Mixed tiers. GDPR — data stays in UK on-prem. Confirm UK on-prem NAS is in UK. | PTH rehydration started
Wk18 | Migration | Download Portishead data to on-prem UK NAS. 30 TiB ≈ 363 hrs = 15 days — tight but feasible at 200 Mbps. | Migration Team | Monitor bandwidth. If < 150 Mbps: extend 3 days. Alert Programme Mgr. | PTH download complete
Wk19 | Cutover | Switch 5 PTH-Discovery connectors to NAS. GDPR data residency (UK on-prem) confirmed. Validate. Remove agents. | App Teams + UK Admin + Legal | Legal sign-off on GDPR compliance. | PTH LIVE on NAS
PHASE 5 — EARLY DISCOVERY NL (Oct 1–31, 2026) ¦ 280 TiB ¦ ⚠ Data Box Heavy × 3
Wk20 | Rehydration | ⚠ START REHYDRATION NOW (Sep 1 — 30 days before download window). Submit rehydration for 258 TiB archive (LEI-EarlyDiscovery). Stagger across 22 connectors in batches. | Migration Team + Azure AE | Largest EU store. Rehydration takes 5-7 days for all batches. MUST start Sep 1 to be ready Oct 1. | NL-large rehydration STARTED Sep 1
Wk20 | Hardware | Order 3× Azure Data Box Heavy (100TB each). Azure copies Hot tier data internally. Ships to Leiden NL DC. Zero egress. | Cloud Arch + Azure AE | Order early — device availability varies. 3 devices cover 280 TiB. $7,200 total vs $19,072 internet egress. | Data Box Heavy ordered
Wk21 | Transfer | Azure copies rehydrated NL data to Data Box devices (internal Azure transfer — fast, no egress). Devices shipped via FedEx to Leiden DC. | Azure (automated) + Facilities | Track in Azure Portal. Brief facilities for pallet receipt (each device ~250kg). | Devices shipped
Wk22-25 | Transfer | Data Box devices arrive. Connect to Leiden NAS via 40GbE. Copy 280 TiB to NAS — ~3 days per device at 40GbE. | Migration Team + NL Admin | Copy all 3 devices in parallel if NAS supports it. Generate checksums. | NL-large on NAS
Wk26 | Cutover | Validate checksums (280 TiB). Switch 22 LEI-EarlyDiscovery connectors to NAS. GDPR residency (NL on-prem) confirmed. Remove agents. | App Teams + NL Admin + Legal | Legal sign-off. 22 connectors — test in batches. | NL-large LIVE on NAS
PHASE 6 — EARLY DISCOVERY UK (Nov 1 – Dec 15, 2026) ¦ 335 TiB ¦ ⚠ Data Box Heavy × 4 ¦ 43 connectors
Wk24 | Rehydration | ⚠ START REHYDRATION Oct 15 (2 weeks before download). Submit rehydration for 260 TiB archive (CRP+HAR EarlyDiscovery). Stagger 43 connectors. | Migration Team + Azure AE | Largest site. Rehydration: 5-7 days. Must complete before devices arrive. | UK-large rehydration STARTED Oct 15
Wk24 | Hardware | Order 4× Azure Data Box Heavy. 4 × 100TB = 400TB capacity covers 335 TiB. $9,600 total vs $22,108 internet egress. | Cloud Arch + Azure AE | Order in parallel with Phase 5 Data Box if possible. 2 orders of 2 devices each. | Data Box Heavy ordered
Wk25-29 | Transfer | Azure copies UK data to Data Box devices. Ships to UK DC. Copy 335 TiB to UK NAS via 40GbE. Validate checksums. | Migration Team + UK Admin | 4 devices × 3 days each. Run sequentially or in parallel. | UK-large on NAS
Wk30 | Cutover | Validate all 335 TiB on UK NAS. Switch 43 connectors (CRP+HAR EarlyDiscovery). GDPR UK data residency confirmed. Remove all agents. | App Teams + UK Admin + Legal | Largest connector count (43). Test in site batches. Legal GDPR sign-off. | UK-large LIVE on NAS
PHASE 7 — FULL VALIDATION & DECOMMISSION (Jan–Feb 2027) ¦ Well within Apr 2027 target
Wk31 | Validation | Final cross-check: all 7 Discovery stores confirmed on on-prem NAS. HubStor agents removed at all sites. Zero HubStor reads confirmed. | Cloud Arch | CloudTrail / HubStor access logs confirm zero activity. | ALL sites on NAS
Wk31 | Commercial | Cancel ALL HubStor/Cohesity Discovery licences. Written decommission confirmation from Cohesity AE. | Finance + Legal | Saves $24,807/mo in HubStor storage costs. | HubStor CANCELLED
Wk32 | Decommission | Delete Azure Blob containers per site as 2-month grace periods expire: DE(Sep30)→HU(Oct15)→NL-sm(Oct31)→FI(Nov15)→PTH(Nov30)→NL-lg(Jan31)→UK(Feb28). | Cloud Arch + Finance | Per-site: confirm on-prem data intact before deletion. Download Azure data erasure certificate. | Azure Blob DELETED
Wk32 | Compliance | Azure Backup (Discovery share $2,100/mo): this requires SEPARATE decision — do not cancel until scope understood. Flag as open workstream. | Legal + Finance | Azure Backup may cover data not in HubStor scope. Investigate before any action. | Azure Backup: TBD
Wk33 | Closeout | Project closed. Retrospective. Actual cost vs projected reported to stakeholders. All metadata catalogs archived permanently. | Programme Mgr | $26907/mo saving confirmed. Lessons documented. | PROJECT CLOSED 🎉

## Cost Comparison
AZURE HUBSTOR vs ON-PREM — DISCOVERY COST COMPARISON ¦ Archive→Hot→Download ¦ No AWS
MONTHLY COST — CURRENT vs POST-MIGRATION
Cost Item | Current (Azure/HubStor) | Post-Migration (On-prem) | Monthly Saving | Annual Saving | Notes
HubStor Storage — Discovery sites | 24806.78 | 0 | 24806.78 | 297681.36 | Fully eliminated after decommission
Azure Backup (70% Discovery share) | 2100 | 0 | 2100 | 25200 | Eliminated — Discovery Backup share ceases
On-prem NAS operating cost (est.) | 0 | 500 | -500 | -6000 | Power, maintenance, support — est. $500/mo
TOTAL | 26906.78 | 500 | 26406.78 | 316881.36 | 98.1% saving
DATA BOX HEAVY vs INTERNET EGRESS — LARGE SITE COMPARISON
Site | Size | Internet Egress ($) | Data Box Method | Data Box Cost ($) | Saving ($)
Early Discovery NL | 280 TiB | 19072 | 3× Data Box Heavy | 7200 | 11872
Early Discovery UK | 335 TiB | 22108 | 4× Data Box Heavy | 9600 | 12508
TOTAL DATA BOX SAVING |  |  |  |  | 24380
ROI & PAYBACK
One-time migration cost (total incl. contingency) | 101277.7313
Effective monthly saving (after $500/mo NAS ops) | 26406.78
Annual saving | 316881.36
Payback period (months from full decommission) | 3.8353
Year 1 net saving (annual − migration cost) | 215603.6287
3-year cumulative net saving | 849366.3487