## Milestone Tracker
CMDB — Improve Cloud Resource Ownership ¦ Milestone Tracker
Initiative #2104 ¦ Milestone Owner: Abhijit Chakraborty ¦ Azure US · Azure China · AWS ¦ May 1 – Jun 20, 2026
Earliest Start |  | Latest End Date |  | Late Milestones |  | Milestones Done |  | Overall Status
May 1, 2026 |  | Jun 20, 2026 |  | 0 |  | 0 / 5 |  | In Planning
⭐ Gold = Global Technology 💰 Purple = Money Step 🦠 Teal = Org Effectiveness (Health) ¦ Yellow cells = your inputs
MILESTONES
Ref # | Milestone Name | Type | Owner | Team | Start Date | End Date | Status | % Done | Notes / Next Step
6240 | Full audit report of missing owners by cloud platform | Global Technology | Abhijit Chakraborty | NTT Team | May 1, 2026 | May 31, 2026 | Not Started | 0% | Baseline audit — Azure US, Azure China & AWS
6279 | Establish a scalable, repeatable process for owner assignment and validation | Global Technology | Abhijit Chakraborty | CMDB Team | May 1, 2026 | May 31, 2026 | Not Started | 0% | Process design & tooling confirmed
6281 | Achieve 100% owner field completion | Global Technology | Abhijit Chakraborty | Both | May 19, 2026 | Jun 9, 2026 | Not Started | 0% | Target: 95%+ completion across all platforms
7663 | Actual first wave of implementation of improvements coming from the improved owner | Money Step | Abhijit Chakraborty | Both | Jun 9, 2026 | Jun 20, 2026 | Not Started | 0% | Savings flow from July 2026 onwards
6344 | Final sign-off, process documentation | Org Effectiveness (Health) | Abhijit Chakraborty | Both | Jun 17, 2026 | Jun 20, 2026 | Not Started | 0% | Runbook live; CMDB alerts active; archived
Status dropdown: Not Started · In Progress · Complete · Blocked · Deferred ¦ Team dropdown: NTT Team · CMDB Team · Both ¦ Enter % Done as a decimal (0.5 = 50%) or use 0–1